## MT QUESTIONS
165 RANDOLPH - QUESTIONS ON THE 16 SEP MASTER DEVELOPMENT BUDGET
Matthew Teper, 17 Sep 2026. Every question is written beside the line it refers to, in a new right-hand column on each of your sheets. Highlighted cells are the ones asked about. None of your cells have been changed.
WHERE THE NUMBERS STAND
Master Development Budget, 16 Sep | 89084591 | $1,202/SF on 74,100 SF; your sheet shows $655/SF on 135,953
Our V3, rebuilt on the measured RFEM steel | 77897555 | $1,051/SF. Same programme, 997.2 short tons priced by the ton
Yours after the corrections that survive the takeoff | 77247828 | 0.8% from ours
Trade cost reconciliation, our extract vs your D25 | 0 | 309 lines, variance $0.00
THE FIVE WE NEED FIRST
-1. | Budget Summary D67 - the contingency formula is 10% of the whole project, not of soft costs and FF&E as labelled.
0. | Budget Summary D30 - escalation on the building is blank.
1. | Budget Summary D26 - what is in the $12,000,000 and when is it priced? We expect it to go UP.
2. | General Conditions tab vs Breakdown division 013000 - the same function in two places, $6,175,000 combined.
3. | Breakdown 015800-1 - the $4,000,000 lump vs the $2,589,800 of backup beneath it.
TWO THINGS WE HAD WRONG AND ARE WITHDRAWING
The roof: we had assumed a lift. The RFEM model is a rebuild - 62.4% of column steel starts at grade, all 517 truss members are new at +56.5 to +64.5 ft. Your 74,000 SF of roof demolition is the method, not an error.
The area: we had called 135,953 SF wrong. We can no longer prove that - the model carries 146,508 SF gross. We are now only asking where the number comes from, and for one agreed area schedule derived from the test fit.
INDEX OF EVERY QUESTION
Sheet | Cell | Your line | Our question
Budget Summary | D21 | Parking Garage - 260/spaces | Formula is =86*25000 but the label says 260 spaces. Which is right? And is off-site parking in this deal at all? We carry none.
Budget Summary | D26 | Trade Costs To Be Priced | What scope is inside the $12,000,000, and when can it be priced? Our measured structure alone is $16,710,249 (997.2 short tons off the RFEM takeoff), and this plug also has to cover millwork, doors, glazing, tile, fireproofing and drywall. We expect it to go UP when priced.
Budget Summary | D27 | General Conditions | $3,141,000 here PLUS $3,034,000 of division 013000 inside the trade cost = $6,175,000, 12.36% of trade. Schimenti ran 7.80% and 8.90% at 555 Johnson. Which is the one we are paying? We hold 8.5%.
Budget Summary | D28 | OH&P 9%
Budget Summary | D29 | Contractor Contingency 10%
Budget Summary | D30 | Escalation | Blank in all three versions of this file, while the parking garage gets 5% on D22. On a 20-month programme what should the building carry? We hold 10%.
Budget Summary | I31 | $/SF | I31 divides by 135,953. On the 74,100 SF footprint this is $859/SF.
Budget Summary | D45 | Project Management (Live Nation) | This is our own team, not Live Nation. Same $520,000 in our budget - just the label.
Budget Summary | D67 | Soft Costs & FFE Contingency 10% | Label says Soft Costs & FFE. Formula is =(D23+D31+D47+D65)*0.1 = 10% of the WHOLE PROJECT, on top of the contractor contingency already inside D31. As labelled it would be $1,507,723. $578,648 of it is contingency on contingency. Which is intended?
Budget Summary | D69 | Total Capital | Ours: V3 $77,897,555 on the same programme, measured steel. Apply only the corrections that survive the takeoff and this cell becomes about $77,247,828 - 0.8% from ours.
Budget Summary | D71 | $ PER SF | Divides by 135,953 SF. Where does that number come from? We cannot find a schedule or calculation behind it. On 74,100 SF this total is $1,202/SF. Both are true; please label which.
Budget Summary | B8 | SF: 135,953 | 135,953 SF appears here and in 6 formula cells. Source? The RFEM model has 146,508 SF gross / 120,119 SF enclosed floor; the test fit governs at 74,100 SF footprint. 555 Johnson at $208.63/SF is 134,993 SF - please rule that out.
Budget Summary | A9 |  | Dated 7 Sep; the Breakdown tab says 16 Sep. Which is current?
General Conditions | E13 |  | This tab is the best-evidenced page in the file and we would rather build on it than argue with it. Is the $3,141,000 the ONLY place general conditions lives? Division 013000 on the Breakdown carries site office, field tech, safety, toilets, protection, clean-up, rubbish and final clean for another $3,034,000.
General Conditions | C4 |  | 90 weeks - is that construction only, or does it include pre-con and closeout? Can we see it as a rate x duration so that shortening the programme visibly shortens the cost?
General Conditions | C9 |  | Three superintendents for the full 90 weeks each - all three for the whole period, or overlapping phases?
Building & Fit-out Breakdown | F23 | Project Labor $2,000,000 | Crew, rate and weeks? The General Conditions tab already funds three supers + a general super for 90 weeks. No quantity behind this line.
Building & Fit-out Breakdown | F16 |  | What is included in Field Technology at $200,000?
Building & Fit-out Breakdown | F27 | 013000 subtotal $3,034,000 | All of this division reads as general conditions. Is it meant to sit inside trade cost AND under the GC line on the summary? We think it is one function in two places.
Building & Fit-out Breakdown | F30 | Sidewalk bridge $4,000,000 | The lump says $4,000,000. The two rows beneath it - 1,126 LF @ $500 and 27,024 SF @ $75 - foot to $2,589,800. Which is right? And how many LF of PUBLIC sidewalk does the building front? A shed is only required where there is one; the alleys and lot lines have none. We carry 1,089 LF perimeter x $210 erected + 24 months rental.
Building & Fit-out Breakdown | F33 | Interior scaffolding $2,000,000 | What is being staged, at what rate, for how many weeks? The high roof is only 8.65 lb/SF of short-span W12/W6 framing - not a heavy erection. And the ground-supported stage and production towers are erected FIRST; can they carry the access instead of renting it twice?
Building & Fit-out Breakdown | F58 | Demo pre-cast roof 74,000 SF | Confirms the REBUILD method, which the RFEM model also uses and which we now accept. Separate question: is the existing roof genuinely pre-cast concrete? It decides whether a PARTIAL lift over the 27,393 SF high-roof zone is even possible.
Building & Fit-out Breakdown | F93 | 033000 subtotal $177,450 | Nearly every line zero quantity - no footings, no stage slab, no mezzanine deck pour, no base-plate grout. The takeoff gives 124 footing locations (up from 81 in Rev 43). We carry $2,543,000 of foundations.
Building & Fit-out Breakdown | F151 | 055100 STRUCTURAL STEEL $0 | ALL 19 LINES ZERO. The RFEM takeoff (VE1) gives 997.2 SHORT TONS: beams/girders 508.4, columns 360.6, trusses 67.7, braces 40.2, CFS 20.3 (11,557 LF). Please price off the lb column - the file's 't' column is metric tonnes (904.6) and using it understates steel by 10.2%. Your own $6,000/TON on line 2 is right for rolled framing.
Building & Fit-out Breakdown | E131 | Trusses/girders/columns @ $6,000/TON | 202.0 tons of the columns are BUILT-UP PLATE GIRDERS (I 48/24 through I 69.023/24, 60 LF each on grids B and E), not rolled shapes. Does $6,000/TON apply to shop-welded plate? We carry $8,400.
Building & Fit-out Breakdown | E140 | Stage lighting & AV support @ $8/LB | Your $8.00/LB here corroborates our ground-supported rigging grid, which works out to $9.21/LB. Note: the stage carries the rigging, not the roof. Please confirm the roof design loads EXCLUDE production rigging.
Building & Fit-out Breakdown | F182 | 064000 MILLWORK $0 | Every bar and back bar at $2,000/LF with no linear feet - but 220000 already carries NINE bars roughed at $30,000 each. Nate can give you the LF off the test fit. We carry $510,500 of millwork.
Building & Fit-out Breakdown | F204 | 078100 FIREPROOFING $0 | All three lines zero at $5.00/SF. On ~107,000 SF of new deck and roof that is about $536,000 at your own rate.
Building & Fit-out Breakdown | F213 | 081000 DOORS $0 | Zero, including every acoustical door and pair into the music hall at $10,000 / $20,000. We carry $546,800.
Building & Fit-out Breakdown | F229 | 084100 STOREFRONT $0 | Zero. We carry $292,000 for storefront and glazing together.
Building & Fit-out Breakdown | F270 | 092000 DRYWALL $119,664 | 9 of 10 lines zero. $119,664 looks like a fraction of a room needing sound-rated separation between a 7,440-capacity hall and everything else. We carry $1,019,276.
Building & Fit-out Breakdown | F326 | Coat Check Lockers 2,000 @ $500 | 2,000 lockers serves 27% of a 7,440 house at once, at a gym-locker rate. Is 2,000 right? 750 @ $350 is a generous January coat check. Worth $737,500 at trade.
Building & Fit-out Breakdown | F334 | 100500 ACOUSTICAL $581,802 | $581,802 of K13 against our $1,864,000 of acoustic treatment. Next to residential this is the licence to operate. What is the acoustic performance target this was priced to?
Building & Fit-out Breakdown | F361 | 142000 ELEVATOR $480,000 | No question - 4 lobby + 2 stage stops @ $75,000 plus a hydraulic lift is better built than our $300,000 allowance. We are adopting yours.
Building & Fit-out Breakdown | C366 | 2nd floor sprinklers 50,000 SF | 50,000 SF. The RFEM model measures the mezzanine at 32,942 SF + 13,077 SF tiered seating = 46,019 SF. Close - can you confirm the basis?
Building & Fit-out Breakdown | C365 |  | 69,000 SF - the footprint is 74,100 SF. Should this be higher?
Building & Fit-out Breakdown | C383 | Fixture counts | 178 WC + 154 lavs + 51 urinals across the building at $4,000 each. Can we see the CODE FIXTURE CALCULATION behind the count? We are at $1,757,502 vs your $3,717,250 and one of us is wrong - settleable in an afternoon.
Building & Fit-out Breakdown | C398 |  | Nine bars roughed here - so the building knows it has nine bars, but 064000 prices none of them.
Building & Fit-out Breakdown | F415 | HVAC 132,542 SF @ $45 | ONE LINE, 132,542 SF x $45.00, no tonnage. Was this priced on a LOAD or an AREA? A 64 ft clear room with 7,440 people is a volume and occupancy load. Can we see tons and the basis? Ours is $5,950,650 built from load - almost the same total, which is a coincidence not agreement.
Building & Fit-out Breakdown | F427 | I/O lighting package $1,631,436 | 'PROVIDED BY OTHERS' - is this yours or ours? FF&E line 310 separately carries $1,750,000 of Architectural & Exterior Lighting. That is $3,381,436 of architectural lighting in one budget. Keep the conduit and wiring here, delete the fixtures?
Building & Fit-out Breakdown | F447 |  | Two 4,000A boards = 8,000A service, matches our sizing. Is this confirmed with Con Ed - is there a feasibility letter?
Building & Fit-out Breakdown | F451 |  | $250,000 allowance - has Con Ed responded on the 8,000A service and the vault?
Building & Fit-out Breakdown | F478 |  | Adopting this. We had not carried VESDA and you are right that a 64 ft volume with haze and pyro needs it.
Building & Fit-out Breakdown | C477 |  | 135,953 SF basis - see the area question on the summary sheet.
Soft Cost & FF&E Budget Detail | E14 | Roof Abatement | 70,000 SF @ $21 = $1,470,000. Where does $21/SF come from, and has anyone SAMPLED the roof? No ACP-5 exists. We carry $7.50/SF. Also: this sits in soft costs; we carry abatement as a trade.
Soft Cost & FF&E Budget Detail | E26 | A&E $3,100,000 | One $3,100,000 lump with architecture, MEP and structural all 'carried in line #3'. Can it be split? We cannot tell whether structural is funded at the level the RFEM model needs.
Soft Cost & FF&E Budget Detail | E54 | Acoustical $15,000 | $15,000 is testing. Is there an acoustic DESIGN fee anywhere? We carry $200,000 - next to residential it is the licence to operate.
Soft Cost & FF&E Budget Detail | E74 | Permit fees 1.3% | 1.3% of trade cost - understood, so this falls automatically as trade moves. Is 1.3% right for a project filing an ST structural permit at +64 ft 6 in? We carry a separate $120,000 for the ST filing and expediting; we cannot find it here.
Soft Cost & FF&E Budget Detail | E93 | Attorney Fees $0 | Attorney fees $0. Is the SLA application, the cabaret question and the theater use-classification filing genuinely inside the $342,000 already spent? On a comparable project the liquor licence was approved at zero and came in at $250,000. We carry $250,000.
Soft Cost & FF&E Budget Detail | E101 | Controlled inspections $50,000 | $50,000 on a job with new structural steel, welding, fireproofing, sprinklers and a new 8,000A service. We carry $140,000. Does this cover NYC special inspections?
Soft Cost & FF&E Budget Detail | E105 | Project Management | Same $500,000 in our budget - no question on the number. Only the '(Live Nation)' label on the summary sheet; this is our team.
Soft Cost & FF&E Budget Detail | E128 | GA folding chairs | 3,714 @ $125 = $464,250, plus 657 box chairs @ $300 below. HOLDING - seat count is a licensing determination (theater classification drives the liquor licence) and counsel has not ruled. Not a pricing disagreement. We carry 720 removable @ $25.
Soft Cost & FF&E Budget Detail | E156 | Bar & kitchen equipment | Your note above - '* BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K' - is the most useful line in the file. Against it, 74 bar positions here at $9,000 = $666,000 looks LIGHT to us, and so do our 53. Is it?
Soft Cost & FF&E Budget Detail | E168 | Freight & Installation $375,000 | $375,000 is 40% of the equipment above it. Freight and install only, or does it carry something else?
Soft Cost & FF&E Budget Detail | E222 | Metal Detectors | 1 allowance, $70,000 - how many screening lanes does that buy? We carry 12 walk-through units for a 7,440 house.
Soft Cost & FF&E Budget Detail | E289 | Soft goods $500,000 | $500,000, and the note excludes the mezzanine-edge cutdown drape. Your own benchmark note on the Production subtotal says Soft Goods $725k. Which is right? We are at $220,000 and think we are light.
Soft Cost & FF&E Budget Detail | B296 | Video walls | Blank, note $1,400/SF. Confirming you also intend both video walls OUT of this budget (Phase 2, artists bring their own)?
Soft Cost & FF&E Budget Detail | E301 | House Sound System | $1,400,000 'includes Theater / VIP / Restaurant & Roof'. Your benchmark note says Audio $690k. We carry $2,200,000 and want to be challenged on it - do you have a vendor who will quote a house PA for a 7,440 room?
Soft Cost & FF&E Budget Detail | E305 | Performance Lighting | $520,000 against your benchmark note of $450k. We are at $340,000 and probably light.
Soft Cost & FF&E Budget Detail | E313 | Architectural lighting $1,750,000 | $1,750,000 here AND $1,631,436 of 'I/O lighting package PROVIDED BY OTHERS' inside the electrical trade (260000). Bought twice? Which one survives?
Building & Fit-outBudget Detail | C50 | GL / Builder's Risk $0 | G.L. $0 and Builder's Risk $0 - both genuinely inside the 9% combined? Schimenti's equivalent line at 555 Johnson says 'Builder's Risk - Excluded' in writing. Can your broker quote both SEPARATELY, and quote an owner-controlled programme? We carry $385,000.
Building & Fit-outBudget Detail | C47 |  | 'Carried in budget summary' - and also carried as division 013000 in trade cost. One function, two places.

## Budget Summary
165 Randolph St. Brooklyn NY
Warehouse Conversion / Add Second Level & Roof Deck
Theater GA Standing: 7,440
Theater GA Seated: 5,954
Eating & Drinking : 769
VIP Lounge
SF: | 135, 953 | [5 empty] | 135,953 SF appears here and in 6 formula cells. Source? The RFEM model has 146,508 SF gross / 120,119 SF enclosed floor; the test fit governs at 74,100 SF footprint. 555 Johnson at $208.63/SF is 134,993 SF - please rule that out.
2026-09-07 | [6 empty] | Dated 7 Sep; the Breakdown tab says 16 Sep. Which is current?
Version #: 1
Construction Duration: 20 Months
Expected Certificate of Occupancy: TBD
Expected Frist Show:
Project Completion:
|  | Budget Total | 2023 | 2024 | 2025 |  | OUR QUESTION / ANALYSIS (MT, 17 Sep)
000 | OFF SITE COSTS
| Parking Garage - 260/spaces |  | 0 | 0 | 0 |  | Formula is =86*25000 but the label says 260 spaces. Which is right? And is off-site parking in this deal at all? We carry none.
| Escalation (Calculated at 5%) |  | 0 | 0 | 0
|  |  | 0 | 0 | 0
100 | Building & Fit-Out Costs
| Trade Costs |  | 0 | 0 | 0
| Trade Costs To Be Priced | 12000000 |  |  |  |  | What scope is inside the $12,000,000, and when can it be priced? Our measured structure alone is $16,710,249 (997.2 short tons off the RFEM takeoff), and this plug also has to cover millwork, doors, glazing, tile, fireproofing and drywall. We expect it to go UP when priced.
| General Conditions and General Requirements | 3141000 | 0 | 0 | 0 | 90 wks | $3,141,000 here PLUS $3,034,000 of division 013000 inside the trade cost = $6,175,000, 12.36% of trade. Schimenti ran 7.80% and 8.90% at 555 Johnson. Which is the one we are paying? We hold 8.5%.
| Overhead, Profit & Insurance (9% Combined) |  | 0 | 0 | 0
| Contractor Contingency 10% |  | 0 | 0 | 0
| Escalation (Calculated at 5%) |  | 0 | 0 | 0 |  | Blank in all three versions of this file, while the parking garage gets 5% on D22. On a 20-month programme what should the building carry? We hold 10%.
|  |  | 0 | 0 | 0 |  | I31 divides by 135,953. On the 74,100 SF footprint this is $859/SF.
200 | Soft Costs
| Abatement |  | 0 | 0 | 0
Feasibility Study
| Architectural / Engineering / Consultant Fees |  | 0 | 0 | 0
| Site & Civil |  | 0 | 0 | 0
Traffic Engineering
Acousticsl Engineering
Geotechnical Engineering
Enviromental Studies
| Zoning/Permit Fees |  | 0 | 0 | 0
Utility Connection Fees
Attorney Fees
| Testing / Quality Control |  |  | 0 | 0
| Project Management (Live Nation) |  | 0 | 0 | 0 |  | This is our own team, not Live Nation. Same $520,000 in our budget - just the label.
| Reimbursable Expenses |  | 0 | 0 | 0
300 | FF&E Costs
| Seating & Furniture |  | 0 | 0 | 0
| Kitchen & Bar Equipment |  | 0 | 0 | 0
| POS |  | 0 | 0 | 0
| CCTV |  | 0 | 0 | 0
| Data (Wifi & Network) Systems |  | 0 | 0 | 0
| Office Furniture |  | 0 | 0 | 0
| Exterior Signage / Wayfinding |  | 0 | 0 | 0
| Interior Art & Décor "Warehouse Scope" |  | 0 | 0 | 0
| Administration |  | 0 | 0 | 0
Facility
Operations
| Production - FF&E |  | 0 | 0 | 0
| Production - Soft Goods |  | 0 | 0 | 0
| Production - Audio & Video System |  | 0 | 0 | 0
Production - Performance Lighting
| Architectural Lighting |  | 0 | 0 | 0
400 | Soft Costs & FFE Contingency 10% |  | 0 | 0 | 0 |  | Label says Soft Costs & FFE. Formula is =(D23+D31+D47+D65)*0.1 = 10% of the WHOLE PROJECT, on top of the contractor contingency already inside D31. As labelled it would be $1,507,723. $578,648 of it is contingency on contingency. Which is intended?
\
| Total Capital | [5 empty] | Ours: V3 $77,897,555 on the same programme, measured steel. Apply only the corrections that survive the takeoff and this cell becomes about $77,247,828 - 0.8% from ours.
| $ PER SF | [5 empty] | Divides by 135,953 SF. Where does that number come from? We cannot find a schedule or calculation behind it. On 74,100 SF this total is $1,202/SF. Both are true; please label which.

## Soft Cost & FF&E Budget Detail
165 Randolph St Brooklyn NY
Scope : | Warehouse Conversion / Add Second Level & Roof Decks
Capacity: | ##
SF: | 135953
Date:
Version: | 1
200 | SOFT COSTS
201 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES | OUR QUESTION / ANALYSIS (MT, 17 Sep)
Abatement
1 | Pipe Insulation Abatement | 190 | 72
2 | Roof Abatement | 70000 | 21 |  |  | 70,000 SF @ $21 = $1,470,000. Where does $21/SF come from, and has anyone SAMPLED the roof? No ACP-5 exists. We carry $7.50/SF. Also: this sits in soft costs; we carry abatement as a trade.
Total Abatement
202 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Feasibility Study
1 | Due Diligence & Feasibility Study | 1 | 342000
Total Feasibility Study
203 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Architectural Fees
1 | Conceptual & Brand Development | 1 | 45000
| Interior Design | 1 | 90000
| Architecture & Engineering | 1 | 3100000 |  |  | One $3,100,000 lump with architecture, MEP and structural all 'carried in line #3'. Can it be split? We cannot tell whether structural is funded at the level the RFEM model needs.
| Architecture |  | 0 |  | Carried in line #3
| MEP Engineering |  | 0 |  | Carried in line #3
| Structural Engineering |  | 0 |  | Carried in line #3
| MEP Consultant | 1 | 30000
| Lighting Design (Bandit) | 1 | 51000
| Kitchen Equipment Design (TriMark) | 1 | 20000
| LV/AV Design | 1 | 35000
| Signage & Way Finding Design | 1 | 75000
| Renderings | 1 | 50000
| Reimbursables | 1 | 30000
Total Architectural Fees
204 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Civil Engineering
1 | Civil Engineering | 1 | 10000 |  | Exterior work: New Sidewalks, Street Work
Total Civil Engineering
205 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Traffic Engineering
1 | Traffic Engineering | 1 | 10000 |  | Verify w/ Traffic Consultant Report
2 |  |  | 0
Total Traffic Engineering
206 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Acoustical Engineering
1 | Sound and Vibration Testing | 1 | 15000 |  | Sound & Vibration Testing / Design Documentation & Consulting | $15,000 is testing. Is there an acoustic DESIGN fee anywhere? We carry $200,000 - next to residential it is the licence to operate.
4 |  |  | 0
5 |  |  | 0
Total Acoustical Engineering
207 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Geotechnical Engineering
1 | Geotechnical Engineering | 1 | 150000 |  | 13 Borings 50' deep required for ST Permit
Total Geotechnical Engineering
208 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Environmental Studies
1 | Carried in Feasibility Study
Total Environmental Studies
209 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Zoning / Permit Fees
1 | Permit fees & plan review fees | 1 |  |  | 1.3% Trade Costs | 1.3% of trade cost - understood, so this falls automatically as trade moves. Is 1.3% right for a project filing an ST structural permit at +64 ft 6 in? We carry a separate $120,000 for the ST filing and expediting; we cannot find it here.
| Special Projects Program | 1 | 50000
3 | MEP and misc. permit fees | 1 | 10000
4 | Expeditor (allowance for Addt'l services) | 0
5 | FA Consultant & Expediting Services | 1 | 35000 |  | Consulting/ Filing/ FA Inspection Filing & Inspection Scheduling/ TCO Affidavit/ FDNY NOD
6 | Fire Safety & Emergency Action Plan | 1 | 21500
7 | Fire Protection Plan & Filing with FDNY | 1 | 18500
Total Zoning / Permit Fees
210 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Utility Connection Fees
1 | Electrical Service Upgrade | 1 | 50000 |  | Service upgrade required. Vault located in street, new conduit and feeders from vault into MPOE electrical room. Only Con Ed costs carried.
Total Utility Connection Fees
211 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Attorney Fees
1 | SLA Legal Fees carried in Feasibility DD | 0 | 0 |  |  | Attorney fees $0. Is the SLA application, the cabaret question and the theater use-classification filing genuinely inside the $342,000 already spent? On a comparable project the liquor licence was approved at zero and came in at $250,000. We carry $250,000.
Total Attorney Fees
212 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Testing / Quality Control
1 | Controlled inspections | 1 | 50000 |  |  | $50,000 on a job with new structural steel, welding, fireproofing, sprinklers and a new 8,000A service. We carry $140,000. Does this cover NYC special inspections?
2
Total Testing / Quality Control
213 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
| Project Management |  |  |  |  | Same $500,000 in our budget - no question on the number. Only the '(Live Nation)' label on the summary sheet; this is our team.
1 | Project Management | 1 | 500000
| Estimating Services | 1 | 20000
0
Total Miscellaneous
214 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Reimbursable Expenses
1 |  | 0 | 0
0
4 |  |  | 0
0
0
Total Reimbursable Expenses
TOTAL SOFT COSTS
300 | FF&E COSTS
SEATING & FURNITURE
301 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | VENDOR | NOTES
Seating and Accessories
| Theater Ground Floor GA Cushioned Folding Chairs | 3714 | 125 |  |  | 3,714 @ $125 = $464,250, plus 657 box chairs @ $300 below. HOLDING - seat count is a licensing determination (theater classification drives the liquor licence) and counsel has not ruled. Not a pricing disagreement. We carry 720 removable @ $25.
| Mezzanine Level Box Chairs | 657 | 300
| Mezzanine Level Elevated Chairs | 63 | 300
| Mezzanine Level Elevated Couches | 15 | 2500
| Mezzanine Level Elevated Coffee Tables | 24 | 250
| Stage R&L Viewing Boxes | 2 | 7500
| VIP Lounge Furniture | 1 | 75000 |  | 2nd Fl / 3rd Fl
| VIP Lounge Roof Terrace Furniture | 1 | 15000
| Restaurant Furniture | 1 | 60000
| Restaurant Terrace Furniture | 1 | 10000
| Roof Terrace Furniture | 1 | 25000
| Roof Lounge Furniture | 1 | 35000
| Dressing Room Furniture | 6 | 10000
| Crew & Artist Lounge Area | 1 | 25000
| Artist & Crew Furniture | 0 | 0
Total Seating/Accessories
SUB-TOTAL FURNITURE
BAR & KITCHEN EQUIPMENT
302 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
| Bar Equipment |  |  |  | * BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K
1 | Kitchen Equipment | 1 | 130000 |  |  | Your note above - '* BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K' - is the most useful line in the file. Against it, 74 bar positions here at $9,000 = $666,000 looks LIGHT to us, and so do our 53. Is it?
| Lobby Bar Equipment | 5 | 9000
| Music Hall House Left Bar | 16 | 9000
| Music Hall House Right Bar | 15 | 9000
| Music Hall Rear Bar | 14 | 9000
| Mezz. House Right Bar | 8 | 9000
| Mezz. House Left Bar | 8 | 9000
| VIP Lounge Bar including Roof | 2 | 20000
| Restaurant Bar | 2 | 20000
| Roof Lobby Bar | 4 | 12000
| Ice Machines | 4 | 15000
| Walk-In Coolers | 2 | 15000
| Freight & Installation | 1 | 375000 |  |  | $375,000 is 40% of the equipment above it. Freight and install only, or does it carry something else?
| POS | 0 | 3000 |  | Lease POS terminals / lease costs carried under operating costs
Total Concessions
SUB-TOTAL CONCESSIONS
DATA SYSTEMS / IT / CCTV
303 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Data Systems / IT / CCTV
| Data Cabling |  |  |  | Carried Construction Costs
| VoIP Phones / Data Switch / WiFi | 1 | 200000
| CCTV - Security Cameras | 110 | 2000
Total Data Systems
SUB-TOTAL DATA SYSTEMS
OFFICE FURNITURE
304 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Office Furniture/Accessories
Administration
| Administration Furniture | 1 | 50000
| Admin.Appliances |  | 0
Production
1 | Desks-Production | 1 | 15000
| Desk Chairs-Production |  | 0
Total Office Furniture/Access.
SUB-TOTAL OFFICE FURNITURE
SIGNAGE / SCENIC
305 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Exterior Builidng Signage
1 | Exterior Signage | 1 | 400000
Total Exterior Builidng Signage
Wayfinding
1 | Interior Wayfinding and ADA Signage | 1 | 100000
Total Wayfinding
Art
1 | Interior Art and Décor | 1 | 150000 |  | Inerior Scenic Work & Exterior Building Murals
Total Art
SUB-TOTAL SIGNAGE / SCENIC
ADMINISTRATION
306 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Office Equipment
| Safe-Accounting | 1 | 1000
2 | Safe-Box Office | 1 | 1000
3 | Safe-Concessions | 1 | 1000
| Radios | 1 | 20000
Total Office Equipment
| Metal Detectors |  |  |  |  | 1 allowance, $70,000 - how many screening lanes does that buy? We carry 12 walk-through units for a 7,440 house.
| Metal Detectors | 1 | 70000
Total Metal Detectors
SUB-TOTAL ADMINISTRATION
FACILITY
307 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Administration/Main Entrance
1 | Merch Cases | 1 | 26000
Total Admin/Main Entrance
Landscape Furniture
|  | 0 | 0
Total Landscape Furniture
Lighting/Sound/Video-Other
|  | 0 | 0
Total Lighting/Sound/Video
SUB-TOTAL FACILITY
OPERATIONS
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Custodial Equipment
1 | Venue Trash Cans | 80 | 150
| Decorative Trash Cans | 0 | 0
| Janitor Carts | 2 | 500
Total Custodial Equipment
Landscape Equipment
0
Total Landscape Equipment
| Miscellaneous Equipment |  | 0
1
Total Misc. Equipment
Security/Police/Traffic
1 | Bicycle Rack | 1 | 1000
2 | Police Barricades | 1 | 10000
3
Total Sec/Police/Traffic
Shop Equipment
| Hand Tools-Miscellaneous | 1 | 3000
| Ladders | 1 | 1000
3 | Shelving / Cabinets | 1 | 1000
Total Shop Equipment
SUB-TOTAL OPERATIONS
PRODUCTION
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Production FF&E
1 | AVS - Test |  | 0
| Stage Barricade | 1 | 18000
| Portable Stage | 1 | 30000
| Fork Lift | 1 | 35000
| Scissor Lift | 1 | 25000
| Washer & Dryer | 1 | 5000
| Risers | 1 | 12000
| Dock Plates/Ramps/Hand Carts & Dollies | 1 | 30000
| Hand Cart & Dollies | 1 | 30000
| Storage Shelving | 1 | 1500
| Tools | 1 | 7000
Total Production FF&E
Soft Goods
1 | All soft goods | 1 | 500000 |  | Stage / Perimeter Walls Music Hall - CUTDOWN DRAPE @ MEZZ EDGE Not Included | $500,000, and the note excludes the mezzanine-edge cutdown drape. Your own benchmark note on the Production subtotal says Soft Goods $725k. Which is right? We are at $220,000 and think we are light.
Total Soft Goods
Video System
1 | Music Hall Projector | 1 | 75000
| Displays & Distribution | 1 | 200000
| VIP Lounge Projector | 1 | 10000
| Upstage Video Wall |  |  |  | $1,400/SF | Blank, note $1,400/SF. Confirming you also intend both video walls OUT of this budget (Phase 2, artists bring their own)?
Overhead Video Wall
Total Video System
Audio System
1 | House Sound System | 1 | 1400000 |  | Includes Theater / VIP / Restaurant & Roof Area | $1,400,000 'includes Theater / VIP / Restaurant & Roof'. Your benchmark note says Audio $690k. We carry $2,200,000 and want to be challenged on it - do you have a vendor who will quote a house PA for a 7,440 room?
Total Audio System
Production Lighting
1 | Performance Lighting | 1 | 520000 |  |  | $520,000 against your benchmark note of $450k. We are at $340,000 and probably light.
2 | Performance Lighting VIP |  | 0
Total Performance Lighting
| SUB-TOTAL PRODUCTION |  |  |  |  | Misc. Equipment $60K, Soft Goods $725k, Video $236k, Audio $690k, Performance Lighting $450k
ARCHITECTURAL LIGHTING
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
1 | Architectural & Exterior Lighting | 1 | 1750000 |  |  | $1,750,000 here AND $1,631,436 of 'I/O lighting package PROVIDED BY OTHERS' inside the electrical trade (260000). Bought twice? Which one survives?
SUB-TOTAL ARCHITECTURAL LIGHTING

## Building & Fit-outBudget Detail
Venue
Scope :
Capacity: | 7440
SF:
Date: | 2026-09-16
Version:
100 | BUILDING & FIT-OUT COSTS
CSI # | TRADE | BUDGET | COST/SF | NOTES | OUR QUESTION / ANALYSIS (MT, 17 Sep)
013000 | PROJECT REQUIREMENTS
015800 | SCAFFOLDING & STAGING
024100 | DEMOLITION
033000 | CONCRETE
042000 | MASONRY
044000 | STONE & CERAMICS
055100 | STRUCTURAL STEEL & MISC METALS
061000 | ROUGH CARPENTRY
064000 | MILLWORK AND FURNITURE INSTALL
075000 | ROOFING
078100 | FIREPROOFING
081000 | DOORS, FRAMES & HARDWARE
083000 | SPECIAL DOORS
084100 | STOREFRONT
088000 | GLASS/GLAZING
092000 | DRYWALL
092300 | TILE/BRICK TILE
096000 | CARPET/RESILIENT FLOORING
096050 | FLOOR PREPARATION
096400 | WOOD FLOORING
099000 | PAINTING/PLASTER
100000 | SPECIALITIES
100500 | ACOUSTICAL PANELS/K13
101400 | SIGNAGE
120000 | FF&E INSTALL
114000 | FOOD SERVICE AND BAR EQUIPMENT
142000 | ELEVATOR
210000 | FIRE PROTECTION
220000 | PLUMBING
230000 | HVAC
260000 | ELECTRIC
270000 | LOW VOLTAGE CABLING
265000 | LIGHTING
283100 | FIRE ALARM
320000 | SITEWORK
001000 | PRECONSTRUCTION | 60000
010000 | GENERAL CONDITIONS | 0 |  | Carried in budget summary | 'Carried in budget summary' - and also carried as division 013000 in trade cost. One function, two places.
010001 | BONDS | 0 |  | NIC
SUB TOTAL
500005 | G.L. INSURANCE | 0 |  |  | G.L. $0 and Builder's Risk $0 - both genuinely inside the 9% combined? Schimenti's equivalent line at 555 Johnson says 'Builder's Risk - Excluded' in writing. Can your broker quote both SEPARATELY, and quote an owner-controlled programme? We carry $385,000.
500006 | BUILDERS RISK INSURANCE | 0
| C.M. OVERHEAD & FEE | 0
SUB TOTAL
500010 | STATE/PROJECT TAX (IF APPLICABLE) | 0
700002 | DESIGN CONTINGENCY | 0
700003 | CONSTRUCTION CONTINGENCY | 0
700004 | EXPEDITING/OVERTIME CONTINGENCY | 0
TOTAL

## Building & Fit-out Breakdown
Venue
Scope:
Capacity: | 7440
SF:
Date:
Architect: | Wake
Version:
ITEM | DESCRIPTION | QTY | UNIT | UNIT PRICE | TOTAL | NOTES |  |  | OUR QUESTION / ANALYSIS (MT, 17 Sep)
013000 | PROJECT REQUIREMENTS
1 | BIM Set Up & Coordination | 1 | LS | 30000
| Plans / Reprographics | 1 | LS | 7500
| Site Office & Equipment | 1 | LS | 12000
| Field Techonology | 1 | LS | 200000 |  |  |  |  | What is included in Field Technology at $200,000?
| Construction Signage | 1 | LS | 4500
| Site Security | 1 | LS | 13000
| Site Safety Plan / First Aid / TPP / FE's / Safety Inspector | 1 | LS | 400000
| Portable Toilets | 80 | WK | 400
| Clean up Materials | 1 | LS | 65000
| Protection Materials | 1 | LS | 50000
| Project Labor | 1 | LS | 2000000 |  |  |  |  | Crew, rate and weeks? The General Conditions tab already funds three supers + a general super for 90 weeks. No quantity behind this line.
| Project Rubbish Removals | 1 | LS | 120000
| Final Clean | 1 | LS | 100000
Sub Total | [8 empty] | All of this division reads as general conditions. Is it meant to sit inside trade cost AND under the GC line on the summary? We think it is one function in two places.
015800 | SCAFFOLDING & HOARDING
1 | Install sidewalk bridge and scaffolding around building | 1 | LS | 4000000 |  |  |  | 500/LF bridge | The lump says $4,000,000. The two rows beneath it - 1,126 LF @ $500 and 27,024 SF @ $75 - foot to $2,589,800. Which is right? And how many LF of PUBLIC sidewalk does the building front? A shed is only required where there is one; the alleys and lot lines have none. We carry 1,089 LF perimeter x $210 erected + 24 months rental.
|  | 1126 | LF | 500
|  |  | SF | 75
2 | Interior scaffolding | 1 | LS | 2000000 |  |  |  | $75/SF for scaffolding | What is being staged, at what rate, for how many weeks? The high roof is only 8.65 lb/SF of short-span W12/W6 framing - not a heavy erection. And the ground-supported stage and production towers are erected FIRST; can they carry the access instead of renting it twice?
3 | Barricades | 1 | LS | 150000
| Site safety During Erection | 1 | LS | 20000
4
Sub Total
024100 | DEMOLITION
1 | Demo existing CMU/masonry walls at new Entry/Lobby area | 2500 | SF | 12
| Demo 8" CMU interior wall 20' tall | 1975 | SF | 12
| Demo 8" CMU interior wall 12' tall |  | SF | 12
| Demo office area partitions, ceilings, doors, flooring MEP's, (CMU walls line above) | 6825 | SF | 5
| Demo existing exterior roll up doors | 8 | EA | 5000
| Demo existing exterior doors | 7 | EA | 250
| Demo existing windows 1'x10' | 34 | EA | 300
| Demo ceiling mount steam heaters and associated piping | 28 | EA | 750
| Demo 5,250MBH boiler and piping (15'x6'x7' 13,000lbs) | 2 | EA | 20000
| Demo misc. piping, lighting, electrical panels / switchgear / appurtenances throughout space | 1 | SF | 74000
| Demo dock levelers | 3 | EA | 2500
| Demo slab at load-in ramp plan west | 1423 | SF | 10
| Trench slab for new grade beams at new façade | 132 | LF | 100 |  |  | $2,500/cy
| Demo / excavate 6" slab 4' tall at load-in area |  | SF | 12 |  |  | $2,500/cy
| Trench slab for below grade sanitary line for bars and bathrooms | 800 | LF | 80 |  |  | Trenching $150/LF Pour back $50K/LF
| Demo / excavate elevator pits | 2 | EA | 25000 |  |  | New Elvator 4' pit $50K excavate and concrete
| Shoring Demo of Steel | 1 | LS | 50000
| Demo Steel Columns / Roof Steel | 1 | EA | 100000
| Demo Pre-cast concrete roof | 74000 | SF | 8 |  | Abatement by others |  |  | Confirms the REBUILD method, which the RFEM model also uses and which we now accept. Separate question: is the existing roof genuinely pre-cast concrete? It decides whether a PARTIAL lift over the 27,393 SF high-roof zone is even possible.
| Allow for Floor trenching for MEPS | 0 | LS | 50000
| Demo floor for Recessed floor - Include Excavation | 0 | SF | 0 |  | Included Above
| Misc Façade Demo Along Johnson Ave (Doors, Roll-ups, Windows, etc.) | 0 | LS | 20000
Sub Total | [5 empty] | $10/SF
033000 | CONCRETE
1 | Excavation related to New Columns at Music hall | 0 | SF | 6.5 |  | Based on Footprint of New Roof
2 | CMU wall footing excavation allow 2' deep for new Load bearing wall at Music hall- East wall | 0 | LF | 150
3 | Concrete at New footings | 0 | EA | 7500
Excavate & Install New Footings at Stage
4
| 1st Floor Raised Slab - Concrete on Styrofoam 24" | 1500 | CY | 70 |  | 20,314 SF (Includes two ramps down to GA)
Concrete ramp stage
| Concrete 4'6" H on Styrofoam | 0 | SF | 50
| Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50
| F/I new foundation wall / perimeter grade beam | 132 | LF | 300 |  |  | $750/CY
| F/I new retaining wall at load-in area excavate slab 4' tall | 219 | LF | 150 |  | 877 SF | $100/CY
4 | Concrete at CMU footing | 0 | LF | 100
5 | Patch slab due to New footing | 0 | SF | 30
6 | Patch conc. At Trenching for MEPS | 0 | SF | 30
| New slab Pour-back at Excavated Areas | 0 | SF | 30
| New slab at Recessed floor | 0 | SF | 0 |  | Included Above
| Concrete on Deck for Mezz of Music Hall with Platforms | 0 | SF | 25
| Concrete In-fill on New Pan Stairs | 0 | EA | 4000 |  | (2) Feature Stairs, (2) BOH Stairs
| Grouting at Steel Trusses & Column Base Plates | 0 | LS | 15000
| Polished concrete | 0 | SF | 8
| Concrete pads | 0 | LS | 10000
| Patch sidewalk | 0 | LS | 35000
| Misc. Equipment Pads | 0 | LS | 25000
| Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50
Sub Total | [8 empty] | Nearly every line zero quantity - no footings, no stage slab, no mezzanine deck pour, no base-plate grout. The takeoff gives 124 footing locations (up from 81 in Rev 43). We carry $2,543,000 of foundations.
042000 | MASONRY
FIRST FLOOR
1 | Patch & Repair Existing Masonry Wall | 9972 | SF | 10
| New Masonry Wall at Entry Lobby Area | 2022 | SF
| CMU and Brick façade at removed windows | 34 | SF
CMU and Brick façade at removed doors
CMU and Brick façade at removed rolling grilles
Patch masonry at new exterior doors
Patch Masonry at louver openings
| F&I CMU wall vestibule stair tower 1 1st FL | 0 | SF | 35
F&I CMU wall vestibule stair tower 2 1st Fl
F&I CMU wall vestibule stair tower 1 2nd FL
F&I CMU wall vestibule stair tower 2 2nd FL
F&I CMU wall vestibule stair tower 1 3rd Fl
F&I CMU wall vestibule stair tower 2 3rd Fl
| F&I CMU elevator tower entrance | 3220 | SF | 35
| F&I CMU elevator tower Stage | 2977 | SF | 35
| F&I CMU at back wall of music hall | 6097 | SF | 35
2 | F&I Brick façade at music hall bump up | 0 | SF | 35
3 | CMU and Brick infills at old windows and door opening | 0 | SF | 70
4 | Repair/ cleaning and minor repointing of existing brick facade | 0 | SF | 10
5 | Misc. Patching allow at penetrations | 0 | LS | 5000
Sub Total
044200 | STONE & CERAMICS
1 | Lobby stone flooring |  | SF | 45
2 | VIP Lounge Stone Floorin | 1614 | SF | 45
3 | Roof Lobby Stone Flooring |  | SF | 45
4 | Courtyard Stone Pavers | 4268 | SF | 75
Sub Total
055100 | STRUCTURAL STEEL & MISC METALS
1 | Disconnect roof framing for Demo & Shore at select areas | 0 | SF | 5
2 | F&I new Roof Trusses, girders, Columns at Music Hall area | 0 | TONS | 6000 |  |  |  |  | 202.0 tons of the columns are BUILT-UP PLATE GIRDERS (I 48/24 through I 69.023/24, 60 LF each on grids B and E), not rolled shapes. Does $6,000/TON apply to shop-welded plate? We carry $8,400.
3 | F&I Roof deck | 0 | SF | 4
F&I Steel for Stage Support
F/I metal decking Stage
4 | Steel Framing at Mezz area - Including Elevated Standing & Box Seating | 0 | TONS | 6000
5 | Steel Framing at upper balcony - incluing balcony seating | 0 | TONS | 6000
6 | Stage Lighting & AV support structure | 0 | LBS | 8 |  |  |  |  | Your $8.00/LB here corroborates our ground-supported rigging grid, which works out to $9.21/LB. Note: the stage carries the rigging, not the roof. Please confirm the roof design loads EXCLUDE production rigging.
7 | Small stair to access Stage | 0 | EA | 13000
8 | Roof Dunnage for HVAC Equipment's | 0 | LOC | 20000
9 | Roof Penetrations framing for Toilet exhaust & Kitchen exhaust | 0 | LS | 25000
10 | Stairs | 0 | FL | 30000
11 | Allow for Unistrut at select area of stage | 0 | SF | 35
12 | Railing at Roof Deck | 0 | LF | 500
13 | Railing at Theatre | 0 | LF | 275
14 | Misc. Lintels | 0 | LS | 10000
15 | Allow for access Ladders at Stage Overhead lighting grid area | 0 | LS | 15000
Sub Total | [8 empty] | ALL 19 LINES ZERO. The RFEM takeoff (VE1) gives 997.2 SHORT TONS: beams/girders 508.4, columns 360.6, trusses 67.7, braces 40.2, CFS 20.3 (11,557 LF). Please price off the lb column - the file's 't' column is metric tonnes (904.6) and using it understates steel by 10.2%. Your own $6,000/TON on line 2 is right for rolled framing.
062000 | Rough Carpentry/OSHA Protection
1 | Safety Protection at Roof cut out | 0 | LS | 35000
| Safety Protection at Footings trenches | 0 | LS | 30000
2 | Entry Barricade | 0 | SF | 40
| Safety at New Mezz Build outs | 0 | SF | 2
3 | Rough Carpentry work at Stage area | 0 | SF | 5
Sub Total
064000 | MILLWORK
1 | Lobby Bar/Back Bar - Complete | 0 | LF | 2000
2 | VIP Bar/Back Bar - Complete | 0 | LF | 2000
| Music Hall GA Bar/Back Bars - Complete | 0 | LF | 2000
| Mezzanine Bar/Back Bars - Complete | 0 | LF | 2000
| Balcony bar/back bar- complete | 0 | LF | 2000
| Upper lounge bar/back bar- complete | 0 | LF | 2000
| Lower lounge bar/back bar- complete | 0 | LF | 2000
| Foundry bar/back bar- complete | 0 | LF | 2000
| Decorative Features Above Each Back Bar | 0 | EA | 10000
| Green room Bathrooms & Counter tops | 0 | LF | 350
| Public Bathroom Counter top | 0 | LF | 400
| Millwork at Merchandise | 0 | LS | 12000
| Pantry at Office Area | 0 | LF | 850
| Millwork shelf & Pole at Coat closet area | 0 | LF | 150
| Install Furniture | 0 | LS | 25000
| Additional millwork in public areas | 0 | LS | 30000
| Decorative Millwork at Proscenium | 0 | EA | 10000
| Millwork at BOX Office | 0 | LF | 500
Sub Total | [8 empty] | Every bar and back bar at $2,000/LF with no linear feet - but 220000 already carries NINE bars roughed at $30,000 each. Nate can give you the LF off the test fit. We carry $510,500 of millwork.
075000 | ROOFING
1 | 2nd Floor Terrace Roof Membrane | 2041 | SF | 36
| 3rd Floor Terrace Roof Membrane VIP | 1592 | SF | 36
| 3rd Floor Terrace Roof Membrane Restaurant | 4432 | SF | 36
| Music Hall low roof | 17547 | SF | 36
| Music Hall Upper level | 30000 | SF | 36
| 3rd Floor Roof | 8538 | SF | 36
| 2nd Floor concrete pavers on pedestals | 2041 | SF | 36
| 3rd Floor Terrace concrete pavers on pedestals VIP | 0 | SF | 31
| 3rd Floor Terrace concrete pavers on pedestals Restaurant | 4432 | SF | 36
| Patch roofing at Misc. Penetrations | 1 | LS | 15000
Sub Total
078100 | FIREPROOFING
1 | Allow for fireproofing at New steel at Roof | 0 | SF | 5
2 | Allow for fireproofing at New steel at Mezzanine | 0 | SF | 5
3 | Add fireproofing to existing roof steel | 0 | SF | 5
Sub Total | [8 empty] | All three lines zero at $5.00/SF. On ~107,000 SF of new deck and roof that is about $536,000 at your own rate.
081000 | DOORS, FRAMES & HARDWARE
1 | Single Hollow Metal Doors - Non-Acoustical | 0 | EA | 2200 |  |  | Storefront double door
2 | Double Hollow Metal Doors - Non-Acoustical | 0 | EA | 3200 |  |  | F/I HM Double Door & hardware
3 | Acoustical doors at Music Hall | 0 | EA | 10000
4 | Acoustical double doors at Music Hall | 0 | PAIR | 20000
Sub Total | [8 empty] | Zero, including every acoustical door and pair into the music hall at $10,000 / $20,000. We carry $546,800.
083000 | SPECIAL DOORS
1 | Eliason doors | 2 | EA | 3000
| Rolling Grille | 40 | LF | 1750
Sub Total
084100 | STOREFRONT
1 | F&I New Storefront with Doors | 0 | SF | 250
2 | F&I New Storefront with doors to roof deck | 0 | SF | 150
3 | Storefront double door to roof deck | 0 | PAIRS | 4500
4 | Interior Storefront at VIP Lounge | 0 | SF | 75
5 | Interior Storefront at foundry | 0 | SF | 75
6 | Interior double door at VIP Lounge | 0 | PAIR | 4500
Sub Total | [8 empty] | Zero. We carry $292,000 for storefront and glazing together.
088000 | GLAZING
2 | Mirror at Bathrooms- Public | 0 | SF | 50
3 | Mirror at Green room | 0 | SF | 50
4 | Mirror behind bars | 0 | LOT | 35000
| Ballistic Box office window | 0 | LOT | 10000
Sub Total
092000 | DRYWALL
FIRST FLOOR
1 | Perimeter wall partition at existing exterior wall | 9972 | SF | 12
| Perimeter wall partition at new exterior wall | 2022 | SF
| 2HR Fire Rated Wall Reat Stage - 20' High | 5565 | SF
| 2HR Fire Rated Wall Rear Music Hall - 20' High | 2857 | SF
| F/I Plywood 8'AFF at Stage Walls |  | SF
| F/I 2" Insulation above 8' AFF Floor to 38'AFF |  | SF
| F/I Proscenium Wall |  | SF
SECOND FLOOR
THIRD FLOOR
2 | Perimeter wall furring/sheathing at new Music Hall bump up | 0 | SF | 20
3 | Interior Sound/Fire rated walls at music hall, stair ways and elevator shafts | 0 | SF | 20
4 | Interior Non Sound walls | 0 | SF | 12
5 | Drywall ceilings | 0 | SF | 12
6 | Acoustical Ceilngs | 0 | SF | 10
7 | Install Doors/Frames/Hardware | 0 | EA | 650
8 | Blocking | 0 | LS | 30000
9 | FRP Kitchen walls | 0 | SF | 15
10 | Diamond wall plates at Loading dock area for wall protection | 0 | SF | 15
11 | Install Items Furnished By Others | 0 | LS | 25000
Sub Total | [8 empty] | 9 of 10 lines zero. $119,664 looks like a fraction of a room needing sound-rated separation between a 7,440-capacity hall and everything else. We carry $1,019,276.
092300 | TILE
1 | Tile at Restroom/Shower Floors | 0 | SF | 30
2 | Tile at Restroom Walls | 0 | SF | 30
3 | Faux brick at Lobby | 0 | SF | 35
4 | Tile at Bar Floors | 0 | SF | 20
5 | Tile & Base at Kitchen | 0 | SF | 20
Sub Total
096000 | CARPET/RESILIENT FLOORING
1 | Carpete tile at office and production | 0 | SF | 5.5
| LVT Flooring at Green room areas and Dresssing rooms | 0 | SF | 10
| LVT Music Hall and egress stair landings | 30505 | SF | 20
| LVT Coatcheck | 1189 | SF | 12
| VCT in coat room/box office | 0 | SF | 7
| F&I Vinyl Base | 0 | LF | 2.75
| Sealed concrete stage load-in / 1st Fl BOH |  | SF | 20
| Minor Prep floor | 0 | SF | 1.5
| Entry Mats | 0 | SF | 100
| Stair Treads | 0 | LS | 17500
Sub Total
096050 | FLOOR PREPARATION
1 | Music Hall shot blasting & MVB | 24538 | SF | 12
2 | Music Hall cement overlay and top coat | 24538 | SF | 9
3 | Music Hall sealed concrete at new concrete areas | 0 | SF | 5
Sub Total
096400 | WOOD FLOORING
1 | F&I T&G Wood floor at Stage | 4634 | SF | 45
2 | Wood Flooring Restaurant | 3656 | SF | 45
Sub Total
099000 | PAINTING/PLASTER
1 | Paint all Walls & Doors & Ceilings | 135953 | SF | 5
2 | Upgrade finishes at walls in Green room area | 1 | LS | 12000
3 | Plaster | 0 | SF | 25
4 | Wall Covering VIP / Restaurant | 5000 | SF | 80
Sub Total
100000 | SPECIALTIES
1 | Fire extinguishers & cabinets | 60 | EA | 350
| Toilet Acc |  | SET | 600
| Toilet Partitions |  | EA | 1750
| Urinal screens |  | EA | 500
| Bathroom Mirrors |  | EA | 300
| Hand dryers and paper towel dispensers | 1 | Allow | 30000
| Appliances at Pantry | 1 | Allow | 7500
| Coat Check Lockers | 2000 | EA | 500 |  | 333LF |  |  | 2,000 lockers serves 27% of a 7,440 house at once, at a gym-locker rate. Is 2,000 right? 750 @ $350 is a generous January coat check. Worth $737,500 at trade.
Sub Total
100500 | ACOUSTICAL PANELS/ K13
1 | Allowance for wall mount acoustic panels, decorative acoustic integrations | 1 | Allow | 150000
2 | K13 at Underside Music Hall Ceilings | 30843 | SF | 14
Sub Total | [8 empty] | $581,802 of K13 against our $1,864,000 of acoustic treatment. Next to residential this is the licence to operate. What is the acoustic performance target this was priced to?
101400 | SIGNAGE
1 | Allow for interior Door signs | 1 | Allow | 45000
| Allow for Directional signage | 0 | LOT | 0
| Install misc signage allowance | 1 | LOT | 5000
Sub Total
101400 | FF&E Install
1 | Uncrate / dispose owner vendor FF&E | 1 | Allow | 50000
Sub Total
114000 | FOOD SERVICE EQUIPMENT - BY OWNER
1 | F&I Food service equipment | 0 | LS |  |  | By owner vendor
2 | Hood Fire Protection system | 0 | LS |  |  | By owner vendor
3 | F&I Kitchen exhaust hood | 1 | Allow | 15000 |  | Misc scope not covered by OV
4 | Dispose of owner vendor packaging & misc. scope | 1 | Allow | 35000
Sub Total
142000 | ELEVATOR
1 | Elevator Lobby | 4 | STOPS | 75000
2 | Elevator Stage | 2 | STOPS | 75000
3 | Hydraulic Lift 12'x6' | 1 | EA | 30000
Sub Total | [8 empty] | No question - 4 lobby + 2 stage stops @ $75,000 plus a hydraulic lift is better built than our $300,000 allowance. We are adopting yours.
210000 | FIRE PROTECTION
1 | Safe Off / Disconnect | 1 | LS | 10000
| First Floor Rework Existing Fire Protection System First | 69000 | SF | 4 |  |  |  |  | 69,000 SF - the footprint is 74,100 SF. Should this be higher?
| 2nd Floor Extend Sprinkler Mains / New Fire Protection & Stand Pipe | 50000 | SF | 15 |  |  |  |  | 50,000 SF. The RFEM model measures the mezzanine at 32,942 SF + 13,077 SF tiered seating = 46,019 SF. Close - can you confirm the basis?
| 3rd Floor Extend Sprinkler Mains / New Fire Protection & Stand Pipe | 8538 | SF | 15
| New Diesel Fire Pump 1,00 GPM 65PSI 75HP motor | 1 | LS | 150000 |  | Requires dedicated 2/hr rated room,
| Fire Stopping | 1 | LS | 20000
Sub Total
220000 | PLUMBING
1 | F&I new 6" C.W service with RPZ with water meter | 1 | LS | 50000
2 | F/I new 6" sanitary service | 2 | EA | 10000
3 | F/I new storm water detention tank | 1 | LS | 35000
| F&I |  | LS
1 | Water piping | 2500 | LF | 85
| Vent piping | 2400 | LF | 65
| Gas Pipe | 450 | LF | 125
| New storm drainage piping |  | LF | 100
| W/C 1st Fl | 92 | EA | 4000 |  |  |  |  | 178 WC + 154 lavs + 51 urinals across the building at $4,000 each. Can we see the CODE FIXTURE CALCULATION behind the count? We are at $1,757,502 vs your $3,717,250 and one of us is wrong - settleable in an afternoon.
| W/C 2nd Fl |  | EA | 4000
| W/C Roof | 11 | EA | 4000
| Lavs 1st Fl | 68 | EA | 4000
| Lavs 2nd Fl |  | EA | 4000
| Lavs 3rd Fl | 20 | EA | 4000
| Urinals 1st Fl | 32 | EA | 4000
| Urinals 2nd Fl | 13 | EA | 4000
| Urinals Roof | 6 | EA | 4000
| Showers | 6 | EA | 5000
| Green room sinks | 6 | EA | 5500
| Pantry sinks | 2 | EA | 6000
| Water fountains | 4 | EA | 5500
| Floor Drains & Sinks | 65 | EA | 3500
| Water Heater- Electrical | 10 | EA | 7500
| F&I Bar roughing | 9 | EA | 30000 |  |  |  |  | Nine bars roughed here - so the building knows it has nine bars, but 064000 prices none of them.
| Grease Traps Bars | 9 | EA | 7500
| Grease Trap Restaurant | 1 | EA | 125000
| Restaurant Bar | 1 | EA | 75000
| Lobby Bar | 2 | EA | 50000
| VIP Bars | 2 | EA | 40000
| Music Bars | 5 | EA | 40000
| F&I Kitchen roughing | 1 | LS | 135000
| F&I Roof Drains | 11 | EA | 8500
| Demo. Disconnects | 1 | LS | 10000
| Misc Equipment | 1 | LS | 30000
| Firestopping | 1 | LS | 15000
Sub Total
230000 | HVAC
1 | HVAC System including BMS |  | SF | 45 |  |  |  |  | ONE LINE, 132,542 SF x $45.00, no tonnage. Was this priced on a LOAD or an AREA? A 64 ft clear room with 7,440 people is a volume and occupancy load. Can we see tons and the basis? Ours is $5,950,650 built from load - almost the same total, which is a coincidence not agreement.
Sub Total
260000 | ELECTRIC
1 | Demo & Disconnects | 1 | LS | 20000
2 | Demo & remove existing 400A service | 1 | EA | 50000
3 | Temp Lighting & Power | 135953 | SF | 2
Lighting
1 | F/I Emergency lighting package | 135953 | SF | 1
| I/O lighting package throughout provided by others | 135953 | SF | 12 |  |  |  |  | 'PROVIDED BY OTHERS' - is this yours or ours? FF&E line 310 separately carries $1,750,000 of Architectural & Exterior Lighting. That is $3,381,436 of architectural lighting in one budget. Keep the conduit and wiring here, delete the fixtures?
| Install architectural dimming control system, F/I wiring | 135953 | SF | 0.75
Power Wiring & Devices
1 | F/I general power throughout - duplex, quadraplex, floor boxes, J boxes, ceiling outlets | 135953 | SF | 6
2 | F/I dedicated circuits at all Kitchen equipment | 1500 | SF | 35
| F/I dedicated power to stage equipment | 2500 | SF | 15
| F/I Stage power Clean Switches | 1 | LS | 65000
| Panels and Secondary distribution | 1 | LS | 200000
Mechanical Power
1 | F/I power to Mechanical Equipment | 135953 | SF | 3
2 | F/I power to VAV's | 15 | EA | 2500
3 | F/I power to Exhaust Fans | 20 | EA | 5000
4 | Combine Existing Services | 0 | LS | 200000
5 | Stand Pipe Water Booster Pump Wiring | 1 | LS | 20000
Switch Gear & Emergency Power
1 | F/I 4,000A Service End Boxes | 2 | EA | 65000
| F/I 4,000A CT Cabinets | 2 | EA | 55000
| F/I 4000A 208Y/120V Switchboard w/ main Circuit Breaker | 2 | EA | 290000 |  |  |  |  | Two 4,000A boards = 8,000A service, matches our sizing. Is this confirmed with Con Ed - is there a feasibility letter?
| Secondary service conductors, service end box to CT cabinet to Switchboard | 2 | EA | 75000
| NYC electrical plan review drawings, short circuit / coordination / arch flas study and DOB electrical filing | 1 | EA | 35000
| F/I 80KW Generator | 1 | LS | 275000
| Con Edison customer contribution / excess distribution facilities charges | 1 | Allow | 250000 |  |  |  |  | $250,000 allowance - has Con Ed responded on the 8,000A service and the vault?
Misc.
1 | F/I firestopping at cores & penetrations | 1 | LS | 35000
Sub Total
270000 | LOW VOLTAGE
1 | Wiring for security Camera | 110 | EA | 750
| Door intrusion entry/exit security | 0 | LOC | 5000
| A/V wiring only | 1 | LS | 60000
| Phone/Data wiring | 1 | LS | 85000
Sub Total
270000 | LIGHTING AND CONTROLS - BY OWNER
1 | Exit Signs / BOH fixtures | 1 | LS | 40000
Stage Lighting
Bar Lighting
Specialty Fixtures
Dimming Control PKG
6 | Inverter PKG
Sub Total
283100 | FIRE ALARM
1 | F&I Fire alarm system | 135953 | SF | 2 |  |  |  |  | 135,953 SF basis - see the area question on the summary sheet.
2 | F/I Vesda System Music Hall | 1 | LS | 250000 |  |  |  |  | Adopting this. We had not carried VESDA and you are right that a 64 ft volume with haze and pyro needs it.
Sub Total
32000 | SITEWORK
1 | Patch / Repair / Install new sidewalks around building | 8295 | SF | 13 |  | 8,295sf of existing sidewalk around building
| Trees | 1 | Allow | 30000
| Fencing | 300 | LF | 100
4 | Fie escape egress music hall Grid F to Col. 7-17 (10' wide w/ railing) |  | SF | 75
Sub Total

## General Conditions (hidden)
OUR QUESTION / ANALYSIS (MT, 17 Sep)
Exec | 10 | 9200 | This tab is the best-evidenced page in the file and we would rather build on it than argue with it. Is the $3,141,000 the ONLY place general conditions lives? Division 013000 on the Breakdown carries site office, field tech, safety, toilets, protection, clean-up, rubbish and final clean for another $3,034,000.
PM | 90 | 6400 | 90 weeks - is that construction only, or does it include pre-con and closeout? Can we see it as a rate x duration so that shortening the programme visibly shortens the cost?
APM | 90 | 4600
Engineer | 90 | 3900
Accoutnant | 10 | 2800
Super | 90 | 6000 | Three superintendents for the full 90 weeks each - all three for the whole period, or overlapping phases?
Super | 90 | 6000
Super | 90 | 6000
General Super | 10 | 6000

## Project At-a-Glance (hidden)
Cost Report Date: | 2023-01-31 |  |  | Venue Capacity: | TBD
Project Name: |  |  |  | Landlord Work Start Date: | TBD
Location: |  |  |  | LNE Work Start Date: | TBD
Address: |  |  |  | Certificate of Occupancy: | TBD
Project Number: |  |  |  | First Show Date: | TBD
Budget: |  |  |  | Project Completion Date: | TBD
Venue EVP: | TBD |  |  | Project Manager: | TBD
Description | Budget | Committed Costs Total | Costs to Date Total | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance
FF&E Costs
Total Contingency
TOTAL
Risk Summary
Risk Report Total
Remaining Contingency
Exposure
Estimated Final Cost (Including Risk Items)

## Project Summary (hidden)
Description | Budget | Committed Costs | Costs to Date | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance
|  | Total | Total
Building Costs Total
Soft Costs Total
FF&E Costs Total
Sub-Total
Contingency
GRAND TOTAL

## Project Detail (hidden)
Code | Cost Code | Vendor | Description | Budget | Committed Costs | Change Orders | Costs to Date (Gross) | Retention | Costs to Date | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance | Notes | Remaining to Invoice | P11-21 (Fcst) | P12-21 (Fcst) | Q4-21 TOTAL (Fcst) | P01-22 (Fcst) | P02-22 (Fcst) | P03-22 (Fcst) | Q1-22 TOTAL (Fcst) | Q4-21/Q1-22 TOTAL | Remaining to Allocate
100 |  | Building Costs
101 |  | Building & Fit-Out Costs
101-1 |  | General Contractor | [5 empty] | 0
101-2 |  |  |  | 0 |  |  |  | 0
101-3 |  |  |  | 0 |  |  |  | 0
101-4 |  |  |  | 0 |  |  |  | 0
| 101 |  | Total Building & Fit-Out Costs
102 |  | Secondary Contractors
102-1 |  |  |  | 0 |  |  |  | 0
102-2 |  |  |  | 0 |  |  |  | 0
102-3 |  |  |  | 0 |  |  |  | 0
102-4 |  |  |  | 0 |  |  |  | 0
| 102 |  | Total Secondary Contractors
103 |  | Miscellaneous
103-1 |  |  |  | 0 |  |  |  | 0
103-2 |  |  |  | 0 |  |  |  | 0
103-3 |  |  |  | 0 |  |  |  | 0
103-4 |  |  |  | 0 |  |  |  | 0
| 103 |  | Total Mics.
104
104-1 |  |  |  | 0 |  |  |  | 0
104-2 |  |  |  | 0 |  |  |  | 0
104-3 |  |  |  | 0 |  |  |  | 0
104-4 |  |  |  | 0 |  |  |  | 0
| 104 |  | Total
TOTAL BUILDING COSTS
200 |  | Soft Costs
201 |  | Project Management
201-1 |  | LNE | Project Management |  |  |  |  | 0
201-2 |  | TBD | Project Management (3rd Party) |  |  |  |  | 0
201-3 |  |  |  | 0 |  |  |  | 0
201-4 |  |  |  | 0 |  |  |  | 0
| 201 |  | Total Project Management
202 |  | Architectural Fees
202-1 |  | TBD | Architectural Fees |  |  |  |  | 0
202-2 |  |  |  | 0 |  |  |  | 0
202-3 |  |  |  | 0 |  |  |  | 0 |  |  | 0
202-4 |  |  |  | 0 |  |  |  | 0
| 202 |  | Total Architectural Fees
203 |  | Design, Engineering & Misc.
203-1 |  | K2 | AV/LV Design |  |  |  |  | 0
203-2 |  | Trimark | Kitchen Design |  |  |  |  | 0
203-3 |  | Bandit Lites | Lighting Design |  |  |  |  | 0
203-4 |  | TBD | Branding |  |  |  |  | 0
203-5 |  | TBD | Civil Engineering |  |  |  |  | 0
203-6 |  | K2 / Metro Acoustics | Acoustic Design |  |  |  |  | 0
203-7 |  | TBD | Signage / Wayfinding Design |  |  |  |  | 0
203-8 |  | TBD | Zoning & Permit Fees |  |  |  |  | 0
203-9 |  | TBD | Testing / Quality Control |  |  |  |  | 0
203-10 |  | TBD | Reimbursable Expenses |  |  |  |  | 0
| 203 |  | Total Design, Engineering & Misc.
TOTAL SOFT COSTS
300 |  | FF&E Costs
301 |  | Seating
301-1 |  | TBD | Fixed Seating |  |  |  |  | 0
301-2 |  | N/A | Chairs - Gasser Bar Stools |  |  |  |  | 0
301-3 |  | N/A | Chairs - Gasser |  |  |  |  | 0
301-4 |  | N/A | Ottoman - Boxes |  |  |  |  | 0
301-5 |  | N/A | Side Tables - Boxes |  |  |  |  | 0
301-6 |  | N/A | VIP - Cocktail Table |  |  |  |  | 0
301-7 |  | N/A | VIP - Stools |  |  |  |  | 0
301-8 |  | N/A | VIP - Coffee Tables |  |  |  |  | 0
301-9 |  | N/A | VIP - Hightop |  |  |  |  | 0
301-10 |  | N/A | VIP - Sofa |  |  |  |  | 0
301-11 |  | N/A | VIP - Banquet |  |  |  |  | 0
301-12 |  | N/A | Artist Lounge |  |  |  |  | 0
301-13 |  | N/A | Dressing Room |  |  |  |  | 0
301-14 |  | N/A | Rugs |  |  |  |  | 0
301-15 |  | N/A | Catering Room Chairs |  |  |  |  | 0 |  |  | 0
301-16 |  | N/A | Catering Room Tables |  |  |  |  | 0 |  |  | 0
301-17 |  | Multiple Vendors | Box & VIP Seats |  |  |  |  | 0
301-18 |  |  |  | 0 |  |  |  | 0
| 301 |  | Total Seating
302 |  | Concessions
302-1 |  | TriMark | Kitchen and Bars |  |  |  |  | 0
302-2 |  | TBD | Miscellaneous Equipment (POS) |  |  |  |  | 0
302-3 |  | TBD | Portable Bars |  |  |  |  | 0 |  |  | 0
302-4 |  |  |  | 0 |  |  |  | 0
| 302 |  | Total Concession
303 |  | Phone & Data Systems
303-1 |  | Multiple Vendors | CCTV |  |  |  |  | 0
303-2 |  | Entisys, Insight, Multi-Link | Data /Wifi Systems |  |  |  |  | 0
| 303 |  | Total Phone & Data
304 |  | Office Furniture
304-1 |  | Pivot / YE Co. | Office Furniture (From Furniture Tracker) |  |  |  |  | 0
304-2 |  | N/A | Administration Refrigerator |  |  |  |  | 0
304-3 |  | N/A | Desks-Production |  |  |  |  | 0
304-4 |  | N/A | Desk Chairs-Production |  |  |  |  | 0
304-5 |  | N/A | File Cabinets-Production |  |  |  |  | 0
| 304 |  | Total Office Furniture
305 |  | Signage/Graphics
305-1 |  | TBD | Exterior Signage / Wayfinding | 0 |  |  |  | 0 |  |  | 0
305-2 |  | TBD | Interior Art & Décor "Warehouse Scope" | 0 |  |  |  | 0
305-3 | [7 empty] | 0
305-4 | [7 empty] | 0
305-5 | [7 empty] | 0
305-6 | [7 empty] | 0
305-7 | [7 empty] | 0
305-8 | [7 empty] | 0
305-9 | [7 empty] | 0
305-10 | [7 empty] | 0
305-11 |  |  |  | 0 |  |  |  | 0 |  |  | 0
305-12 |  |  |  | 0 |  |  |  | 0 |  |  | 0
305-13 |  |  |  | 0 |  |  |  | 0 |  |  | 0
305-14 |  |  |  | 0 |  |  |  | 0 |  |  | 0
305-15 |  |  |  | 0 |  |  |  | 0
305-16 |  |  |  | 0 |  |  |  | 0
305-17 |  |  |  | 0 |  |  |  | 0 | [6 empty] | 10135
| 305 |  | Total Signage/Graphics
306 |  | Administration
306-1 |  | TBD | Administration |  |  |  |  | 0 |  |  | 0
306-2 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-3 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-4 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-5 |  | TBD |  | 0 |  |  |  | 0
306-6 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-7 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-8 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-10 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
306-11 |  | TBD |  | 0 |  |  |  | 0 |  |  | 0
| 306 |  | Total Administration
307 |  | Facility
307-1 |  | TBD | Facility | 0 |  |  |  | 0 |  |  | 0
307-2 |  |  |  | 0 |  |  |  | 0 |  |  | 0
307-3 | [7 empty] | 0
307-4 |  |  |  | 0 |  |  |  | 0 |  |  | 0
307-5 |  |  |  | 0 |  |  |  | 0
307-6 |  |  |  | 0 |  |  |  | 0
| 307 |  | Total Facility
308 |  | Operations
308-1 |  | TBD | Operations | 0 |  |  |  | 0
308-2 | [7 empty] | 0
308-3 | [7 empty] | 0
308-4 |  |  |  | 0 |  |  |  | 0
308-5 |  |  |  | 0 |  |  |  | 0 |  |  | 0
308-6 |  |  |  | 0 |  |  |  | 0
308-7 |  |  |  | 0 |  |  |  | 0 |  |  | 0
308-8 |  |  |  | 0 |  |  |  | 0 |  |  | 0
308-9 |  |  |  | 0 |  |  |  | 0 |  |  | 0
308-10 |  |  |  | 0 |  |  |  | 0 |  |  | 0
| 308 |  | Total Operations
309 |  | Production
309-1 |  | TBD | FF&E |  |  |  |  | 0 |  |  | 0
309-2 |  | TBD | Soft Goods |  |  |  |  | 0 |  |  | 0
309-3 |  | TBD | Audio & Video System |  |  |  |  | 0 |  |  | 0
309-4 |  | TBD | Production Lighting |  |  |  |  | 0 |  |  | 0
309-5 |  |  |  | 0 |  |  |  | 0 |  |  | 0
309-6 |  |  |  | 0 |  |  |  | 0
309-7 |  |  |  | 0 |  |  |  | 0
309-8 |  |  |  | 0 |  |  |  | 0
309-9 |  |  |  | 0 |  |  |  | 0
309-10 |  |  |  | 0 |  |  |  | 0 |  |  | 0
309-11 |  |  |  | 0 |  |  |  | 0 |  |  | 0
309-12 |  |  |  | 0 |  |  |  | 0
309-13 |  |  |  | 0 |  |  |  | 0
309-14 |  |  |  | 0 |  |  |  | 0
| 309 |  | Total Production
TOTAL FF&E COSTS
400 |  | Contingency
TOTALS
Test (Must be True)
[12 empty] | Remaining Contingency Balance |  |  | 0 | 0 |  | 0 | 0 | 0
GRAND TOTALS

## Committed Costs (hidden)
Committed Costs
Executed Date | Cost Code | Vendor | Description | P.O. Number | Contract Value | Notes
Total Commitments

## Invoices (hidden)
Invoices
Cost Code | Vendor | Description | Invoice # | Invoice Date | Invoice Amount | GL Period | Notes | Payment Status
2022 Invoices
March Invoices Total
INVOICES GRAND TOTAL

## Change Orders (hidden)
Date Issued | C.O. Number | Vendor | Amount | Cost Code | Description | Notes
Total Change Orders

## Contingency (hidden)
Date | Cost Code | Vendor | Description | Amount Applied | Remaining Balance | Notes
March 2020 Contingency | [6 empty] | Contingency
2020-03-31 | N/A | N/A | Initial Contingency Amount | 0
March Contingency Totals
CONTINGENCY TOTALS

## Risk Report (hidden)
Risk Report
Requestor | Item | High | Expected Settlement Value | Low | Notes
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
| Current Sources (as of 01/31/2023) | Remaining Contingency
Contingency Balance
Exposure
*Sources reflect over budget items pending resolution.