## Budget Summary
165 Randolph St. Brooklyn NY
Warehouse Conversion / Add Second Level & Roof Deck
Theater GA Standing: 7,440
Theater GA Seated: 5,954
Eating & Drinking : 769
VIP Lounge
SF: | 135, 953 | [5 empty] | 78000000
2026-09-07
Version #: 1
Construction Duration: 20 Months
Expected Certificate of Occupancy: TBD
Expected Frist Show:
Project Completion:
|  | Budget Total | 2023 | 2024 | 2025
000 | OFF SITE COSTS
| Parking Garage - 260/spaces | 2150000 | 0 | 0 | 0
| Escalation (Calculated at 5%) | 107500 | 0 | 0 | 0
|  | 2257500 | 0 | 0 | 0
100 | Building & Fit-Out Costs
| Trade Costs | 37945959.75 | 0 | 0 | 0
| Trade Costs To Be Priced | 12000000
| General Conditions and General Requirements | 3141000 | 0 | 0 | 0 | 90 wks
| Overhead, Profit & Insurance (9% Combined) | 4777826.3775 | 0 | 0 | 0
| Contractor Contingency 10% | 5786478.6128 | 0 | 0 | 0
| Escalation (Calculated at 5%) |  | 0 | 0 | 0
|  | 63651264.7402 | 0 | 0 | 0 | 468.1858
200 | Soft Costs
| Abatement | 1483680 | 0 | 0 | 0
| Feasibility Study | 342000
| Architectural / Engineering / Consultant Fees | 3526000 | 0 | 0 | 0
| Site & Civil | 10000 | 0 | 0 | 0
| Traffic Engineering | 10000
| Acousticsl Engineering | 15000
| Geotechnical Engineering | 150000
| Enviromental Studies | 0
| Zoning/Permit Fees | 628297.4767 | 0 | 0 | 0
| Utility Connection Fees | 50000
| Attorney Fees | 0
| Testing / Quality Control | 50000 | 50000 | 0 | 0
| Project Management (Live Nation) | 520000 | 0 | 0 | 0
| Reimbursable Expenses | 0 | 0 | 0 | 0
|  | 6784977.4767 | 50000 | 0 | 0 | 49.9068
300 | FF&E Costs
| Seating & Furniture | 1043750 | 0 | 0 | 0
| Kitchen & Bar Equipment | 1317000 | 0 | 0 | 0
| POS | 0 | 0 | 0 | 0
| CCTV | 220000 | 0 | 0 | 0
| Data (Wifi & Network) Systems | 200000 | 0 | 0 | 0
| Office Furniture | 65000 | 0 | 0 | 0
| Exterior Signage / Wayfinding | 500000 | 0 | 0 | 0
| Interior Art & Décor "Warehouse Scope" | 150000 | 0 | 0 | 0
| Administration | 93000 | 0 | 0 | 0
| Facility | 26000
| Operations | 29000
| Production - FF&E | 193500 | 0 | 0 | 0
| Production - Soft Goods | 500000 | 0 | 0 | 0
| Production - Audio & Video System | 1685000 | 0 | 0 | 0
| Production - Performance Lighting | 520000
| Architectural Lighting | 1750000 | 0 | 0 | 0
|  | 8292250 | 0 | 0 | 0 | 60.9935
400 | Soft Costs & FFE Contingency 10% | 8098599.2217 | 0 | 0 | 0 | 59.5691
\
| Total Capital | 89084591.4387 | 50000 | 0 | 0
| $ PER SF | 655.2602 |  |  |  | 638.6552

## Soft Cost & FF&E Budget Detail
165 Randolph St Brooklyn NY
Scope : | Warehouse Conversion / Add Second Level & Roof Decks
Capacity: | ##
SF: | 135953
Date:
Version: | 1
200 | SOFT COSTS
201 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Abatement
1 | Pipe Insulation Abatement | 190 | 72 | 13680
2 | Roof Abatement | 70000 | 21 | 1470000
| Total Abatement |  |  | 1483680
202 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Feasibility Study
1 | Due Diligence & Feasibility Study | 1 | 342000 | 342000
| Total Feasibility Study |  |  | 342000
203 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Architectural Fees
1 | Conceptual & Brand Development | 1 | 45000 | 45000
2 | Interior Design | 1 | 90000 | 90000
3 | Architecture & Engineering | 1 | 3100000 | 3100000
4 | Architecture |  | 0 | 0 | Carried in line #3
5 | MEP Engineering |  | 0 | 0 | Carried in line #3
6 | Structural Engineering |  | 0 | 0 | Carried in line #3
7 | MEP Consultant | 1 | 30000 | 30000
8 | Lighting Design (Bandit) | 1 | 51000 | 51000
9 | Kitchen Equipment Design (TriMark) | 1 | 20000 | 20000
10 | LV/AV Design | 1 | 35000 | 35000
11 | Signage & Way Finding Design | 1 | 75000 | 75000
12 | Renderings | 1 | 50000 | 50000
13 | Reimbursables | 1 | 30000 | 30000
| Total Architectural Fees |  |  | 3526000
204 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Civil Engineering
1 | Civil Engineering | 1 | 10000 | 10000 | Exterior work: New Sidewalks, Street Work
| Total Civil Engineering |  |  | 10000
205 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Traffic Engineering
1 | Traffic Engineering | 1 | 10000 | 10000 | Verify w/ Traffic Consultant Report
2 |  |  | 0 | 0
| Total Traffic Engineering |  |  | 10000
206 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Acoustical Engineering
1 | Sound and Vibration Testing | 1 | 15000 | 15000 | Sound & Vibration Testing / Design Documentation & Consulting
4 |  |  | 0 | 0
5 |  |  | 0 | 0
| Total Acoustical Engineering |  |  | 15000
207 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Geotechnical Engineering
1 | Geotechnical Engineering | 1 | 150000 | 150000 | 13 Borings 50' deep required for ST Permit
| Total Geotechnical Engineering |  |  | 150000
208 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Environmental Studies
1 | Carried in Feasibility Study |  |  | 0
| Total Environmental Studies |  |  | 0
209 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Zoning / Permit Fees
1 | Permit fees & plan review fees | 1 | 493297.4767 | 493297.4767 | 1.3% Trade Costs
2 | Special Projects Program | 1 | 50000 | 50000
3 | MEP and misc. permit fees | 1 | 10000 | 10000
4 | Expeditor (allowance for Addt'l services) | 0 |  | 0
5 | FA Consultant & Expediting Services | 1 | 35000 | 35000 | Consulting/ Filing/ FA Inspection Filing & Inspection Scheduling/ TCO Affidavit/ FDNY NOD
6 | Fire Safety & Emergency Action Plan | 1 | 21500 | 21500
7 | Fire Protection Plan & Filing with FDNY | 1 | 18500 | 18500
| Total Zoning / Permit Fees |  |  | 628297.4767
210 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Utility Connection Fees
1 | Electrical Service Upgrade | 1 | 50000 | 50000 | Service upgrade required. Vault located in street, new conduit and feeders from vault into MPOE electrical room. Only Con Ed costs carried.
| Total Utility Connection Fees |  |  | 50000
211 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Attorney Fees
1 | SLA Legal Fees carried in Feasibility DD | 0 | 0 | 0
| Total Attorney Fees |  |  | 0
212 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Testing / Quality Control
1 | Controlled inspections | 1 | 50000 | 50000
2
| Total Testing / Quality Control |  |  | 50000
213 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Project Management
1 | Project Management | 1 | 500000 | 500000
2 | Estimating Services | 1 | 20000 | 20000
3 |  |  | 0 | 0
| Total Miscellaneous |  |  | 520000
214 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | NOTES
Reimbursable Expenses
1 |  | 0 | 0 | 0
1 |  |  | 0 | 0
4 |  |  | 0 | 0
5 |  |  | 0 | 0
6 |  |  | 0 | 0
| Total Reimbursable Expenses |  |  | 0
| TOTAL SOFT COSTS |  |  | 6784977.4767
300 | FF&E COSTS
SEATING & FURNITURE
301 | DESCRIPTION | QTY | UNIT PRICE | BUDGET TOTAL | VENDOR | NOTES
Seating and Accessories
1 | Theater Ground Floor GA Cushioned Folding Chairs | 3714 | 125 | 464250
2 | Mezzanine Level Box Chairs | 657 | 300 | 197100
3 | Mezzanine Level Elevated Chairs | 63 | 300 | 18900
4 | Mezzanine Level Elevated Couches | 15 | 2500 | 37500
5 | Mezzanine Level Elevated Coffee Tables | 24 | 250 | 6000
6 | Stage R&L Viewing Boxes | 2 | 7500 | 15000
7 | VIP Lounge Furniture | 1 | 75000 | 75000 | 2nd Fl / 3rd Fl
8 | VIP Lounge Roof Terrace Furniture | 1 | 15000 | 15000
9 | Restaurant Furniture | 1 | 60000 | 60000
10 | Restaurant Terrace Furniture | 1 | 10000 | 10000
11 | Roof Terrace Furniture | 1 | 25000 | 25000
12 | Roof Lounge Furniture | 1 | 35000 | 35000
13 | Dressing Room Furniture | 6 | 10000 | 60000
14 | Crew & Artist Lounge Area | 1 | 25000 | 25000
15
16
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0
21 |  |  |  | 0
22 | Artist & Crew Furniture | 0 | 0 | 0
| Total Seating/Accessories |  |  | 1043750
| SUB-TOTAL FURNITURE |  |  | 1043750
BAR & KITCHEN EQUIPMENT
302 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
| Bar Equipment |  |  |  | * BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K
1 | Kitchen Equipment | 1 | 130000 | 130000
2 | Lobby Bar Equipment | 5 | 9000 | 45000
3 | Music Hall House Left Bar | 16 | 9000 | 144000
4 | Music Hall House Right Bar | 15 | 9000 | 135000
5 | Music Hall Rear Bar | 14 | 9000 | 126000
6 | Mezz. House Right Bar | 8 | 9000 | 72000
7 | Mezz. House Left Bar | 8 | 9000 | 72000
8 | VIP Lounge Bar including Roof | 2 | 20000 | 40000
9 | Restaurant Bar | 2 | 20000 | 40000
10 | Roof Lobby Bar | 4 | 12000 | 48000
11 | Ice Machines | 4 | 15000 | 60000
12 | Walk-In Coolers | 2 | 15000 | 30000
13 | Freight & Installation | 1 | 375000 | 375000
14 |  |  |  | 0
15 |  |  |  | 0
16 | POS | 0 | 3000 | 0 | Lease POS terminals / lease costs carried under operating costs
| Total Concessions |  |  | 1317000
| SUB-TOTAL CONCESSIONS |  |  | 1317000
DATA SYSTEMS / IT / CCTV
303 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Data Systems / IT / CCTV
1 | Data Cabling |  |  |  | Carried Construction Costs
2 | VoIP Phones / Data Switch / WiFi | 1 | 200000 | 200000
3 | CCTV - Security Cameras | 110 | 2000 | 220000
| Total Data Systems |  |  | 420000
| SUB-TOTAL DATA SYSTEMS |  |  | 420000
OFFICE FURNITURE
304 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Office Furniture/Accessories
Administration
1 | Administration Furniture | 1 | 50000 | 50000
2 | Admin.Appliances |  | 0 | 0
Production
1 | Desks-Production | 1 | 15000 | 15000
2 | Desk Chairs-Production |  | 0 | 0
| Total Office Furniture/Access. |  |  | 65000
| SUB-TOTAL OFFICE FURNITURE |  |  | 65000
SIGNAGE / SCENIC
305 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Exterior Builidng Signage
1 | Exterior Signage | 1 | 400000 | 400000
| Total Exterior Builidng Signage |  |  | 400000
Wayfinding
1 | Interior Wayfinding and ADA Signage | 1 | 100000 | 100000
| Total Wayfinding |  |  | 100000
Art
1 | Interior Art and Décor | 1 | 150000 | 150000 | Inerior Scenic Work & Exterior Building Murals
| Total Art |  |  | 150000
| SUB-TOTAL SIGNAGE / SCENIC |  |  | 650000
ADMINISTRATION
306 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Office Equipment
1 | Safe-Accounting | 1 | 1000 | 1000
2 | Safe-Box Office | 1 | 1000 | 1000
3 | Safe-Concessions | 1 | 1000 | 1000
| Radios | 1 | 20000 | 20000
| Total Office Equipment |  |  | 23000
Metal Detectors
1 | Metal Detectors | 1 | 70000 | 70000
| Total Metal Detectors |  |  | 70000
| SUB-TOTAL ADMINISTRATION |  |  | 93000
FACILITY
307 | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Administration/Main Entrance
1 | Merch Cases | 1 | 26000 | 26000
| Total Admin/Main Entrance |  |  | 26000
Landscape Furniture
1 |  | 0 | 0 | 0
| Total Landscape Furniture |  |  | 0
Lighting/Sound/Video-Other
1 |  | 0 | 0 | 0
| Total Lighting/Sound/Video |  |  | 0
| SUB-TOTAL FACILITY |  |  | 26000
OPERATIONS
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Custodial Equipment
1 | Venue Trash Cans | 80 | 150 | 12000
2 | Decorative Trash Cans | 0 | 0 | 0
3 | Janitor Carts | 2 | 500 | 1000
| Total Custodial Equipment |  |  | 13000
Landscape Equipment
1 |  |  | 0 | 0
| Total Landscape Equipment |  |  | 0
| Miscellaneous Equipment |  | 0
1
| Total Misc. Equipment |  |  | 0
Security/Police/Traffic
1 | Bicycle Rack | 1 | 1000 | 1000
2 | Police Barricades | 1 | 10000 | 10000
3
| Total Sec/Police/Traffic |  |  | 11000
Shop Equipment
1 | Hand Tools-Miscellaneous | 1 | 3000 | 3000
2 | Ladders | 1 | 1000 | 1000
3 | Shelving / Cabinets | 1 | 1000 | 1000
| Total Shop Equipment |  |  | 5000
| SUB-TOTAL OPERATIONS |  |  | 29000
PRODUCTION
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
Production FF&E
1 | AVS - Test |  | 0 | 0
2 | Stage Barricade | 1 | 18000 | 18000
3 | Portable Stage | 1 | 30000 | 30000
4 | Fork Lift | 1 | 35000 | 35000
5 | Scissor Lift | 1 | 25000 | 25000
6 | Washer & Dryer | 1 | 5000 | 5000
7 | Risers | 1 | 12000 | 12000
8 | Dock Plates/Ramps/Hand Carts & Dollies | 1 | 30000 | 30000
9 | Hand Cart & Dollies | 1 | 30000 | 30000
10 | Storage Shelving | 1 | 1500 | 1500
11 | Tools | 1 | 7000 | 7000
| Total Production FF&E |  |  | 193500
Soft Goods
1 | All soft goods | 1 | 500000 | 500000 | Stage / Perimeter Walls Music Hall - CUTDOWN DRAPE @ MEZZ EDGE Not Included
| Total Soft Goods |  |  | 500000
Video System
1 | Music Hall Projector | 1 | 75000 | 75000
2 | Displays & Distribution | 1 | 200000 | 200000
3 | VIP Lounge Projector | 1 | 10000 | 10000
4 | Upstage Video Wall |  |  |  | $1,400/SF
5 | Overhead Video Wall
| Total Video System |  |  | 285000
Audio System
1 | House Sound System | 1 | 1400000 | 1400000 | Includes Theater / VIP / Restaurant & Roof Area
| Total Audio System |  |  | 1400000
Production Lighting
1 | Performance Lighting | 1 | 520000 | 520000
2 | Performance Lighting VIP |  | 0 | 0
| Total Performance Lighting |  |  | 520000
| SUB-TOTAL PRODUCTION |  |  | 2898500 |  | Misc. Equipment $60K, Soft Goods $725k, Video $236k, Audio $690k, Performance Lighting $450k
ARCHITECTURAL LIGHTING
# | DESCRIPTION | QTY | PRICE | BUDGET | VENDOR | NOTES
1 | Architectural & Exterior Lighting | 1 | 1750000 | 1750000
1750000
| SUB-TOTAL ARCHITECTURAL LIGHTING |  |  | 1750000

## Building & Fit-outBudget Detail
Venue
Scope : | Warehouse Conversion / Add Second Level & Roof Decks
Capacity: | 7440
SF: | 135953
Date: | 2026-09-16
Version: | 1
100 | BUILDING & FIT-OUT COSTS
CSI # | TRADE | BUDGET | COST/SF | NOTES
013000 | PROJECT REQUIREMENTS | 3034000 | 22.3165
015800 | SCAFFOLDING & STAGING | 6170000 | 45.3833
024100 | DEMOLITION | 1287817 | 9.4725
033000 | CONCRETE | 177450 | 1.3052
042000 | MASONRY | 530010 | 3.8985
044000 | STONE & CERAMICS | 764340 | 5.6221
055100 | STRUCTURAL STEEL & MISC METALS | 0 | 0
061000 | ROUGH CARPENTRY | 0 | 0
064000 | MILLWORK AND FURNITURE INSTALL | 0 | 0
075000 | ROOFING | 2557428 | 18.8111
078100 | FIREPROOFING | 0 | 0
081000 | DOORS, FRAMES & HARDWARE | 0 | 0
083000 | SPECIAL DOORS | 76000 | 0.55902
084100 | STOREFRONT | 0 | 0
088000 | GLASS/GLAZING | 0 | 0
092000 | DRYWALL | 119664 | 0.88019
092300 | TILE/BRICK TILE | 0 | 0
096000 | CARPET/RESILIENT FLOORING | 765048 | 5.6273
096050 | FLOOR PREPARATION | 515298 | 3.7903
096400 | WOOD FLOORING | 373050 | 2.744
099000 | PAINTING/PLASTER | 1091765 | 8.0305
100000 | SPECIALITIES | 1548500 | 11.39
100500 | ACOUSTICAL PANELS/K13 | 581802 | 4.2794
101400 | SIGNAGE | 50000 | 0.36777
120000 | FF&E INSTALL | 50000 | 0.36777
114000 | FOOD SERVICE AND BAR EQUIPMENT | 50000 | 0.36777
142000 | ELEVATOR | 480000 | 3.5306
210000 | FIRE PROTECTION | 1334070 | 9.8127
220000 | PLUMBING | 3717250 | 27.3422
230000 | HVAC | 5964390 | 43.871
260000 | ELECTRIC | 5512336.75 | 40.5459
270000 | LOW VOLTAGE CABLING | 227500 | 1.6734
265000 | LIGHTING | 40000 | 0.29422
283100 | FIRE ALARM | 521906 | 3.8389
320000 | SITEWORK | 346335 | 2.5475
001000 | PRECONSTRUCTION | 60000 | 0.44133
010000 | GENERAL CONDITIONS | 0 | 0 | Carried in budget summary
010001 | BONDS | 0 | 0 | NIC
| SUB TOTAL | 37945959.75 | 279.1109
500005 | G.L. INSURANCE | 0 | 0
500006 | BUILDERS RISK INSURANCE | 0 | 0
| C.M. OVERHEAD & FEE | 0 | 0
| SUB TOTAL | 37945959.75
500010 | STATE/PROJECT TAX (IF APPLICABLE) | 0 | 0
700002 | DESIGN CONTINGENCY | 0 | 0
700003 | CONSTRUCTION CONTINGENCY | 0 | 0
700004 | EXPEDITING/OVERTIME CONTINGENCY | 0 | 0
| TOTAL | 37945959.75

## Building & Fit-out Breakdown
Venue
Scope: | Warehouse Conversion / Add Second Level & Roof Decks
Capacity: | 7440
SF: | 135953
Date: | 2026-09-16
Architect: | Wake
Version: | 1
ITEM | DESCRIPTION | QTY | UNIT | UNIT PRICE | TOTAL | NOTES
013000 | PROJECT REQUIREMENTS
1 | BIM Set Up & Coordination | 1 | LS | 30000 | 30000
2 | Plans / Reprographics | 1 | LS | 7500 | 7500
3 | Site Office & Equipment | 1 | LS | 12000 | 12000
4 | Field Techonology | 1 | LS | 200000 | 200000
5 | Construction Signage | 1 | LS | 4500 | 4500
6 | Site Security | 1 | LS | 13000 | 13000
7 | Site Safety Plan / First Aid / TPP / FE's / Safety Inspector | 1 | LS | 400000 | 400000
8 | Portable Toilets | 80 | WK | 400 | 32000
9 | Clean up Materials | 1 | LS | 65000 | 65000
10 | Protection Materials | 1 | LS | 50000 | 50000
11 | Project Labor | 1 | LS | 2000000 | 2000000
12 | Project Rubbish Removals | 1 | LS | 120000 | 120000
13 | Final Clean | 1 | LS | 100000 | 100000
Sub Total | PROJECT REQUIREMENTS |  |  |  | 3034000
015800 | SCAFFOLDING & HOARDING
1 | Install sidewalk bridge and scaffolding around building | 1 | LS | 4000000 | 4000000 |  |  | 500/LF bridge
|  | 1126 | LF | 500
|  | 27024 | SF | 75
2 | Interior scaffolding | 1 | LS | 2000000 | 2000000 |  |  | $75/SF for scaffolding
3 | Barricades | 1 | LS | 150000 | 150000
| Site safety During Erection | 1 | LS | 20000 | 20000
4
Sub Total | SCAFFOLDING & HOARDING |  |  |  | 6170000
024100 | DEMOLITION
1 | Demo existing CMU/masonry walls at new Entry/Lobby area | 2500 | SF | 12 | 30000
2 | Demo 8" CMU interior wall 20' tall | 1975 | SF | 12 | 23700
3 | Demo 8" CMU interior wall 12' tall | 7536 | SF | 12 | 90432
4 | Demo office area partitions, ceilings, doors, flooring MEP's, (CMU walls line above) | 6825 | SF | 5 | 34125
5 | Demo existing exterior roll up doors | 8 | EA | 5000 | 40000
6 | Demo existing exterior doors | 7 | EA | 250 | 1750
7 | Demo existing windows 1'x10' | 34 | EA | 300 | 10200
8 | Demo ceiling mount steam heaters and associated piping | 28 | EA | 750 | 21000
9 | Demo 5,250MBH boiler and piping (15'x6'x7' 13,000lbs) | 2 | EA | 20000 | 40000
10 | Demo misc. piping, lighting, electrical panels / switchgear / appurtenances throughout space | 1 | SF | 74000 | 74000
11 | Demo dock levelers | 3 | EA | 2500 | 7500
12 | Demo slab at load-in ramp plan west | 1423 | SF | 10 | 14230
13 | Trench slab for new grade beams at new façade | 132 | LF | 100 | 13200 |  | $2,500/cy
14 | Demo / excavate 6" slab 4' tall at load-in area | 2640 | SF | 12 | 31680 |  | $2,500/cy
15 | Trench slab for below grade sanitary line for bars and bathrooms | 800 | LF | 80 | 64000 |  | Trenching $150/LF Pour back $50K/LF
16 | Demo / excavate elevator pits | 2 | EA | 25000 | 50000 |  | New Elvator 4' pit $50K excavate and concrete
17 | Shoring Demo of Steel | 1 | LS | 50000 | 50000
18 | Demo Steel Columns / Roof Steel | 1 | EA | 100000 | 100000
19 | Demo Pre-cast concrete roof | 74000 | SF | 8 | 592000 | Abatement by others
20 | Allow for Floor trenching for MEPS | 0 | LS | 50000 | 0
21 | Demo floor for Recessed floor - Include Excavation | 0 | SF | 0 | 0 | Included Above
22 | Misc Façade Demo Along Johnson Ave (Doors, Roll-ups, Windows, etc.) | 0 | LS | 20000 | 0
Sub Total | DEMOLITION |  |  |  | 1287817 | $10/SF
033000 | CONCRETE
1 | Excavation related to New Columns at Music hall | 0 | SF | 6.5 | 0 | Based on Footprint of New Roof
2 | CMU wall footing excavation allow 2' deep for new Load bearing wall at Music hall- East wall | 0 | LF | 150 | 0
3 | Concrete at New footings | 0 | EA | 7500 | 0
| Excavate & Install New Footings at Stage |  |  |  | 0
[5 empty] | 0 |  | 4
| 1st Floor Raised Slab - Concrete on Styrofoam 24" | 1500 | CY | 70 | 105000 | 20,314 SF (Includes two ramps down to GA)
| Concrete ramp stage |  |  |  | 0
| Concrete 4'6" H on Styrofoam | 0 | SF | 50 | 0
| Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50 | 0
0
0
| F/I new foundation wall / perimeter grade beam | 132 | LF | 300 | 39600 |  | $750/CY
| F/I new retaining wall at load-in area excavate slab 4' tall | 219 | LF | 150 | 32850 | 877 SF | $100/CY
4 | Concrete at CMU footing | 0 | LF | 100 | 0
5 | Patch slab due to New footing | 0 | SF | 30 | 0
6 | Patch conc. At Trenching for MEPS | 0 | SF | 30 | 0
7 | New slab Pour-back at Excavated Areas | 0 | SF | 30 | 0
8 | New slab at Recessed floor | 0 | SF | 0 | 0 | Included Above
9 | Concrete on Deck for Mezz of Music Hall with Platforms | 0 | SF | 25 | 0
10 | Concrete In-fill on New Pan Stairs | 0 | EA | 4000 | 0 | (2) Feature Stairs, (2) BOH Stairs
11 | Grouting at Steel Trusses & Column Base Plates | 0 | LS | 15000 | 0
12 | Polished concrete | 0 | SF | 8 | 0
13 | Concrete pads | 0 | LS | 10000 | 0
14 | Patch sidewalk | 0 | LS | 35000 | 0
15 | Misc. Equipment Pads | 0 | LS | 25000 | 0
16 | Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50 | 0
Sub Total | CONCRETE |  |  |  | 177450
042000 | MASONRY
FIRST FLOOR
1 | Patch & Repair Existing Masonry Wall | 9972 | SF | 10 | 99720
| New Masonry Wall at Entry Lobby Area | 2022 | SF
| CMU and Brick façade at removed windows | 34 | SF
CMU and Brick façade at removed doors
CMU and Brick façade at removed rolling grilles
Patch masonry at new exterior doors
Patch Masonry at louver openings
| F&I CMU wall vestibule stair tower 1 1st FL | 0 | SF | 35
F&I CMU wall vestibule stair tower 2 1st Fl
F&I CMU wall vestibule stair tower 1 2nd FL
F&I CMU wall vestibule stair tower 2 2nd FL
F&I CMU wall vestibule stair tower 1 3rd Fl
F&I CMU wall vestibule stair tower 2 3rd Fl
| F&I CMU elevator tower entrance | 3220 | SF | 35 | 112700
| F&I CMU elevator tower Stage | 2977 | SF | 35 | 104195
| F&I CMU at back wall of music hall | 6097 | SF | 35 | 213395
2 | F&I Brick façade at music hall bump up | 0 | SF | 35 | 0
3 | CMU and Brick infills at old windows and door opening | 0 | SF | 70 | 0
4 | Repair/ cleaning and minor repointing of existing brick facade | 0 | SF | 10 | 0
5 | Misc. Patching allow at penetrations | 0 | LS | 5000 | 0
Sub Total | MASONRY |  |  |  | 530010
044200 | STONE & CERAMICS
1 | Lobby stone flooring | 6442 | SF | 45 | 289890
2 | VIP Lounge Stone Floorin | 1614 | SF | 45 | 72630
3 | Roof Lobby Stone Flooring | 1816 | SF | 45 | 81720
4 | Courtyard Stone Pavers | 4268 | SF | 75 | 320100
Sub Total | STONE & CERAMICS |  |  |  | 764340
055100 | STRUCTURAL STEEL & MISC METALS
1 | Disconnect roof framing for Demo & Shore at select areas | 0 | SF | 5 | 0
2 | F&I new Roof Trusses, girders, Columns at Music Hall area | 0 | TONS | 6000 | 0
3 | F&I Roof deck | 0 | SF | 4 | 0
F&I Steel for Stage Support
F/I metal decking Stage
4 | Steel Framing at Mezz area - Including Elevated Standing & Box Seating | 0 | TONS | 6000 | 0
5 | Steel Framing at upper balcony - incluing balcony seating | 0 | TONS | 6000 | 0
6 | Stage Lighting & AV support structure | 0 | LBS | 8 | 0
7 | Small stair to access Stage | 0 | EA | 13000 | 0
8 | Roof Dunnage for HVAC Equipment's | 0 | LOC | 20000 | 0
9 | Roof Penetrations framing for Toilet exhaust & Kitchen exhaust | 0 | LS | 25000 | 0
10 | Stairs | 0 | FL | 30000 | 0
11 | Allow for Unistrut at select area of stage | 0 | SF | 35 | 0
12 | Railing at Roof Deck | 0 | LF | 500 | 0
13 | Railing at Theatre | 0 | LF | 275 | 0
14 | Misc. Lintels | 0 | LS | 10000 | 0
15 | Allow for access Ladders at Stage Overhead lighting grid area | 0 | LS | 15000 | 0
Sub Total | STRUCTURAL STEEL & MISC METALS |  |  |  | 0
062000 | Rough Carpentry/OSHA Protection
1 | Safety Protection at Roof cut out | 0 | LS | 35000 | 0
2 | Safety Protection at Footings trenches | 0 | LS | 30000 | 0
2 | Entry Barricade | 0 | SF | 40 | 0
3 | Safety at New Mezz Build outs | 0 | SF | 2 | 0
3 | Rough Carpentry work at Stage area | 0 | SF | 5 | 0
Sub Total | Rough Carpentry/OSHA Protection |  |  |  | 0
064000 | MILLWORK
1 | Lobby Bar/Back Bar - Complete | 0 | LF | 2000 | 0
2 | VIP Bar/Back Bar - Complete | 0 | LF | 2000 | 0
3 | Music Hall GA Bar/Back Bars - Complete | 0 | LF | 2000 | 0
4 | Mezzanine Bar/Back Bars - Complete | 0 | LF | 2000 | 0
5 | Balcony bar/back bar- complete | 0 | LF | 2000 | 0
6 | Upper lounge bar/back bar- complete | 0 | LF | 2000 | 0
7 | Lower lounge bar/back bar- complete | 0 | LF | 2000 | 0
8 | Foundry bar/back bar- complete | 0 | LF | 2000 | 0
9 | Decorative Features Above Each Back Bar | 0 | EA | 10000 | 0
10 | Green room Bathrooms & Counter tops | 0 | LF | 350 | 0
11 | Public Bathroom Counter top | 0 | LF | 400 | 0
12 | Millwork at Merchandise | 0 | LS | 12000 | 0
13 | Pantry at Office Area | 0 | LF | 850 | 0
14 | Millwork shelf & Pole at Coat closet area | 0 | LF | 150 | 0
15 | Install Furniture | 0 | LS | 25000 | 0
16 | Additional millwork in public areas | 0 | LS | 30000 | 0
17 | Decorative Millwork at Proscenium | 0 | EA | 10000 | 0
18 | Millwork at BOX Office | 0 | LF | 500 | 0
Sub Total | MILLWORK |  |  |  | 0
075000 | ROOFING
1 | 2nd Floor Terrace Roof Membrane | 2041 | SF | 36 | 73476
2 | 3rd Floor Terrace Roof Membrane VIP | 1592 | SF | 36 | 57312
3 | 3rd Floor Terrace Roof Membrane Restaurant | 4432 | SF | 36 | 159552
4 | Music Hall low roof | 17547 | SF | 36 | 631692
5 | Music Hall Upper level | 30000 | SF | 36 | 1080000
6 | 3rd Floor Roof | 8538 | SF | 36 | 307368
7 | 2nd Floor concrete pavers on pedestals | 2041 | SF | 36 | 73476
8 | 3rd Floor Terrace concrete pavers on pedestals VIP | 0 | SF | 31 | 0
9 | 3rd Floor Terrace concrete pavers on pedestals Restaurant | 4432 | SF | 36 | 159552
10 | Patch roofing at Misc. Penetrations | 1 | LS | 15000 | 15000
Sub Total | ROOFING |  |  |  | 2557428
078100 | FIREPROOFING
1 | Allow for fireproofing at New steel at Roof | 0 | SF | 5 | 0
2 | Allow for fireproofing at New steel at Mezzanine | 0 | SF | 5 | 0
3 | Add fireproofing to existing roof steel | 0 | SF | 5 | 0
Sub Total | FIREPROOFING |  |  |  | 0
081000 | DOORS, FRAMES & HARDWARE
1 | Single Hollow Metal Doors - Non-Acoustical | 0 | EA | 2200 | 0 |  | Storefront double door
2 | Double Hollow Metal Doors - Non-Acoustical | 0 | EA | 3200 | 0 |  | F/I HM Double Door & hardware
3 | Acoustical doors at Music Hall | 0 | EA | 10000 | 0
4 | Acoustical double doors at Music Hall | 0 | PAIR | 20000 | 0
Sub Total | DOORS, FRAMES & HARDWARE |  |  |  | 0
083000 | SPECIAL DOORS
1 | Eliason doors | 2 | EA | 3000 | 6000
| Rolling Grille | 40 | LF | 1750 | 70000
Sub Total | SPECIAL DOORS |  |  |  | 76000
084100 | STOREFRONT
1 | F&I New Storefront with Doors | 0 | SF | 250 | 0
2 | F&I New Storefront with doors to roof deck | 0 | SF | 150 | 0
3 | Storefront double door to roof deck | 0 | PAIRS | 4500 | 0
4 | Interior Storefront at VIP Lounge | 0 | SF | 75 | 0
5 | Interior Storefront at foundry | 0 | SF | 75 | 0
6 | Interior double door at VIP Lounge | 0 | PAIR | 4500 | 0
Sub Total | STOREFRONT |  |  |  | 0
088000 | GLAZING
2 | Mirror at Bathrooms- Public | 0 | SF | 50 | 0
3 | Mirror at Green room | 0 | SF | 50 | 0
4 | Mirror behind bars | 0 | LOT | 35000 | 0
5 | Ballistic Box office window | 0 | LOT | 10000 | 0
Sub Total | GLAZING |  |  |  | 0
092000 | DRYWALL
FIRST FLOOR
1 | Perimeter wall partition at existing exterior wall | 9972 | SF | 12 | 119664
| Perimeter wall partition at new exterior wall | 2022 | SF
| 2HR Fire Rated Wall Reat Stage - 20' High | 5565 | SF
| 2HR Fire Rated Wall Rear Music Hall - 20' High | 2857 | SF
| F/I Plywood 8'AFF at Stage Walls | 1672 | SF
| F/I 2" Insulation above 8' AFF Floor to 38'AFF | 6932 | SF
| F/I Proscenium Wall | 4194 | SF
SECOND FLOOR
THIRD FLOOR
2 | Perimeter wall furring/sheathing at new Music Hall bump up | 0 | SF | 20 | 0
3 | Interior Sound/Fire rated walls at music hall, stair ways and elevator shafts | 0 | SF | 20 | 0
4 | Interior Non Sound walls | 0 | SF | 12 | 0
5 | Drywall ceilings | 0 | SF | 12 | 0
6 | Acoustical Ceilngs | 0 | SF | 10 | 0
7 | Install Doors/Frames/Hardware | 0 | EA | 650 | 0
8 | Blocking | 0 | LS | 30000 | 0
9 | FRP Kitchen walls | 0 | SF | 15 | 0
10 | Diamond wall plates at Loading dock area for wall protection | 0 | SF | 15 | 0
11 | Install Items Furnished By Others | 0 | LS | 25000 | 0
Sub Total | DRYWALL |  |  |  | 119664
092300 | TILE
1 | Tile at Restroom/Shower Floors | 0 | SF | 30 | 0
2 | Tile at Restroom Walls | 0 | SF | 30 | 0
3 | Faux brick at Lobby | 0 | SF | 35 | 0
4 | Tile at Bar Floors | 0 | SF | 20 | 0
5 | Tile & Base at Kitchen | 0 | SF | 20 | 0
Sub Total | TILE |  |  |  | 0
096000 | CARPET/RESILIENT FLOORING
1 | Carpete tile at office and production | 0 | SF | 5.5 | 0
2 | LVT Flooring at Green room areas and Dresssing rooms | 0 | SF | 10 | 0
3 | LVT Music Hall and egress stair landings | 30505 | SF | 20 | 610100
4 | LVT Coatcheck | 1189 | SF | 12 | 14268
5 | VCT in coat room/box office | 0 | SF | 7 | 0
6 | F&I Vinyl Base | 0 | LF | 2.75 | 0
| Sealed concrete stage load-in / 1st Fl BOH | 7034 | SF | 20 | 140680
7 | Minor Prep floor | 0 | SF | 1.5 | 0
8 | Entry Mats | 0 | SF | 100 | 0
9 | Stair Treads | 0 | LS | 17500 | 0
Sub Total | CARPET/RESILIENT FLOORING |  |  |  | 765048
096050 | FLOOR PREPARATION
1 | Music Hall shot blasting & MVB | 24538 | SF | 12 | 294456
2 | Music Hall cement overlay and top coat | 24538 | SF | 9 | 220842
3 | Music Hall sealed concrete at new concrete areas | 0 | SF | 5 | 0
Sub Total | FLOOR PREPARATION |  |  |  | 515298
096400 | WOOD FLOORING
1 | F&I T&G Wood floor at Stage | 4634 | SF | 45 | 208530
2 | Wood Flooring Restaurant | 3656 | SF | 45 | 164520
Sub Total | WOOD FLOORING |  |  |  | 373050
099000 | PAINTING/PLASTER
1 | Paint all Walls & Doors & Ceilings | 135953 | SF | 5 | 679765
2 | Upgrade finishes at walls in Green room area | 1 | LS | 12000 | 12000
3 | Plaster | 0 | SF | 25 | 0
4 | Wall Covering VIP / Restaurant | 5000 | SF | 80 | 400000
Sub Total | PAINTING/PLASTER |  |  |  | 1091765
100000 | SPECIALTIES
1 | Fire extinguishers & cabinets | 60 | EA | 350 | 21000
2 | Toilet Acc | 178 | SET | 600 | 106800
3 | Toilet Partitions | 178 | EA | 1750 | 311500
4 | Urinal screens | 51 | EA | 500 | 25500
5 | Bathroom Mirrors | 154 | EA | 300 | 46200
6 | Hand dryers and paper towel dispensers | 1 | Allow | 30000 | 30000 |  |  |  | 500
7 | Appliances at Pantry | 1 | Allow | 7500 | 7500
8 | Coat Check Lockers | 2000 | EA | 500 | 1000000 | 333LF
Sub Total | SPECIALTIES |  |  |  | 1548500
100500 | ACOUSTICAL PANELS/ K13
1 | Allowance for wall mount acoustic panels, decorative acoustic integrations | 1 | Allow | 150000 | 150000
2 | K13 at Underside Music Hall Ceilings | 30843 | SF | 14 | 431802
Sub Total | ACOUSTICAL PANELS/ K13 |  |  |  | 581802
101400 | SIGNAGE
1 | Allow for interior Door signs | 1 | Allow | 45000 | 45000
2 | Allow for Directional signage | 0 | LOT | 0 | 0
3 | Install misc signage allowance | 1 | LOT | 5000 | 5000
Sub Total | SIGNAGE |  |  |  | 50000
101400 | FF&E Install
1 | Uncrate / dispose owner vendor FF&E | 1 | Allow | 50000 | 50000
Sub Total | FF&E Install |  |  |  | 50000
114000 | FOOD SERVICE EQUIPMENT - BY OWNER
1 | F&I Food service equipment | 0 | LS |  | 0 | By owner vendor
2 | Hood Fire Protection system | 0 | LS |  | 0 | By owner vendor
3 | F&I Kitchen exhaust hood | 1 | Allow | 15000 | 15000 | Misc scope not covered by OV
4 | Dispose of owner vendor packaging & misc. scope | 1 | Allow | 35000 | 35000
Sub Total | FOOD SERVICE EQUIPMENT - BY OWNER |  |  |  | 50000
142000 | ELEVATOR
1 | Elevator Lobby | 4 | STOPS | 75000 | 300000
2 | Elevator Stage | 2 | STOPS | 75000 | 150000
3 | Hydraulic Lift 12'x6' | 1 | EA | 30000 | 30000
Sub Total | ELEVATOR |  |  |  | 480000
210000 | FIRE PROTECTION
1 | Safe Off / Disconnect | 1 | LS | 10000 | 10000
2 | First Floor Rework Existing Fire Protection System First | 69000 | SF | 4 | 276000
3 | 2nd Floor Extend Sprinkler Mains / New Fire Protection & Stand Pipe | 50000 | SF | 15 | 750000
4 | 3rd Floor Extend Sprinkler Mains / New Fire Protection & Stand Pipe | 8538 | SF | 15 | 128070
5 | New Diesel Fire Pump 1,00 GPM 65PSI 75HP motor | 1 | LS | 150000 | 150000 | Requires dedicated 2/hr rated room,
6 | Fire Stopping | 1 | LS | 20000 | 20000
Sub Total | FIRE PROTECTION |  |  |  | 1334070
220000 | PLUMBING
1 | F&I new 6" C.W service with RPZ with water meter | 1 | LS | 50000 | 50000
2 | F/I new 6" sanitary service | 2 | EA | 10000 | 20000
3 | F/I new storm water detention tank | 1 | LS | 35000 | 35000
| F&I |  | LS
1 | Water piping | 2500 | LF | 85 | 212500
2 | Vent piping | 2400 | LF | 65 | 156000
3 | Gas Pipe | 450 | LF | 125 | 56250
| New storm drainage piping | 550 | LF | 100 | 55000
4 | W/C 1st Fl | 92 | EA | 4000 | 368000
5 | W/C 2nd Fl | 75 | EA | 4000 | 300000
6 | W/C Roof | 11 | EA | 4000 | 44000
7 | Lavs 1st Fl | 68 | EA | 4000 | 272000
8 | Lavs 2nd Fl | 66 | EA | 4000 | 264000
9 | Lavs 3rd Fl | 20 | EA | 4000 | 80000
10 | Urinals 1st Fl | 32 | EA | 4000 | 128000
11 | Urinals 2nd Fl | 13 | EA | 4000 | 52000
12 | Urinals Roof | 6 | EA | 4000 | 24000
13 | Showers | 6 | EA | 5000 | 30000
14 | Green room sinks | 6 | EA | 5500 | 33000
15 | Pantry sinks | 2 | EA | 6000 | 12000
16 | Water fountains | 4 | EA | 5500 | 22000
17 | Floor Drains & Sinks | 65 | EA | 3500 | 227500
18 | Water Heater- Electrical | 10 | EA | 7500 | 75000
19 | F&I Bar roughing | 9 | EA | 30000 | 270000
20 | Grease Traps Bars | 9 | EA | 7500 | 67500
21 | Grease Trap Restaurant | 1 | EA | 125000 | 125000
20 | Restaurant Bar | 1 | EA | 75000 | 75000
21 | Lobby Bar | 2 | EA | 50000 | 100000
22 | VIP Bars | 2 | EA | 40000 | 80000
23 | Music Bars | 5 | EA | 40000 | 200000
24 | F&I Kitchen roughing | 1 | LS | 135000 | 135000
25 | F&I Roof Drains | 11 | EA | 8500 | 93500
26 | Demo. Disconnects | 1 | LS | 10000 | 10000
27 | Misc Equipment | 1 | LS | 30000 | 30000
28 | Firestopping | 1 | LS | 15000 | 15000
Sub Total | PLUMBING |  |  |  | 3717250
230000 | HVAC
1 | HVAC System including BMS | 132542 | SF | 45 | 5964390
Sub Total | HVAC |  |  |  | 5964390
260000 | ELECTRIC
1 | Demo & Disconnects | 1 | LS | 20000 | 20000
2 | Demo & remove existing 400A service | 1 | EA | 50000 | 50000
3 | Temp Lighting & Power | 135953 | SF | 2 | 271906
Lighting
1 | F/I Emergency lighting package | 135953 | SF | 1 | 135953
2 | I/O lighting package throughout provided by others | 135953 | SF | 12 | 1631436
3 | Install architectural dimming control system, F/I wiring | 135953 | SF | 0.75 | 101964.75
| Power Wiring & Devices |  |  |  | 0
1 | F/I general power throughout - duplex, quadraplex, floor boxes, J boxes, ceiling outlets | 135953 | SF | 6 | 815718
2 | F/I dedicated circuits at all Kitchen equipment | 1500 | SF | 35 | 52500
3 | F/I dedicated power to stage equipment | 2500 | SF | 15 | 37500
4 | F/I Stage power Clean Switches | 1 | LS | 65000 | 65000
5 | Panels and Secondary distribution | 1 | LS | 200000 | 200000
Mechanical Power
1 | F/I power to Mechanical Equipment | 135953 | SF | 3 | 407859
2 | F/I power to VAV's | 15 | EA | 2500 | 37500
3 | F/I power to Exhaust Fans | 20 | EA | 5000 | 100000
4 | Combine Existing Services | 0 | LS | 200000 | 0
5 | Stand Pipe Water Booster Pump Wiring | 1 | LS | 20000 | 20000
Switch Gear & Emergency Power
1 | F/I 4,000A Service End Boxes | 2 | EA | 65000 | 130000
2 | F/I 4,000A CT Cabinets | 2 | EA | 55000 | 110000
3 | F/I 4000A 208Y/120V Switchboard w/ main Circuit Breaker | 2 | EA | 290000 | 580000
4 | Secondary service conductors, service end box to CT cabinet to Switchboard | 2 | EA | 75000 | 150000
5 | NYC electrical plan review drawings, short circuit / coordination / arch flas study and DOB electrical filing | 1 | EA | 35000 | 35000
6 | F/I 80KW Generator | 1 | LS | 275000 | 275000
7 | Con Edison customer contribution / excess distribution facilities charges | 1 | Allow | 250000 | 250000
0
| Misc. |  |  |  | 0
1 | F/I firestopping at cores & penetrations | 1 | LS | 35000 | 35000
Sub Total | ELECTRIC |  |  |  | 5512336.75
270000 | LOW VOLTAGE
1 | Wiring for security Camera | 110 | EA | 750 | 82500
2 | Door intrusion entry/exit security | 0 | LOC | 5000 | 0
3 | A/V wiring only | 1 | LS | 60000 | 60000
4 | Phone/Data wiring | 1 | LS | 85000 | 85000
Sub Total | LOW VOLTAGE |  |  |  | 227500
270000 | LIGHTING AND CONTROLS - BY OWNER
1 | Exit Signs / BOH fixtures | 1 | LS | 40000 | 40000
2 | Stage Lighting
3 | Bar Lighting
4 | Specialty Fixtures
5 | Dimming Control PKG
6 | Inverter PKG
Sub Total | LIGHTING AND CONTROLS - BY OWNER |  |  |  | 40000
283100 | FIRE ALARM
1 | F&I Fire alarm system | 135953 | SF | 2 | 271906
2 | F/I Vesda System Music Hall | 1 | LS | 250000 | 250000
Sub Total | FIRE ALARM |  |  |  | 521906
32000 | SITEWORK
1 | Patch / Repair / Install new sidewalks around building | 8295 | SF | 13 | 107835 | 8,295sf of existing sidewalk around building
2 | Trees | 1 | Allow | 30000 | 30000
3 | Fencing | 300 | LF | 100 | 30000
4 | Fie escape egress music hall Grid F to Col. 7-17 (10' wide w/ railing) | 2380 | SF | 75 | 178500 |  |  | 7140
Sub Total | SITEWORK |  |  |  | 346335

## General Conditions (hidden)
Exec | 10 | 9200 | 92000
PM | 90 | 6400 | 576000
APM | 90 | 4600 | 414000
Engineer | 90 | 3900 | 351000
Accoutnant | 10 | 2800 | 28000
0
Super | 90 | 6000 | 540000
Super | 90 | 6000 | 540000
Super | 90 | 6000 | 540000
General Super | 10 | 6000 | 60000
3141000

## Project At-a-Glance (hidden)
Cost Report Date: | 2023-01-31 |  |  | Venue Capacity: | TBD
Project Name: |  |  |  | Landlord Work Start Date: | TBD
Location: |  |  |  | LNE Work Start Date: | TBD
Address: |  |  |  | Certificate of Occupancy: | TBD
Project Number: |  |  |  | First Show Date: | TBD
Budget: | #REF! |  |  | Project Completion Date: | TBD
Venue EVP: | TBD |  |  | Project Manager: | TBD
Description | Budget | Committed Costs Total | Costs to Date Total | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance
|  | Total | Total
Building Costs | 63651264.7402 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0
Soft Costs | #REF! | 0 | 0 | #REF! | #REF! | #REF!
FF&E Costs | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Sub-Total | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Total Contingency | 8098599.2217 |  |  | 8098599.2217 | 8098599.2217 | 0
TOTAL | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Risk Summary
Risk Report Total |  | 0
Remaining Contingency |  | 8098599.2217
Exposure |  | 0
Estimated Final Cost (Including Risk Items) |  | #REF!

## Project Summary (hidden)
Description | Budget | Committed Costs | Costs to Date | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance
|  | Total | Total
Building Costs
Building & Fit-Out Costs | 63651264.7402 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0
Secondary Contractors | 0 | 0 | 0 | 0 | 0 | 0
Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0
Building Costs Total | 63651264.7402 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0
Soft Costs
Project Management | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Architectural Fees | 3526000 | 0 | 0 | 0 | 0 | 3526000
Design, Engineering & Misc. | #REF! | 0 | 0 | 0 | 0 | #REF!
Soft Costs Total | #REF! | 0 | 0 | #REF! | #REF! | #REF!
FF&E Costs
Seating | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Concessions | #REF! | 0 | 0 | 0 | 0 | #REF!
Phone & Data Systems | 420000 | 0 | 0 | 420000 | 420000 | 0
Office Furniture | 65000 | 0 | 0 | 0 | 0 | 65000
Signage/Graphics | 0 | 0 | 0 | 0 | 0 | 0
Administration | 93000 | 0 | 0 | 0 | 0 | 93000
Facility | 0 | 0 | 0 | 0 | 0 | 0
Operations | 0 | 0 | 0 | 0 | 0 | 0
Production | 4128500 | 0 | 0 | 0 | 0 | 4128500
FF&E Costs Total | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Sub-Total | #REF! | 0 | 0 | #REF! | #REF! | #REF!
Contingency | 8098599.2217 |  |  | 8098599.2217 | 8098599.2217 | 0
GRAND TOTAL | #REF! | 0 | 0 | #REF! | #REF! | #REF!

## Project Detail (hidden)
Code | Cost Code | Vendor | Description | Budget | Committed Costs | Change Orders | Costs to Date (Gross) | Retention | Costs to Date | Remaining Estimate | Estimated Final Cost | Budget vs EFC Variance | Notes | Remaining to Invoice | P11-21 (Fcst) | P12-21 (Fcst) | Q4-21 TOTAL (Fcst) | P01-22 (Fcst) | P02-22 (Fcst) | P03-22 (Fcst) | Q1-22 TOTAL (Fcst) | Q4-21/Q1-22 TOTAL | Remaining to Allocate
100 |  | Building Costs
101 |  | Building & Fit-Out Costs
101-1 |  | General Contractor |  | 63651264.7402 | 0 | 0 | 0 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0
101-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 101 |  | Total Building & Fit-Out Costs | 63651264.7402 | 0 | 0 | 0 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 |  | Secondary Contractors
102-1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 102 |  | Total Secondary Contractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  | Miscellaneous
103-1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 103 |  | Total Mics. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104
104-1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 104 |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL BUILDING COSTS | 63651264.7402 | 0 | 0 | 0 | 0 | 0 | 63651264.7402 | 63651264.7402 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 |  | Soft Costs
201 |  | Project Management
201-1 |  | LNE | Project Management | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
201-2 |  | TBD | Project Management (3rd Party) | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF!
201-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 201 |  | Total Project Management | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 |  | Architectural Fees
202-1 |  | TBD | Architectural Fees | 3526000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3526000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
202-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
202-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
202-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 202 |  | Total Architectural Fees | 3526000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3526000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 |  | Design, Engineering & Misc.
203-1 |  | K2 | AV/LV Design | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
203-2 |  | Trimark | Kitchen Design | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
203-3 |  | Bandit Lites | Lighting Design | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
203-4 |  | TBD | Branding | 1483680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1483680
203-5 |  | TBD | Civil Engineering | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
203-6 |  | K2 / Metro Acoustics | Acoustic Design | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
203-7 |  | TBD | Signage / Wayfinding Design | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
203-8 |  | TBD | Zoning & Permit Fees | 628297.4767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628297.4767
203-9 |  | TBD | Testing / Quality Control | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
203-10 |  | TBD | Reimbursable Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 203 |  | Total Design, Engineering & Misc. | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL SOFT COSTS | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 |  | FF&E Costs
301 |  | Seating
301-1 |  | TBD | Fixed Seating | 1043750 | 0 | 0 | 0 | 0 | 0 | 1043750 | 1043750 | 0 |  | 1043750 |  |  | 0 |  |  |  | 0 | 0 | 1043750
301-2 |  | N/A | Chairs - Gasser Bar Stools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-3 |  | N/A | Chairs - Gasser | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-4 |  | N/A | Ottoman - Boxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-5 |  | N/A | Side Tables - Boxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-6 |  | N/A | VIP - Cocktail Table | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-7 |  | N/A | VIP - Stools | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-8 |  | N/A | VIP - Coffee Tables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-9 |  | N/A | VIP - Hightop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-10 |  | N/A | VIP - Sofa | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-11 |  | N/A | VIP - Banquet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-12 |  | N/A | Artist Lounge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-13 |  | N/A | Dressing Room | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-14 |  | N/A | Rugs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-15 |  | N/A | Catering Room Chairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-16 |  | N/A | Catering Room Tables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF! | #REF!
301-17 |  | Multiple Vendors | Box & VIP Seats | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! |  |  | 0 |  |  |  | 0 | 0 | #REF!
301-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 301 |  | Total Seating | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
302 |  | Concessions
302-1 |  | TriMark | Kitchen and Bars | 1317000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1317000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
302-2 |  | TBD | Miscellaneous Equipment (POS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
302-3 |  | TBD | Portable Bars | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
302-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 302 |  | Total Concession | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 |  | Phone & Data Systems
303-1 |  | Multiple Vendors | CCTV | 220000 | 0 | 0 | 0 | 0 | 0 | 220000 | 220000 | 0 |  | 220000 |  |  | 0 |  |  |  | 0 | 0 | 220000
303-2 |  | Entisys, Insight, Multi-Link | Data /Wifi Systems | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 |  | 200000 |  |  | 0 |  |  |  | 0 | 0 | 200000
| 303 |  | Total Phone & Data | 420000 | 0 | 0 | 0 | 0 | 0 | 420000 | 420000 | 0 |  | 420000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420000
304 |  | Office Furniture
304-1 |  | Pivot / YE Co. | Office Furniture (From Furniture Tracker) | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
304-2 |  | N/A | Administration Refrigerator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF!
304-3 |  | N/A | Desks-Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF!
304-4 |  | N/A | Desk Chairs-Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF!
304-5 |  | N/A | File Cabinets-Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | #REF! |  |  |  | 0 | #REF!
| 304 |  | Total Office Furniture | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 |  | Signage/Graphics
305-1 |  | TBD | Exterior Signage / Wayfinding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-2 |  | TBD | Interior Art & Décor "Warehouse Scope" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 17000 |  | 17000 |  |  |  | 0 | 17000 | -17000
305-16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
305-17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10135 |  | 10135 |  |  |  | 0 | 10135 | -10135
| 305 |  | Total Signage/Graphics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 27135 | 0 | 27135 | 0 | 0 | 0 | 0 | 27135 | -27135
306 |  | Administration
306-1 |  | TBD | Administration | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-2 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-3 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-4 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-5 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-6 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-7 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-8 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-10 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
306-11 |  | TBD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 306 |  | Total Administration | 93000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 |  | Facility
307-1 |  | TBD | Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
307-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
307-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
307-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
307-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307-6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 307 |  | Total Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 |  | Operations
308-1 |  | TBD | Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
308-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 308 |  | Total Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 |  | Production
309-1 |  | TBD | FF&E | 193500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193500 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-2 |  | TBD | Soft Goods | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-3 |  | TBD | Audio & Video System | 1685000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-4 |  | TBD | Production Lighting | 1750000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750000 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
309-14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
| 309 |  | Total Production | 4128500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4128500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | TOTAL FF&E COSTS | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 27135 | 0 | 27135 | 0 | 0 | 0 | 0 | 27135 | #REF!
400 |  | Contingency |  | 8098599.2217
|  |  | TOTALS | #REF! | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | 27135 | 0 | 27135 | 0 | 0 | 0 | 0 | 27135 | #REF!
|  |  | Test (Must be True) | #REF!
[12 empty] | Remaining Contingency Balance |  | 8098599.2217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8098599.2217
[12 empty] | GRAND TOTALS |  | #REF! | 27135 | 0 | 27135 | 0 | 0 | 0 | 0 | 27135 | #REF!

## Committed Costs (hidden)
Committed Costs
Executed Date | Cost Code | Vendor | Description | P.O. Number | Contract Value | Notes
|  |  |  | Total Commitments | 0
TRUE

## Invoices (hidden)
Invoices
Cost Code | Vendor | Description | Invoice # | Invoice Date | Invoice Amount | GL Period | Notes | Payment Status
2022 Invoices
|  |  |  | March Invoices Total | 0
|  |  |  | INVOICES GRAND TOTAL | 0
TRUE

## Change Orders (hidden)
Date Issued | C.O. Number | Vendor | Amount | Cost Code | Description | Notes
|  | Total Change Orders | 0

## Contingency (hidden)
Date | Cost Code | Vendor | Description | Amount Applied | Remaining Balance | Notes
March 2020 Contingency | [6 empty] | Contingency
2020-03-31 | N/A | N/A | Initial Contingency Amount | 0 | 8098599.2217 |  | 8098599.2217
|  |  | March Contingency Totals | 0 | 8098599.2217
|  |  | CONTINGENCY TOTALS | 0 | 8098599.2217

## Risk Report (hidden)
Risk Report
Requestor | Item | High | Expected Settlement Value | Low | Notes
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
Project Team
|  | 0 | 0 | 0
| Current Sources (as of 01/31/2023) | Remaining Contingency | 8098599.2217
|  | Contingency Balance | 8098599.2217
|  | Exposure | 0
*Sources reflect over budget items pending resolution.