## Read Me First
165 RANDOLPH STREET
THE ANSWER, IN ONE PAGE
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
He is $24.4M high. About $21M of that is mechanical.
His 16 Sep budget totals $89,084,591. Our own bottom-up budget is $64,648,067. That is a $24,436,524 gap.
I rebuilt his workbook line by line. My reconstruction of his trade cost ties to his own cell to $0.00, so every number below is his, not mine.
Then I corrected only his own arithmetic and basis errors — using his rates, his quantities and, where he wrote them down, his own backup rows. His budget falls to $68,143,696.
Strip the off-site parking garage, which we do not carry at all, and he lands at $65,886,196 against our $64,648,067. That is 1.9% apart.
So the two estimates actually agree. The quote is not high because he thinks the building is harder to build than we do. It is high because of four mechanical faults: a contingency line that computes on the whole project instead of on what its label says, $10.3M of trade cost multiplied by a square footage this building does not have, the general-conditions function charged in two places at once, and three lump sums that disagree with their own backup.
Do NOT go back at him with the $24M. Go back with the four faults. They are checkable, they are his own cells, and they are very hard to argue with.
THE BRIDGE
| 16 Sep as sent | Corrected | Delta
Off-site - parking garage + 5% escalation | 2257500 | 2257500 | 0
Trade cost | 37945959.75 | 24804236.75 | -13141723
Trade cost to be priced (the plug) | 12000000 | 12000000 | 0
General conditions | 3141000 | 3073153.7686 | -67846.2314
Escalation on the building | 0 | 1488254.205 | 1488254.205
Overhead, profit & insurance 9% | 4777826.38 | 3588965.1467 | -1188861.2333
Contractor contingency 10% | 5786478.61 | 4346635.5665 | -1439843.0435
CONSTRUCTION COST — the work plus its markups | 63651264.74 | 49301245.4368 | -14350019.3032
Soft costs | 6784977.48 | 6784977.48 | 0
FF&E | 8292250 | 8292250 | 0
Contingency | 8098599.22 | 1507722.748 | -6590876.472
TOTAL CAPITAL | 89084591.44 | 68143695.6648 | -20940895.7752
$ per SF on the real 74,100 SF — as sent | 1202.2212 |  | His own sheet reports $655/SF, but it divides by 135,953.
$ per SF on the real 74,100 SF — corrected | 919.618
$ per SF on the real 74,100 SF — our V2 | 872.4435

## Reconciliation
165 RANDOLPH STREET
STEP 1 — RECONCILE BEFORE YOU ANALYSE
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
If this variance is not zero I am auditing my own transcription, not his budget.
Amount
Sum of the 309 line items I extracted from 'Building & Fit-out Breakdown' | 37885959.75
+ 001000 PRECONSTRUCTION (on 'Building & Fit-outBudget Detail' C46 only) | 60000
My reconstruction of his trade cost | 37945959.75
His Trade Cost, Budget Summary D25 | 37945959.75
VARIANCE | 0
309 line items extracted from his Breakdown sheet. Variance $0.00.
STEP 2 — HIS ARITHMETIC, PROVEN CELL BY CELL
Cell | His formula | Recomputed | In the file | What it means
D28 Overhead, Profit & Insurance | =SUM(D25:D27)*0.09 | 4777826.3775 | 4777826.38 | 9% is charged on trade + the $12M plug + general conditions. GC is being marked up.
D29 Contractor Contingency 10% | =SUM(D25:D28)*0.1 | 5786478.613 | 5786478.61 | 10% on a base that already contains the 9% OH&P. Markup on markup.
D67 'Soft Costs & FFE Contingency 10%' | =(D23+D31+D47+D65)*0.1 | 8098599.222 | 8098599.22 | THE LINE DOES NOT DO WHAT IT SAYS. D31 is the whole construction number, which already carries its own 10% contractor contingency. 10% of soft + FF&E, as labelled, is $1,507,723.
D30 Escalation on the building | (blank) | 0 | 0 | The $2,150,000 parking garage gets 5% escalation on row 22. The $63,651,265 building gets nothing. Same as the 4 Sep file -- still not fixed.
D71 $ PER SF | =D69/135953 | 655.2602 | 655.2602 | 135,953 SF is stacked floor area across all levels and it is not this building. On the real 74,100 SF the same total is $1,202/SF.
CASCADE — what $1 of trade cost actually costs you, as the file is built today
x 1.09 overhead, profit & insurance | 1.09
x 1.10 contractor contingency | 1.1
x 1.10 the project contingency on row 67 | 1.1
Every $1 of trade cost becomes | 1.3189
Escalation is blank, so it adds nothing to the cascade today — which is itself a fault, not a saving.

## Findings
165 RANDOLPH STREET
THE FINDINGS — direction, evidence, dollars
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
OVERSTATED = priced too high, negotiate it down. UNDERSTATED = missing or too low, fund it back in. These are opposite actions — never net them together.
No. | Direction / headline | The evidence, quoted from his file | His $ | Should be | What to do
1 | OVERSTATED The contingency line is computed on the whole project, not on what its label says | D67 reads 'Soft Costs & FFE Contingency 10%' and the formula is =(D23+D31+D47+D65)*0.1. D31 is the $63,651,265 construction number, which already contains $5,786,479 of contractor contingency on row 29. | 8098599.22 | 1507722.748 | Either rename it 'Project Contingency' and delete the contractor contingency on row 29, or keep row 29 and cut row 67 back to soft + FF&E. Not both. $578,648 of it is literally contingency on contingency.
2 | OVERSTATED $10.3M of trade cost is priced on 135,953 SF - a floor area this building does not have | 'HVAC System including BMS 132,542 SF @ $45.00 = $5,964,390' is one line with no tonnage and no load behind it. Seven more lines multiply 135,953 SF: paint @ $5, I/O lighting @ $12, general power @ $6, power to mechanical @ $3, temp light & power @ $2, fire alarm @ $2, emergency lighting @ $1, dimming @ $0.75. | 11306898 | 6596075 | Re-cut every one to 74,100 SF (footprint: HVAC volume, mechanical power) or 88,100 SF (covered floor: power, lighting, paint, alarm). Separately, HVAC on a 50 ft clear room is a LOAD, not an area - ask the mechanical engineer for tons, not $/SF.
3 | OVERSTATED The general-conditions function is charged twice, in two different places | Row 27 carries $3,141,000, and the 'General Conditions' tab backs it with a real staffing chart: Exec 10 wks, PM 90 wks @ $6,400, APM, Engineer, Accountant, three Supers @ $6,000 for 90 weeks. That part is good work. But division 013000 PROJECT REQUIREMENTS, $3,034,000, sits INSIDE the trade cost doing the same job - site office, field technology $200,000, site safety plan and inspector $400,000, portable toilets, protection, clean-up, rubbish, final clean, and 'Project Labor 1 LS $2,000,000'. | 6175000 | 3073153.7686 | Combined that is 12.36% of trade. Schimenti priced general conditions at 7.80% and 8.90% on 555 Johnson - open shop, this submarket, Eric Cohen's own GC. Pick ONE place and hold it at 8.35%. 'Project Labor $2,000,000' has no crew, no rate and no duration behind it and the staffing chart already funds three supers for 90 weeks.
4 | OVERSTATED The sidewalk bridge lump does not agree with its own backup rows | 'Install sidewalk bridge and scaffolding around building 1 LS $4,000,000', and directly beneath it, in his own hand: 1,126 LF @ $500 and 27,024 SF @ $75. Those foot to $563,000 + $2,026,800 = $2,589,800. | 4000000 | 2589800 | Ask him which number is right. Also ask why 1,126 LF - a sidewalk bridge is only required where there is a sidewalk, and the alleys and interior lot lines do not have one.
5 | OVERSTATED $2,000,000 of interior scaffolding is priced for a method we are not using | 'Interior scaffolding 1 LS $2,000,000', note '$75/SF for scaffolding' - which implies 26,667 SF of floor plate scaffolded. | 2000000 | 400000 | A roof LIFT jacks the existing roof on the lifter's own towers. You do not scaffold the floor plate to do it. Carry jacking access, rigging access and edge protection instead.
6 | OVERSTATED 2,000 coat check lockers | 'Coat Check Lockers 2000 EA @ $500 = $1,000,000', note '333LF'. | 1000000 | 262500 | 2,000 lockers serves 27% of a 7,440-capacity house at once. 750 at $350 is a generous January coat check. $500 each is a rate for a gym locker bank, not a cloakroom.
7 | DOUBLE-COUNT The lighting package is bought twice | 'I/O lighting package throughout PROVIDED BY OTHERS 135,953 SF @ $12 = $1,631,436' sits inside the trade cost. Meanwhile the FF&E schedule separately carries Architectural Lighting $1,750,000 and Production - Performance Lighting $520,000, and division 270000 carries 'LIGHTING AND CONTROLS - BY OWNER $40,000'. | 1631436 |  | His own line says 'provided by others'. If others provide it, it is not his cost. Keep the conduit, boxes and wiring in the electrical trade and delete the fixture package.
8 | METHOD The budget still demolishes the roof instead of lifting it | 'Demo Pre-cast concrete roof 74,000 SF @ $8 = $592,000', note 'Abatement by others'. Roofing then rebuilds 56,085 SF at $36/SF. | 592000 |  | A roof lift KEEPS the roof: you cut it free of the perimeter walls, jack it, extend the columns underneath and clad the new band. This is the same assumption the 4 Sep file made and it is the single biggest methodological difference between his estimate and ours.
9 | UNDERSTATED Structural steel is still $0 on a project whose own scope line reads 'Add Second Level' | Division 055100 carries nineteen lines and every one of them is zero quantity: 'F&I new Roof Trusses, girders, Columns at Music Hall area 0 TONS @ $6,000', 'Steel Framing at Mezz area 0 TONS @ $6,000', 'Steel Framing at upper balcony 0 TONS @ $6,000', 'Stage Lighting & AV support structure 0 LBS @ $8.00', railings, stairs, dunnage, lintels - all zero. |  |  | This is what the $12,000,000 'Trade Costs To Be Priced' plug is standing in for. His own $8.00/LB rate for stage lighting and AV support structure is worth keeping - our ground-supported rigging grid works out to $9.21/LB, so his rate corroborates ours.
10 | UNDERSTATED 106 line items carry a unit price and a quantity of zero | Eight whole divisions total nothing: 055100 structural steel, 062000 rough carpentry, 064000 millwork (every bar in the building - 'Lobby Bar/Back Bar 0 LF @ $2,000', VIP, Music Hall GA, Mezzanine, Balcony, Upper lounge, Lower lounge, Foundry), 078100 fireproofing, 081000 doors and frames, 084100 storefront, 088000 glazing, 092300 tile. Drywall is priced at $119,664 with nine of its ten lines at zero. |  |  | Priced bottom-up at our own rates this scope is roughly $13.4M, against his $12M plug - so the plug is about right-sized, which is worth saying. But you cannot hold 10% contingency against scope nobody has priced. That is not contingency, it is a guess with a percentage on it.
11 | UNDERSTATED Escalation on the building is blank | Row 22: the $2,150,000 parking garage gets 'Escalation (Calculated at 5%)' = $107,500. Row 30: 'Escalation (Calculated at 5%)' on the $63,651,265 building is an empty cell. |  |  | Third version of this file in a row with that cell blank. On a 20-month programme it is real money and it should be funded. We carry 6%.
12 | SCOPE Off-site parking garage, 86 spaces | D21 '=86*25000' = $2,150,000, labelled 'Parking Garage - 260/spaces'. The label says 260, the formula says 86. | 2257500 |  | Our budget does not carry this at all. Decide whether off-site parking is in the deal, then fix the label or the formula - they disagree with each other.

## Corrections Applied
165 RANDOLPH STREET
EVERY CORRECTION IS MADE TO A SOURCE CELL, THEN HIS OWN FORMULA CHAIN IS RE-RUN
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
No markup is applied by hand anywhere on this sheet. That is deliberate — it is the only way to be sure a correction is not counted twice as it passes through overhead, contingency and contingency-on-contingency.
| Correction to trade cost | Trade $ | All-in effect
A | Area basis: 8 lines re-cut off 135,953 / 132,542 SF onto 74,100 or 88,100 SF | -3616987 | -4770444.1543
B | Sprinklers: 2nd-floor mains priced on 50,000 SF against a 14,000 SF mezzanine deck (1st floor re-cut UP from 69,000 to 74,100 SF) | -519600 | -685300.44
C | Sidewalk bridge cut to his own backup rows | -1410200 | -1859912.78
D | Interior scaffolding cut to jacking and rigging access | -1600000 | -2110240
E | Coat check lockers 2,000 EA -> 750 EA @ $350 | -737500 | -972688.75
F | I/O lighting package removed from trade - FF&E already buys it | -1631436 | -2151700.9404
G | Demo of the pre-cast roof removed - a lift keeps the roof | -592000 | -780788.8
H | Division 013000 moved out of trade and into the general-conditions line | -3034000 | -4001542.6
| NET CORRECTION TO TRADE COST | -13141723 | -17332618.4647
The all-in column is indicative only — the real total on "Read Me First" comes from re-running his formulas, not from multiplying by 1.3189.
| His trade cost | 37945959.75
| Corrected trade cost | 24804236.75
| General conditions at 8.35% (Schimenti, 555 Johnson) | 3073153.7686
| Escalation at 6% on the corrected trade cost | 1488254.205

## Sept 4 to Sept 16
165 RANDOLPH STREET
WHAT MOVED IN TWELVE DAYS
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
The 4 Sep file totalled $42,555,099. The 16 Sep file totals $89,084,591. Most of that is real pricing work he genuinely did — and it is worth saying so.
CSI | Division | 4 Sep | 16 Sep | Delta | Note
015800 | SCAFFOLDING & HOARDING | 0 | 6170000 | 6170000 | ENTIRELY NEW. The single biggest addition in the file.
260000 | ELECTRIC | 558750 | 5512337 | 4953587 | Real distribution now priced. But on 135,953 SF.
220000 | PLUMBING | 1344500 | 3717250 | 2372750
100000 | SPECIALTIES | 0 | 1548500 | 1548500
013000 | PROJECT REQUIREMENTS | 1696000 | 3034000 | 1338000 | General conditions content, sitting in trade cost.
024100 | DEMOLITION | 30408 | 1287817 | 1257409
099000 | PAINTING/PLASTER | 0 | 1091765 | 1091765
044200 | STONE & CERAMICS | 0 | 764340 | 764340
096000 | CARPET/RESILIENT FLOORING | 0 | 765048 | 765048
230000 | HVAC | 5300000 | 5964390 | 664390 | One line: 132,542 SF @ $45. No tonnage, no load.
100500 | ACOUSTICAL PANELS / K13 | 0 | 581802 | 581802
283100 | FIRE ALARM | 0 | 521906 | 521906
096050 | FLOOR PREPARATION | 0 | 515298 | 515298
096400 | WOOD FLOORING | 0 | 373050 | 373050
320000 | SITEWORK | 0 | 346335 | 346335
210000 | FIRE PROTECTION | 1026000 | 1334070 | 308070
033000 | CONCRETE | 0 | 177450 | 177450
083000 | SPECIAL DOORS | 6000 | 76000 | 70000
142000 | ELEVATOR | 600000 | 480000 | -120000
075000 | ROOFING | 5736276 | 2557428 | -3178848 | DOWN $3.2M — he moved off full roof replacement. Good.
055100 | STRUCTURAL STEEL & MISC METALS | 0 | 0 | 0 | STILL ZERO. Nineteen lines, every quantity blank.
064000 | MILLWORK | 0 | 0 | 0 | STILL ZERO. Every bar in the building.
081000 | DOORS, FRAMES & HARDWARE | 0 | 0 | 0 | STILL ZERO.
084100 | STOREFRONT | 0 | 0 | 0 | STILL ZERO.
088000 | GLAZING | 0 | 0 | 0 | STILL ZERO.
078100 | FIREPROOFING | 0 | 0 | 0 | STILL ZERO.
092300 | TILE | 0 | 0 | 0 | STILL ZERO.
062000 | ROUGH CARPENTRY | 0 | 0 | 0 | STILL ZERO.

## Zero Quantity Register
165 RANDOLPH STREET
SCOPE THAT CARRIES A UNIT PRICE AND A QUANTITY OF ZERO
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
This is what the $12,000,000 "Trade Costs To Be Priced" plug stands in for. Each line has his rate on it already — it only needs a quantity.
CSI | Description | Qty | Unit | His rate
024100 | Allow for Floor trenching for MEPS | 0 | LS | 50000
024100 | Misc Façade Demo Along Johnson Ave (Doors, Roll-ups, Windows, etc.) | 0 | LS | 20000
033000 | Excavation related to New Columns at Music hall | 0 | SF | 6.5
033000 | CMU wall footing excavation allow 2' deep for new Load bearing wall at Music hall- East wall | 0 | LF | 150
033000 | Concrete at New footings | 0 | EA | 7500
033000 | Concrete 4'6" H on Styrofoam | 0 | SF | 50
033000 | Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50
033000 | Concrete at CMU footing | 0 | LF | 100
033000 | Patch slab due to New footing | 0 | SF | 30
033000 | Patch conc. At Trenching for MEPS | 0 | SF | 30
033000 | New slab Pour-back at Excavated Areas | 0 | SF | 30
033000 | Concrete on Deck for Mezz of Music Hall with Platforms | 0 | SF | 25
033000 | Concrete In-fill on New Pan Stairs | 0 | EA | 4000
033000 | Grouting at Steel Trusses & Column Base Plates | 0 | LS | 15000
033000 | Polished concrete | 0 | SF | 8
033000 | Concrete pads | 0 | LS | 10000
033000 | Patch sidewalk | 0 | LS | 35000
033000 | Misc. Equipment Pads | 0 | LS | 25000
033000 | Concrete at Stage Platform 4'6" H on Styrofoam | 0 | SF | 50
042000 | F&I CMU wall vestibule stair tower 1 1st FL | 0 | SF | 35
042000 | F&I Brick façade at music hall bump up | 0 | SF | 35
042000 | CMU and Brick infills at old windows and door opening | 0 | SF | 70
042000 | Repair/ cleaning and minor repointing of existing brick facade | 0 | SF | 10
042000 | Misc. Patching allow at penetrations | 0 | LS | 5000
055100 | Disconnect roof framing for Demo & Shore at select areas | 0 | SF | 5
055100 | F&I new Roof Trusses, girders, Columns at Music Hall area | 0 | TONS | 6000
055100 | F&I Roof deck | 0 | SF | 4
055100 | Steel Framing at Mezz area - Including Elevated Standing & Box Seating | 0 | TONS | 6000
055100 | Steel Framing at upper balcony - incluing balcony seating | 0 | TONS | 6000
055100 | Stage Lighting & AV support structure | 0 | LBS | 8
055100 | Small stair to access Stage | 0 | EA | 13000
055100 | Roof Dunnage for HVAC Equipment's | 0 | LOC | 20000
055100 | Roof Penetrations framing for Toilet exhaust & Kitchen exhaust | 0 | LS | 25000
055100 | Stairs | 0 | FL | 30000
055100 | Allow for Unistrut at select area of stage | 0 | SF | 35
055100 | Railing at Roof Deck | 0 | LF | 500
055100 | Railing at Theatre | 0 | LF | 275
055100 | Misc. Lintels | 0 | LS | 10000
055100 | Allow for access Ladders at Stage Overhead lighting grid area | 0 | LS | 15000
062000 | Safety Protection at Roof cut out | 0 | LS | 35000
062000 | Safety Protection at Footings trenches | 0 | LS | 30000
062000 | Entry Barricade | 0 | SF | 40
062000 | Safety at New Mezz Build outs | 0 | SF | 2
062000 | Rough Carpentry work at Stage area | 0 | SF | 5
064000 | Lobby Bar/Back Bar - Complete | 0 | LF | 2000
064000 | VIP Bar/Back Bar - Complete | 0 | LF | 2000
064000 | Music Hall GA Bar/Back Bars - Complete | 0 | LF | 2000
064000 | Mezzanine Bar/Back Bars - Complete | 0 | LF | 2000
064000 | Balcony bar/back bar- complete | 0 | LF | 2000
064000 | Upper lounge bar/back bar- complete | 0 | LF | 2000
064000 | Lower lounge bar/back bar- complete | 0 | LF | 2000
064000 | Foundry bar/back bar- complete | 0 | LF | 2000
064000 | Decorative Features Above Each Back Bar | 0 | EA | 10000
064000 | Green room Bathrooms & Counter tops | 0 | LF | 350
064000 | Public Bathroom Counter top | 0 | LF | 400
064000 | Millwork at Merchandise | 0 | LS | 12000
064000 | Pantry at Office Area | 0 | LF | 850
064000 | Millwork shelf & Pole at Coat closet area | 0 | LF | 150
064000 | Install Furniture | 0 | LS | 25000
064000 | Additional millwork in public areas | 0 | LS | 30000
064000 | Decorative Millwork at Proscenium | 0 | EA | 10000
064000 | Millwork at BOX Office | 0 | LF | 500
075000 | 3rd Floor Terrace concrete pavers on pedestals VIP | 0 | SF | 31
078100 | Allow for fireproofing at New steel at Roof | 0 | SF | 5
078100 | Allow for fireproofing at New steel at Mezzanine | 0 | SF | 5
078100 | Add fireproofing to existing roof steel | 0 | SF | 5
081000 | Single Hollow Metal Doors - Non-Acoustical | 0 | EA | 2200
081000 | Double Hollow Metal Doors - Non-Acoustical | 0 | EA | 3200
081000 | Acoustical doors at Music Hall | 0 | EA | 10000
081000 | Acoustical double doors at Music Hall | 0 | PAIR | 20000
084100 | F&I New Storefront with Doors | 0 | SF | 250
084100 | F&I New Storefront with doors to roof deck | 0 | SF | 150
084100 | Storefront double door to roof deck | 0 | PAIRS | 4500
084100 | Interior Storefront at VIP Lounge | 0 | SF | 75
084100 | Interior Storefront at foundry | 0 | SF | 75
084100 | Interior double door at VIP Lounge | 0 | PAIR | 4500
088000 | Mirror at Bathrooms- Public | 0 | SF | 50
088000 | Mirror at Green room | 0 | SF | 50
088000 | Mirror behind bars | 0 | LOT | 35000
088000 | Ballistic Box office window | 0 | LOT | 10000
092000 | Perimeter wall furring/sheathing at new Music Hall bump up | 0 | SF | 20
092000 | Interior Sound/Fire rated walls at music hall, stair ways and elevator shafts | 0 | SF | 20
092000 | Interior Non Sound walls | 0 | SF | 12
092000 | Drywall ceilings | 0 | SF | 12
092000 | Acoustical Ceilngs | 0 | SF | 10
092000 | Install Doors/Frames/Hardware | 0 | EA | 650
092000 | Blocking | 0 | LS | 30000
092000 | FRP Kitchen walls | 0 | SF | 15
092000 | Diamond wall plates at Loading dock area for wall protection | 0 | SF | 15
092000 | Install Items Furnished By Others | 0 | LS | 25000
092300 | Tile at Restroom/Shower Floors | 0 | SF | 30
092300 | Tile at Restroom Walls | 0 | SF | 30
092300 | Faux brick at Lobby | 0 | SF | 35
092300 | Tile at Bar Floors | 0 | SF | 20
092300 | Tile & Base at Kitchen | 0 | SF | 20
096000 | Carpete tile at office and production | 0 | SF | 5.5
096000 | LVT Flooring at Green room areas and Dresssing rooms | 0 | SF | 10
096000 | VCT in coat room/box office | 0 | SF | 7
096000 | F&I Vinyl Base | 0 | LF | 2.75
096000 | Minor Prep floor | 0 | SF | 1.5
096000 | Entry Mats | 0 | SF | 100
096000 | Stair Treads | 0 | LS | 17500
096050 | Music Hall sealed concrete at new concrete areas | 0 | SF | 5
099000 | Plaster | 0 | SF | 25
260000 | Combine Existing Services | 0 | LS | 200000
270000 | Door intrusion entry/exit security | 0 | LOC | 5000
106 lines

## Questions for Thomas
165 RANDOLPH STREET
THE ELEVEN QUESTIONS
Audit of the Master Development Budget dated 16 Sep 2026 · method: construction-budget-audit skill · CONFIDENTIAL
Every one of these is answerable from his own workbook. None of them accuses him of padding — and he has not padded. He has made four mechanical mistakes and priced a programme nobody has settled yet.
Ask | Why
Which number is the sidewalk bridge? | $4,000,000 as a lump, or the 1,126 LF @ $500 + 27,024 SF @ $75 = $2,589,800 written directly underneath it? And how many linear feet of actual public sidewalk does this building have?
What is 'Project Labor, 1 LS, $2,000,000'? | Give me the crew, the rate and the weeks. The General Conditions tab already funds three superintendents and a general super for 90 weeks.
Why is the whole building's escalation blank when the parking garage gets 5%? | Row 30 has been empty in all three versions of this file.
Is 'Soft Costs & FFE Contingency 10%' meant to be a project contingency? | The formula is =(D23+D31+D47+D65)*0.1 - that is 10% of everything, on top of the 10% contractor contingency already inside D31. As labelled it should be $1,507,723.
Where does 135,953 SF come from? | It is not this building. 165 Randolph is 74,100 SF under roof with a 14,000 SF mezzanine inside that envelope. 555 Johnson is about 135,000 SF - I think this is a template carryover. Today it multiplies $10.3M of real trade cost.
Was HVAC priced on a load or on an area? | $45.00 x 132,542 SF is one line with no tonnage. A 50 ft clear room with 7,440 people is a volume and an occupancy load, not a floor area. If it was priced on area, it needs to be re-priced by the mechanical engineer.
Does the interior scaffolding assume the roof comes off? | Demo carries 74,000 SF of pre-cast roof demolition at $8. We are LIFTING the roof, not replacing it. If that is the assumption behind the $2,000,000 of interior scaffolding too, both lines need to be re-thought together.
Is the I/O lighting package his or ours? | The line says 'provided by others' and sits in his trade cost at $1,631,436, while FF&E separately carries $1,750,000 of architectural lighting.
When do the 106 zero-quantity lines get priced? | Structural steel, every bar, all doors, storefront, glazing, fireproofing, tile and most of the drywall. The $12,000,000 plug is roughly the right size - we price that scope at about $13.4M - but it is a plug, and contingency should not be charged on top of it.
Parking garage: 86 spaces or 260? | The label says 260 spaces, the formula says =86*25000. And is off-site parking in this deal at all? We do not carry it.
Second floor, third floor, roof decks, balcony, upper and lower lounge, foundry, restaurant. | This is a PROGRAMME question for us and Wake, not an estimating error - he priced what the test fit showed him. But it drives the sprinkler quantities, the fixture counts and the 135,953 SF, so we need to settle it before the next version.