## Building to Building
165 RANDOLPH STREET
JUST THE BRICKS, STEEL, PIPE AND WIRE
Building to building · every markup, soft cost and FF&E stripped from BOTH sides · 16 Sep 2026 estimate vs our V2 · CONFIDENTIAL
He is $10,169,517 over us on physical work — +26.6%
No general conditions. No overhead, profit or insurance. No contractor contingency, no project contingency, no escalation. No soft costs, no FF&E, no off-site parking garage. Both budgets, same treatment.
Our column ties to the $38,166,123 trade cost our own V2 workbook publishes, to the dollar. His column ties to his own $37,945,960 trade cost less the general-conditions content and preconstruction that come off both sides, plus the $1,483,680 of abatement he carries as a soft cost and we carry as a trade.
Work package | OURS | HIS | Delta | His CSI | What is going on
Enabling, sidewalk shed & scaffolding | 1438262.5 | 6170000 | 4731737.5 | 015800 | His single biggest line anywhere. $4,000,000 sidewalk bridge as a lump against his own backup rows of $2,589,800, plus $2,000,000 of interior scaffolding. We carry a shed at $210/LF erected plus 24 months of rental, priced off the perimeter.
Hazmat & abatement | 1000750 | 1483680 | 482930 | soft costs | HE CARRIES THIS AS A SOFT COST, NOT A TRADE. Pulled across here so the comparison is physical-to-physical. Ours presumes ACM on the 1948 precast roof - nobody has sampled it. The ACP-5 survey is worth $555,750 of that line.
Demolition | 601978 | 1287817 | 685839 | 024100 | $592,000 of his is 74,000 SF of pre-cast ROOF demolition at $8/SF. A roof lift keeps the roof. Strip that and he is at $695,817 against our $601,978 - close.
Sitework | 90000 | 346335 | 256335 | 320000 | He prices 8,295 SF of sidewalk repair, trees, fencing and a 2,380 SF fire-escape egress route. We under-carry this.
Concrete & foundations | 1476450 | 177450 | -1299000 | 033000 | EVERY LINE in his 033000 is zero quantity except three. No footings for new columns, no stage platform slab, no mezzanine deck pour. Ours funds the new load path for the lift plus ground-supported stage and mezzanine footings.
Roof: lift contract vs roofing works | 5274243 | 2557428 | -2716815 | 075000 | THESE ARE NOT THE SAME SCOPE. Ours is a $3.5M lifter's contract plus the surrounding work - cut the roof free, jack it, extend the columns, clad the new band. His is 56,085 SF of new membrane at $36/SF over a roof he has already demolished. This is the single biggest methodological difference in the two files.
Structural steel, stage, mezzanine & rigging | 5827740.5 | 0 | -5827740.5 | 055100 | ZERO. Nineteen lines, every quantity blank, on a project whose own scope line reads 'Add Second Level'. His own unpriced rate for stage lighting and AV support structure is $8.00/LB; our rigging grid works out to $9.21/LB, so his rate corroborates ours within 15%.
Fireproofing | 180000 | 0 | -180000 | 078100 | ZERO. Three lines at $5/SF, all blank quantity - new roof steel, new mezzanine steel, and fireproofing added to the existing roof steel.
Envelope - masonry, doors, storefront, glazing | 2182821 | 606010 | -1576811 | 042000/081000/083000/084100/088000 | Masonry is close ($530,010 his vs our $739,626). But doors, storefront and glazing are all zero - including every acoustical door into the music hall at $10,000 each. We also carry 32,670 SF of new wall band created by the 30 ft lift, which his file has nowhere to put.
Interior construction - drywall & carpentry | 1147776 | 119664 | -1028112 | 092000/061000 | Nine of his ten drywall lines are zero quantity. The $119,664 he does carry is a fraction of a room that needs sound-rated separation between a 7,440-capacity hall and everything else.
Finishes - flooring, stone, tile, paint | 866500 | 3509501 | 2643001 | 044200/092300/096000/096050/096400/099000 | HE IS 4x US HERE AND HE MAY WELL BE RIGHT. $764,340 of stone, $765,048 of resilient, $515,298 of floor prep, $373,050 of wood, $1,091,765 of paint. Some of it is the 135,953 SF error (paint is 135,953 x $5), but most of it is finish level - he is pricing a restaurant and VIP lounges we have not designed. This is a PROGRAMME conversation, not an error.
Acoustics | 1864000 | 581802 | -1282198 | 100500 | $581,802 of K13 against our $1,864,000. Ours is not decoration - it is the licence to operate next to residential. Under-carried by him.
Specialties, millwork & signage | 966250 | 1648500 | 682250 | 100000/064000/101400/120000 | His $1,548,500 of specialties contains $1,000,000 of coat check lockers - 2,000 at $500 each. Meanwhile ALL millwork is zero: every bar in the building at $2,000/LF with no linear feet against it, eight bars, plus back bars, box office and counters.
Conveying / elevators | 300000 | 480000 | 180000 | 142000 | 4 lobby stops + 2 stage stops at $75,000 plus a hydraulic lift. His is the better-built number; ours is a $300,000 allowance.
Fire protection - sprinklers | 963000 | 1334070 | 371070 | 210000 | He prices 119,000 SF of sprinkler coverage (69,000 + 50,000). Coverage is 88,100 SF - 74,100 ground plus the 14,000 SF mezzanine deck. The 2nd-floor line alone is $540,000 over.
Plumbing | 1757502 | 3717250 | 1959748 | 220000 | HE IS 2.1x US. 178 water closets, 154 lavatories, 51 urinals at $4,000 each, nine bars roughed, a $125,000 restaurant grease trap. His fixture count may be right for 7,440 - ours may be light. GET THE ARCHITECT'S CODE FIXTURE CALCULATION and settle it with arithmetic.
HVAC | 5950650 | 5964390 | 13740 | 230000 | Almost identical totals - and that is a coincidence, not agreement. His is ONE LINE: 132,542 SF x $45.00, no tonnage, no load, on an area this building does not have. Ours is built from the occupancy load. Same answer, one of us by accident.
Electrical, power & low voltage | 5120150 | 5779836.75 | 659686.75 | 260000/270000/265000 | Within 13% of each other, and his two 4,000A switchboards match our service sizing. But $3,092,931 of his is priced on 135,953 SF, and $1,631,436 of it is an 'I/O lighting package PROVIDED BY OTHERS' that FF&E buys again.
Fire alarm & detection | 405250 | 521906 | 116656 | 283100 | Close. His includes a $250,000 VESDA system for the music hall that we do not carry and probably should.
Kitchen & food service - construction side | 752800 | 50000 | -702800 | 114000 | Both of us carry almost nothing here, for different reasons. His kitchen money is in FF&E ($1,317,000) and in plumbing roughing. Ours is a three-level toggle with L0 and L1 on — a warming kitchen, no grease hood. The Type I versus Type II hood decision still drives this and nobody has made it.
PHYSICAL WORK — priced lines only | 38166123 | 36335639.75 | -1830483.25 |  | His priced lines come to LESS than our entire budget.
+ his "Trade Costs To Be Priced" | 0 | 12000000 | 12000000 |  | The plug standing in for everything above that he left at zero quantity.
BUILDING TO BUILDING | 38166123 | 48335639.75 | 10169516.75
$ per SF on 74,100 SF — ours | 515.0624
$ per SF on 74,100 SF — his | 652.3028

## Where the Gap Sits
165 RANDOLPH STREET
THE GAP IS NOT ONE THING — IT IS THREE, AND THEY MEAN DIFFERENT THINGS
Building to building · every markup, soft cost and FF&E stripped from BOTH sides · 16 Sep 2026 estimate vs our V2 · CONFIDENTIAL
Never net these together. One says negotiate the price down, one says fund scope back in, and one is a decision we owe him. Three different actions.
| Amount | Note
Scope we BOTH priced, where he is higher | 12782993.25 | This is the negotiation. Three packages are 73% of it: scaffolding $4.73M, finishes $2.64M, plumbing $1.96M.
Scope he left at zero or barely touched | -10614463.5 | Structural steel, fireproofing, concrete and foundations, doors and glazing, drywall, millwork, kitchen. This is what the plug is FOR.
His 'Trade Costs To Be Priced' plug | 12000000 | $12,000,000 against $10,614,464 of scope. RIGHT-SIZED, with about $1,385,536 of headroom. Do not negotiate this line - ask him to price it.
Different calls, properly priced on both sides | -3999013 | The roof lift versus roof replacement, and acoustic spec. These are DECISIONS, not missing lines, and the plug should not have to cover them.
BUILDING-TO-BUILDING GAP | 10169516.75
THE POINT
His $12,000,000 plug covers scope we price at $10,614,464. It is right-sized — do not negotiate that line, ask him to price it.
The real argument is the $12,782,993 he is over on scope we BOTH priced. Scaffolding alone is $4,731,738 of it.
And $3,999,013 of the difference is two decisions nobody has made yet: lift the roof or replace it, and how much acoustic treatment the licence actually needs. Those get settled with Wake and Rooflifters, not with Thomas.

## What Came Off
165 RANDOLPH STREET
EVERYTHING STRIPPED OUT, AND WHERE IT LIVES INSTEAD
Building to building · every markup, soft cost and FF&E stripped from BOTH sides · 16 Sep 2026 estimate vs our V2 · CONFIDENTIAL
Stripped from his budget | His cell | Amount | How we carry it
General conditions / project requirements | Div 013000 $3,034,000 + the $3,141,000 staffing line below the line | 6175000 | carried as a % below the line
Preconstruction | Div 001000 | 60000 | we carry it in soft costs
Overhead, profit & insurance 9% | Budget Summary D28 | 4777826.38 | below the line
Contractor contingency 10% | D29 | 5786478.61 | below the line
Project contingency | D67 | 8098599.22 | single $5,000,000 owner-held pot
Escalation | D30 - blank in his file | 0 | 6% below the line
Soft costs | D47 | 6784977.48 | $5,398,000, separately
FF&E | D65 | 8292250 | $5,570,260, separately
Off-site parking garage | D21+D22 | 2257500 | NOT CARRIED AT ALL
TOTAL STRIPPED FROM HIS $89,084,591 |  | 42232631.69
Added back to his physical column
Abatement, which he carries as a soft cost and we carry as a trade |  | 1483680
$89,084,591 − $42,232,632 stripped + $1,483,680 of abatement = $48,335,640 of physical work. His $12,000,000 plug was never stripped — it is inside that number already.

## The Issues
165 RANDOLPH STREET
THE ISSUES, BUILDING TO BUILDING
Building to building · every markup, soft cost and FF&E stripped from BOTH sides · 16 Sep 2026 estimate vs our V2 · CONFIDENTIAL
HIS = his number needs to move. OURS = ours does. BOTH = a decision neither of us can make alone. NEITHER = leave it exactly where it is.
Whose | Issue | The evidence | What to do
HIS | Scaffolding is the single biggest package gap in the file | $6,170,000 against our $1,438,262. A $4,000,000 sidewalk bridge lump with his own backup rows footing to $2,589,800 directly beneath it, plus $2,000,000 of interior scaffolding. | Ask which of his two numbers is right. Then ask how many linear feet of actual public sidewalk this building has — a shed is only required where there is one, and the alleys and interior lot lines do not have one.
HIS | Structural steel is $0 on a project scoped 'Add Second Level' | All nineteen lines of division 055100 are zero quantity: roof trusses and columns at $6,000/TON, mezzanine framing at $6,000/TON, balcony framing, stage lighting and AV support structure at $8.00/LB, railings, stairs, dunnage, lintels. We carry $5,827,740 of it. | This is the biggest single thing his $12M plug has to absorb. His own $8.00/LB rate is good — our rigging grid works out to $9.21/LB, so he corroborates us within 15%.
NEITHER | The $12,000,000 plug is right-sized — leave it alone | The scope he left at zero or barely touched is scope we price at $10,614,464. His plug is $12,000,000, so it covers it with about $1,385,536 of headroom. | The instinct is to attack the biggest round number in the file. Don't. It is the one line in his budget that is about right. Ask him to PRICE it, not cut it — and when he does, the number that changes is the trade cost, not the plug.
BOTH | We are building two different roofs | He demolishes 74,000 SF of pre-cast roof at $8/SF and lays 56,085 SF of new membrane at $36/SF. We lift the existing roof on the lifter's towers, extend the columns and clad a new 30 ft band — $3.5M contract plus surrounding work. | SETTLE THIS FIRST. It moves concrete, steel, scaffolding, demolition and roofing all at once, and nothing else in either budget can be reconciled until it is decided.
HIS | Finishes are 4x ours — and he is probably right | $3,509,501 against our $866,500: stone $764,340, resilient $765,048, floor prep $515,298, wood $373,050, paint $1,091,765. | PROGRAMME, NOT ERROR. He is pricing a restaurant, VIP lounges and a foundry off the test fit. Some of it is the 135,953 SF mistake (paint is 135,953 x $5), but most is finish level. That conversation is with Wake and with us, not with him.
HIS | Plumbing is 2.1x ours and one of us has the fixture count wrong | $3,717,250 against our $1,757,502. 178 water closets, 154 lavatories and 51 urinals at $4,000 each, nine bars roughed, a $125,000 restaurant grease trap. | GET THE ARCHITECT'S CODE FIXTURE CALCULATION. This is settleable with arithmetic in an afternoon and it is worth $2M. Our number may be the light one.
OURS | Acoustics is under-carried by him | $581,802 of K13 against our $1,864,000. | Ours is not decoration — it is the licence to operate next to residential. Do not let this one get value-engineered because his number is lower.
HIS | Concrete and foundations are effectively $0 | $177,450 against our $1,476,450. Every footing line, the stage platform slab, the mezzanine deck pour and the column base grouting are all zero quantity. | Follows directly from the steel being zero. Same plug.
HIS | Every bar in the building is priced at zero | Division 064000: lobby, VIP, music hall GA, mezzanine, balcony, upper lounge, lower lounge and foundry bars, all at $2,000/LF with no linear feet against them. But his PLUMBING carries nine bars roughed at $30,000 each. | His own plumbing sheet knows there are nine bars. Give him the linear feet off the test fit and the millwork prices itself.
HIS | $1,000,000 of coat check lockers sits inside specialties | 2,000 EA at $500, note '333LF'. That serves 27% of a 7,440-capacity house at once, at a rate for a gym locker bank. | 750 at $350 is a generous January coat check. Worth $737,500.
BOTH | HVAC matching is a coincidence, not agreement | $5,964,390 his, $5,950,650 ours. His is ONE LINE — 132,542 SF x $45.00, no tonnage, no load, on an area this building does not have. Ours is built off the occupancy load. | Two wrong methods landing in the same place. Get tons from the mechanical engineer before either number is trusted.
HIS | Abatement is in his soft costs, not his trade cost | $1,483,680 under soft costs. We carry $1,000,750 as a trade. | Not an error, just a different home — but it matters, because abatement is physical work and it belongs in the comparison. Both numbers are guesses until the ACP-5 survey is done.
OURS | Elevators — his number is better built than ours | 4 lobby stops + 2 stage stops at $75,000 plus a hydraulic lift = $480,000. Ours is a $300,000 allowance. | Take his. Ours is a placeholder and his has stops behind it.
OURS | VESDA — he is right and we do not carry it | $250,000 for aspirating smoke detection in the music hall. | A 50 ft clear volume with haze and pyro needs it. Add it to ours.
OURS | Sitework — we under-carry | $346,335 against our $90,000: 8,295 SF of sidewalk repair, trees, fencing and a 2,380 SF fire-escape egress route at $75/SF. | His is the real number. Ours is an allowance.