## Apples to Apples
165 RANDOLPH STREET
OUR BUDGET AND HIS, LINE FOR LINE
Our budget and his, complete, in one identical structure · nothing stripped from either side · 16 Sep 2026 · CONFIDENTIAL
Ours $64,648,067. His $89,084,591. He is $24,436,525 higher.
Every row means the same thing in both columns, and each column foots to the total that budget actually publishes. Two normalisations, and only two, so the rows line up — neither changes either total:
1. His division 013000 PROJECT REQUIREMENTS ($3,034,000) and 001000 PRECONSTRUCTION ($60,000) move out of his trade cost onto the running-the-site rows, where our equivalent already sits.
2. His abatement ($1,483,680) moves out of his soft costs into the hazmat work package, where ours already sits.
| OURS | HIS | Delta | What is going on
Enabling, sidewalk shed & scaffolding | 1438262.5 | 6170000 | 4731737.5 | His single biggest line anywhere. $4,000,000 sidewalk bridge as a lump against his own backup rows of $2,589,800, plus $2,000,000 of interior scaffolding. We carry a shed at $210/LF erected plus 24 months of rental, priced off the perimeter.
Hazmat & abatement | 1000750 | 1483680 | 482930 | HE CARRIES THIS AS A SOFT COST, NOT A TRADE. Pulled across here so the comparison is physical-to-physical. Ours presumes ACM on the 1948 precast roof - nobody has sampled it. The ACP-5 survey is worth $555,750 of that line.
Demolition | 601978 | 1287817 | 685839 | $592,000 of his is 74,000 SF of pre-cast ROOF demolition at $8/SF. A roof lift keeps the roof. Strip that and he is at $695,817 against our $601,978 - close.
Sitework | 90000 | 346335 | 256335 | He prices 8,295 SF of sidewalk repair, trees, fencing and a 2,380 SF fire-escape egress route. We under-carry this.
Concrete & foundations | 1476450 | 177450 | -1299000 | EVERY LINE in his 033000 is zero quantity except three. No footings for new columns, no stage platform slab, no mezzanine deck pour. Ours funds the new load path for the lift plus ground-supported stage and mezzanine footings.
Roof: lift contract vs roofing works | 5274243 | 2557428 | -2716815 | THESE ARE NOT THE SAME SCOPE. Ours is a $3.5M lifter's contract plus the surrounding work - cut the roof free, jack it, extend the columns, clad the new band. His is 56,085 SF of new membrane at $36/SF over a roof he has already demolished. This is the single biggest methodological difference in the two files.
Structural steel, stage, mezzanine & rigging | 5827740.5 | 0 | -5827740.5 | ZERO. Nineteen lines, every quantity blank, on a project whose own scope line reads 'Add Second Level'. His own unpriced rate for stage lighting and AV support structure is $8.00/LB; our rigging grid works out to $9.21/LB, so his rate corroborates ours within 15%.
Fireproofing | 180000 | 0 | -180000 | ZERO. Three lines at $5/SF, all blank quantity - new roof steel, new mezzanine steel, and fireproofing added to the existing roof steel.
Envelope - masonry, doors, storefront, glazing | 2182821 | 606010 | -1576811 | Masonry is close ($530,010 his vs our $739,626). But doors, storefront and glazing are all zero - including every acoustical door into the music hall at $10,000 each. We also carry 32,670 SF of new wall band created by the 30 ft lift, which his file has nowhere to put.
Interior construction - drywall & carpentry | 1147776 | 119664 | -1028112 | Nine of his ten drywall lines are zero quantity. The $119,664 he does carry is a fraction of a room that needs sound-rated separation between a 7,440-capacity hall and everything else.
Finishes - flooring, stone, tile, paint | 866500 | 3509501 | 2643001 | HE IS 4x US HERE AND HE MAY WELL BE RIGHT. $764,340 of stone, $765,048 of resilient, $515,298 of floor prep, $373,050 of wood, $1,091,765 of paint. Some of it is the 135,953 SF error (paint is 135,953 x $5), but most of it is finish level - he is pricing a restaurant and VIP lounges we have not designed. This is a PROGRAMME conversation, not an error.
Acoustics | 1864000 | 581802 | -1282198 | $581,802 of K13 against our $1,864,000. Ours is not decoration - it is the licence to operate next to residential. Under-carried by him.
Specialties, millwork & signage | 966250 | 1648500 | 682250 | His $1,548,500 of specialties contains $1,000,000 of coat check lockers - 2,000 at $500 each. Meanwhile ALL millwork is zero: every bar in the building at $2,000/LF with no linear feet against it, eight bars, plus back bars, box office and counters.
Conveying / elevators | 300000 | 480000 | 180000 | 4 lobby stops + 2 stage stops at $75,000 plus a hydraulic lift. His is the better-built number; ours is a $300,000 allowance.
Fire protection - sprinklers | 963000 | 1334070 | 371070 | He prices 119,000 SF of sprinkler coverage (69,000 + 50,000). Coverage is 88,100 SF - 74,100 ground plus the 14,000 SF mezzanine deck. The 2nd-floor line alone is $540,000 over.
Plumbing | 1757502 | 3717250 | 1959748 | HE IS 2.1x US. 178 water closets, 154 lavatories, 51 urinals at $4,000 each, nine bars roughed, a $125,000 restaurant grease trap. His fixture count may be right for 7,440 - ours may be light. GET THE ARCHITECT'S CODE FIXTURE CALCULATION and settle it with arithmetic.
HVAC | 5950650 | 5964390 | 13740 | Almost identical totals - and that is a coincidence, not agreement. His is ONE LINE: 132,542 SF x $45.00, no tonnage, no load, on an area this building does not have. Ours is built from the occupancy load. Same answer, one of us by accident.
Electrical, power & low voltage | 5120150 | 5779836.75 | 659686.75 | Within 13% of each other, and his two 4,000A switchboards match our service sizing. But $3,092,931 of his is priced on 135,953 SF, and $1,631,436 of it is an 'I/O lighting package PROVIDED BY OTHERS' that FF&E buys again.
Fire alarm & detection | 405250 | 521906 | 116656 | Close. His includes a $250,000 VESDA system for the music hall that we do not carry and probably should.
Kitchen & food service - construction side | 752800 | 50000 | -702800 | Both of us carry almost nothing here, for different reasons. His kitchen money is in FF&E ($1,317,000) and in plumbing roughing. Ours is a three-level toggle with L0 and L1 on — a warming kitchen, no grease hood. The Type I versus Type II hood decision still drives this and nobody has made it.
TRADE COST — the work itself | 38166123 | 36335639.75 | -1830483.25 | His priced lines come to LESS than our entire trade cost — because eight of his divisions are still at zero quantity.
Trade costs to be priced (his plug) | 0 | 12000000 | 12000000 | Standing in for structural steel, fireproofing, concrete, doors, glazing, drywall, all millwork and the kitchen. We price that scope at $10,614,464, so the plug is right-sized.
ALL THE WORK | 38166123 | 48335639.75 | 10169516.75
General conditions — running the site | 3244120.455 | 6175000 | 2930879.545 | Ours is 8.5% of trade. His is a $3,141,000 staffing chart (90 weeks, PM, APM, engineer, three supers) PLUS $3,034,000 of division 013000 sitting inside his trade cost doing the same job. Combined 12.36% against Schimenti's 7.80% and 8.90% at 555 Johnson.
Preconstruction | 0 | 60000 | 60000 | He prices it as a trade. We carry it inside design fees.
Escalation | 3816612.3 | 0 | -3816612.3 | BLANK IN HIS FILE for the third version running — while the $2,150,000 parking garage gets 5% on the row above. On a 20-month programme this is real and it should be funded.
Overhead, profit & insurance | 3434951.07 | 4777826.38 | 1342875.31 | Same 9% rate. His is bigger because his base is bigger — he charges it on trade plus the $12M plug plus general conditions.
Contractor contingency | 0 | 5786478.61 | 5786478.61 | 10% on a base that already contains the 9% overhead and profit. We hold ONE contingency, below, and the owner holds it.
CONSTRUCTION COST | 48661806.825 | 65134944.74 | 16473137.915
Contingency | 5000000 | 8098599.22 | 3098599.22 | His line is labelled 'Soft Costs & FFE Contingency 10%' but the formula is =(D23+D31+D47+D65)*0.1 — 10% of the WHOLE PROJECT, on top of the contractor contingency already inside it. As labelled it would be $1,507,723.
Soft costs | 5398000 | 5301297.48 | -96702.52 | Within $97,000 of each other once his abatement is moved to the work above. The closest agreement anywhere in either budget.
FF&E | 5588260 | 8292250 | 2703990 | His carries $1,750,000 of architectural lighting AND a $1,631,436 'I/O lighting package provided by others' inside his electrical trade. One of those is bought twice.
Off-site parking garage | 0 | 2257500 | 2257500 | D21 is '=86*25000' under a label reading '260/spaces'. We do not carry off-site parking at all. The label and the formula disagree with each other.
TOTAL DEVELOPMENT COST | 64648066.825 | 89084591.44 | 24436524.615
THE SAME TWO BUDGETS, FIVE WAYS
| OURS | HIS | Delta
Total development cost | 64648066.825 | 89084591.44 | 24436524.615
$ per SF on 74,100 SF | 872.4435 | 1202.2212 | 329.7777
$ per capacity unit (7,440) | 8689.2563 | 11973.7354 | 3284.4791
Markups + contingency as % of the work | 40.6% | 51.51% | 10.91%
Contingency as % of construction cost | 10.27% | 12.72% | 2.448%
His own sheet reports $655/SF — it divides by 135,953 SF, which is 555 Johnson, not this building.

## The Issues
165 RANDOLPH STREET
WHAT ACCOUNTS FOR THE DIFFERENCE
Our budget and his, complete, in one identical structure · nothing stripped from either side · 16 Sep 2026 · CONFIDENTIAL
HIS = his number needs to move. OURS = ours does. BOTH = a decision neither of us can make alone. NEITHER = leave it exactly where it is.
Whose | Issue | The evidence, quoted from his file | What to do | All-in $ at stake, indicative
HIS | Contingency is charged on the whole project, not on what the label says | D67 reads 'Soft Costs & FFE Contingency 10%' and computes =(D23+D31+D47+D65)*0.1. D31 is the $63,651,265 construction number, which already holds $5,786,479 of contractor contingency. | Keep one or the other, not both. $578,648 of it is literally contingency on contingency. | 6590876.472
HIS | $9.7M of trade cost is multiplied by a floor area this building does not have | HVAC is one line: 132,542 SF x $45.00 = $5,964,390, no tonnage, no load. Eight more run on 135,953 SF — paint $5, I/O lighting $12, general power $6, mechanical power $3, temp light $2, fire alarm $2, emergency $1, dimming $0.75. Sprinkler mains for a 14,000 SF mezzanine deck are priced on 50,000 SF. (The I/O lighting line runs on 135,953 SF too, but it is counted once below instead of twice here.) | Re-cut to 74,100 SF (footprint) or 88,100 SF (covered floor). 135,953 SF is 555 Johnson, not this building — it is a template carryover. | 5455744.5943
HIS | General conditions is charged in two places at once | $3,141,000 as a staffing chart below the line, plus $3,034,000 of division 013000 inside trade cost — including 'Project Labor 1 LS $2,000,000' with no crew, rate or duration. | 12.36% combined against 7.80% and 8.90% from Schimenti at 555 Johnson — open shop, this submarket, Eric's own GC. Pick one place and hold it at 8.35%. | 2643751
HIS | Scaffolding is the biggest single package gap in the file | $6,170,000 against our $1,438,262. A $4,000,000 sidewalk bridge lump with his own backup rows — 1,126 LF @ $500 and 27,024 SF @ $75 — footing to $2,589,800 directly beneath it, plus $2,000,000 of interior scaffolding. | Ask which of his two numbers is right, and how many linear feet of actual public sidewalk this building has. | 3970153
HIS | Structural steel is $0 on a project scoped 'Add Second Level' | All nineteen lines of 055100 are zero quantity: roof trusses and columns at $6,000/TON, mezzanine framing, balcony framing, stage lighting and AV support structure at $8.00/LB, railings, stairs, dunnage, lintels. We carry $5,827,741. | His own $8.00/LB rate is good — our rigging grid works out to $9.21/LB, so he corroborates us within 15%. Give him the tonnage.
HIS | 2,000 coat check lockers at $500 each | $1,000,000 inside specialties, note '333LF'. That serves 27% of a 7,440-capacity house at once, at a rate for a gym locker bank. | 750 at $350 is a generous January coat check. | 972689
HIS | The lighting package is bought twice | 'I/O lighting package throughout PROVIDED BY OTHERS 135,953 SF @ $12 = $1,631,436' sits in his electrical trade, while FF&E separately carries $1,750,000 of architectural lighting and $520,000 of performance lighting. | His own line says others provide it. Keep the conduit and wiring, delete the fixtures. | 2151701
HIS | Plumbing is 2.1x ours and one of us has the fixture count wrong | $3,717,250 against our $1,757,502. 178 water closets, 154 lavatories and 51 urinals at $4,000 each, nine bars roughed, a $125,000 restaurant grease trap. | GET THE ARCHITECT'S CODE FIXTURE CALCULATION. Settleable with arithmetic in an afternoon, and ours may well be the light one.
BOTH | We are building two different roofs | He demolishes 74,000 SF of pre-cast roof at $8/SF and lays 56,085 SF of new membrane at $36/SF. We lift the existing roof on the lifter's towers, extend the columns and clad a new 30 ft band. | SETTLE THIS FIRST. It moves concrete, steel, scaffolding, demolition and roofing all at once, and nothing else reconciles until it is decided.
BOTH | Second floor, third floor, roof decks, balcony, two lounges, foundry, restaurant | Finishes are 4x ours — $3,509,501 against $866,500. He is pricing a programme off the test fit, and it drives his sprinkler quantities, his fixture counts and the 135,953 SF. | PROGRAMME, NOT AN ERROR. He priced what the drawings showed him. That conversation is with Wake and with us, and it has to happen before the next version.
BOTH | HVAC agreeing is a coincidence | $5,964,390 his against $5,950,650 ours — $13,740 apart. His is one line on an area basis. Ours is built from the occupancy load. | Two different methods landing in the same place. Get tons from the mechanical engineer before either number is trusted.
NEITHER | The $12,000,000 plug is right-sized — leave it alone | The scope he left at zero or barely touched is scope we price at $10,614,464. His plug covers it with about $1,385,536 of headroom. | The instinct is to attack the biggest round number in the file. Don't. Ask him to PRICE it, not cut it — and when he does, the trade cost moves, not the plug.
OURS | Acoustics is under-carried by him and must not be cut to his number | $581,802 of K13 against our $1,864,000. | Ours is not decoration — it is the licence to operate next to residential.
OURS | His elevator build-up is better than our allowance | 4 lobby stops + 2 stage stops at $75,000 plus a hydraulic lift = $480,000. Ours is a $300,000 allowance. | Take his.
OURS | VESDA — he is right and we do not carry it | $250,000 for aspirating smoke detection in the music hall. | A 50 ft clear volume with haze and pyro needs it. Add it.
OURS | Sitework — we under-carry | $346,335 against our $90,000: 8,295 SF of sidewalk repair, trees, fencing and a 2,380 SF fire-escape egress route at $75/SF. | His is the real number; ours is an allowance.
| QUANTIFIED, ALL-IN |  |  | 21784915.0663
The seven quantified items come to $21,784,915 of his $24,436,525 gap. Each is priced on its own, so they are INDICATIVE and do not sum exactly — correcting one changes the base the next one sits on.
For the exact combined effect, the audit workbook applies every correction to a source cell and re-runs his own formula chain: $89,084,591 falls to $68,143,696, a real reduction of $20,940,896.
What is left is programme — a second floor, roof decks, a balcony, two lounges, a foundry and a restaurant that he priced because the test fit showed them to him. That is not an estimating error and it is not his to fix.