## The Other Expenses
165 RANDOLPH STREET
EVERY LINE BELOW THE CONSTRUCTION NUMBER
Soft costs, FF&E and off-site · everything below the construction number · 16 Sep 2026 vs our V2 · CONFIDENTIAL
Ours $12,411,110. His $17,334,727. He is $4,923,617 higher.
His columns tie to his own Budget Summary rows D47, D65 and D23, untouched. Ours tie to divisions 700 and 600 as published, plus three items we carry inside the TRADE cost that he carries here — abatement $1,000,750, signage and wayfinding $125,000, and lighting and controls $299,100. Each is flagged on its own row.
SIX LINES ARE IDENTICAL TO THE DOLLAR: feasibility, project management, data and CCTV, office furniture, merchandise cases, and operations. That is not a coincidence — we built ours off his where his was sound.
SOFT COSTS
| OURS | HIS | Delta | His lines, verbatim | What it means
Abatement | 1000750 | 1483680 | 482930 | Pipe insulation 190 LF @ $72 = $13,680. ROOF ABATEMENT 70,000 SF @ $21 = $1,470,000. | HIS ROOF RATE IS 2.8x OURS ($21 vs our $7.50/SF) and it presumes the roof comes off. A lift keeps it — you abate what you disturb at the perimeter, not the whole field. Also: HE CARRIES THIS AS A SOFT COST, WE CARRY IT AS A TRADE. Neither number means anything until somebody does the ACP-5 survey. Nobody has sampled that roof.
Feasibility & due diligence (spent) | 342000 | 342000 | 0 | Due Diligence & Feasibility Study 1 LS @ $342,000. | IDENTICAL. Already committed, already spent.
Design & engineering | 2906000 | 3561000 | 655000 | Architecture & Engineering $3,100,000 as ONE LUMP, with architecture, MEP and structural all noted 'Carried in line #3'. Plus brand $45,000, interior design $90,000, MEP consultant $30,000, lighting design $51,000, kitchen design $20,000, LV/AV $35,000, signage design $75,000, renderings $50,000, reimbursables $30,000, civil $10,000, traffic $10,000, acoustical $15,000. | He is $655,000 over us, but the comparison is unfair to him until that $3.1M lump is split. Note his ACOUSTICAL ENGINEERING IS $15,000 — 'sound and vibration testing'. We carry $200,000, because acoustic design next to residential is the licence to operate, not a test.
Investigation | 435000 | 150000 | -285000 | Geotechnical $150,000 (13 borings 50 ft deep, required for the ST permit). Environmental studies: $0, 'Carried in Feasibility Study'. | WE ARE $285,000 HIGHER AND WE SHOULD BE. He carries no Phase I, no Phase II, no existing-conditions survey and no Rooflifters Stage 3 structural analysis. Those four are exactly what turns this budget from an estimate into a number — and the Stage 3 analysis decides whether the roof can be lifted at all.
Permits & approvals | 420000 | 678297.48 | 258297.48 | Permit & plan review fees $493,297, stated as '1.3% Trade Costs'. Special Projects Program $50,000, MEP permits $10,000, FA consultant $35,000, fire safety plan $21,500, fire protection plan $18,500, Con Ed connection $50,000. | His $493,297 is a PERCENTAGE OF HIS OWN TRADE COST, so it inherits every inflation in it. Cut the trade cost and this falls with it. We carry $120,000 for DOB structural (ST) permit filing and expediting, which he does not — on a roof lift that filing is 12-18 months and it is the hardest permit in the job.
Legal & licensing | 250000 | 0 | -250000 | Attorney Fees: $0. 'SLA Legal Fees carried in Feasibility DD'. | HE CARRIES NO LEGAL AT ALL. On Factory Town the liquor licence was approved at ZERO and came in at $250,000. We carry SLA counsel $120,000, cabaret or its current equivalent $45,000, theater use-classification filing $55,000 and a zoning determination $30,000. The seating on the drawings is a licensing dependency — this is not optional.
Testing & controlled inspections | 140000 | 50000 | -90000 | Controlled inspections 1 LS @ $50,000. | Light. NYC special inspections on a job with new structural steel, a lifted roof, fireproofing, sprinklers and a new 8,000A service run well past $50,000.
Builder's risk & GL insurance | 385000 | 0 | -385000 | G.L. INSURANCE $0 and BUILDERS RISK INSURANCE $0 on his fit-out sheet. Notionally inside the 9% 'Overhead, Profit & Insurance'. | ASK HIM TO CONFIRM IT IS ACTUALLY IN THE 9%. Schimenti's comparable line at 555 Johnson says 'Builder's Risk Insurance — Excluded' in black and white. If it is excluded here too, this is missing money, not a structural difference.
Project management | 520000 | 520000 | 0 | Project Management $500,000 + Estimating Services $20,000. | IDENTICAL TO THE DOLLAR. But the Budget Summary labels it 'Project Management (Live Nation)'. It is not — Live Nation is the co-pro and programming partner. This is our own development team. Fix the label before this budget goes to a lender.
TOTAL SOFT COSTS | 6398750 | 6784977.48 | 386227.48
FF&E
| OURS | HIS | Delta | His lines, verbatim | What it means
Seating & furniture | 196760 | 1043750 | 846990 | 3,714 GA cushioned folding chairs @ $125 = $464,250. 657 mezzanine box chairs @ $300 = $197,100. 63 elevated chairs, 15 couches, 24 coffee tables. VIP lounge $75,000, VIP roof terrace $15,000, restaurant $60,000, restaurant terrace $10,000, roof terrace $25,000, roof lounge $35,000. Dressing rooms $60,000, crew lounge $25,000. | THE BIGGEST FF&E GAP AND IT IS A LEGAL QUESTION, NOT A FURNITURE ONE. We carry 720 removable mezzanine seats at $25 (MT H127 sourcing) and replace the 657 box chairs with $45,000 of loose stools, high-tops and rail perches. Seating shown on the drawings drives the theater use-classification, which drives the liquor licence. COUNSEL HAS TO SET THE SEAT COUNT BEFORE EITHER NUMBER IS RIGHT. The rest is furniture for a VIP/restaurant/roof programme nobody has designed.
Bar & kitchen equipment | 1050000 | 1317000 | 267000 | Kitchen equipment $130,000. Nine bars at $9,000 per POS position: lobby 5, music hall L 16, R 15, rear 14, mezz R 8, mezz L 8, VIP 2, restaurant 2, roof 4 = 74 positions. Ice machines 4 @ $15,000, walk-ins 2 @ $15,000. Freight & installation $375,000. | HIS OWN NOTE ON THIS SHEET IS THE MOST VALUABLE LINE IN THE FILE: '* BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K'. That is a prior build. 74 positions here at $9,000 = $666,000 against $837,000 for 26 positions plus a prep kitchen there. EVEN ALLOWING FOR THE KITCHEN, HE IS LIGHT — and so are we, at 53 positions. This is the one line where his own benchmark says the budget should go UP.
Data, IT & CCTV | 420000 | 420000 | 0 | VoIP phones / data switch / WiFi $200,000. CCTV 110 cameras @ $2,000 = $220,000. Data cabling: 'Carried Construction Costs'. | IDENTICAL TO THE DOLLAR, camera for camera. We took his rate.
Office furniture | 65000 | 65000 | 0 | Administration $50,000, production desks $15,000. | IDENTICAL.
Signage, wayfinding & art | 275000 | 650000 | 375000 | Exterior signage $400,000, interior wayfinding and ADA $100,000, interior art and decor $150,000 ('interior scenic work & exterior building murals'). | We carry $150,000 of exterior signage in FF&E plus $125,000 of signage and wayfinding inside the trade cost. He is $375,000 higher. A $400,000 exterior sign is a marquee, and on this building it may well be worth it — but it is a brand decision, not an estimate.
Administration & screening | 143000 | 93000 | -50000 | Three safes @ $1,000, radios $20,000, METAL DETECTORS 1 LOT @ $70,000. | WE ARE HIGHER AND WE ARE RIGHT. One lot of metal detectors does not move 7,440 people. We carry 12 walk-through magnetometers at $10,000. Factory Town's security screening came in 49% over its budget.
Facility — merchandise | 26000 | 26000 | 0 | Merch cases $26,000. | IDENTICAL.
Operations — custodial, barricades, shop | 29000 | 29000 | 0 | 80 trash cans @ $150, 2 janitor carts, bike rack $1,000, police barricades $10,000, hand tools $3,000, ladders $1,000, shelving $1,000. | IDENTICAL. Note the bike rack at $1,000 — Factory Town's bike racks came in 69% over budget. Small line, but it is a known direction.
Production equipment | 73500 | 193500 | 120000 | Stage barricade $18,000, portable stage $30,000, FORK LIFT $35,000, SCISSOR LIFT $25,000, washer & dryer $5,000, risers $12,000, dock plates and dollies $60,000, shelving and tools $8,500. | He carries a fork lift, a scissor lift, a portable stage and a washer/dryer that we do not. HE IS RIGHT ON THE LIFTS — a room this size owns them rather than renting them every load-in. Add $60,000 to ours.
Soft goods | 220000 | 500000 | 280000 | 'All soft goods' 1 LS @ $500,000, note: 'Stage / Perimeter Walls Music Hall — CUTDOWN DRAPE @ MEZZ EDGE Not Included'. | His own production benchmark note on the same sheet reads 'Soft Goods $725k'. So his $500,000 is already below his own comp AND explicitly excludes the mezzanine-edge cutdown drape. Ours at $220,000 is the light one here. This needs a real drape package priced off the section.
Video | 75000 | 285000 | 210000 | Music hall projector $75,000, displays & distribution $200,000, VIP projector $10,000. UPSTAGE VIDEO WALL and OVERHEAD VIDEO WALL are both blank, with a note reading '$1,400/SF'. | The projector matches exactly. His $200,000 of displays and distribution is real scope we do not carry — concourse screens, box office, BOH. The video WALLS are Phase 2 in our plan and artists bring or rent their own; his file agrees by leaving them unpriced.
Audio — house PA | 2200000 | 1400000 | -800000 | House Sound System 1 LS @ $1,400,000, 'Includes Theater / VIP / Restaurant & Roof Area'. | WE ARE $800,000 HIGHER AND THIS IS OUR NUMBER TO DEFEND. His own benchmark note on the same sheet says 'Audio $690k'. Ours is $1,850,000 of PA plus $145,000 of tuning and $205,000 of flying hardware. Nobody tours a PA for this size room so it has to be house — but GET A VENDOR QUOTE before this goes to a lender. Right now it is the weakest number we own.
Performance lighting | 340000 | 520000 | 180000 | Performance Lighting 1 LS @ $520,000. VIP performance lighting $0. | His benchmark note says $450k. He is above it, we are below it. A house rig of fixtures, truss and hoists at $340,000 is thin for a 7,440 room — ours probably moves up.
FF&E installation labour | 600000 | 0 | -600000 | Not carried as its own line. His $375,000 of 'Freight & Installation' sits inside the bar and kitchen equipment package above. | Different home, not a different view — but ours is $600,000 across all FF&E against his $375,000 on the bar package alone. Once his lifts, soft goods and screening are installed too, the two get closer than they look.
Architectural lighting | 299100 | 1750000 | 1450900 | Architectural & Exterior Lighting 1 LS @ $1,750,000. SEPARATELY, his ELECTRICAL trade carries 'I/O lighting package throughout PROVIDED BY OTHERS 135,953 SF @ $12 = $1,631,436'. | THE BIGGEST SINGLE ITEM IN THE OTHER EXPENSES, AND IT IS BOUGHT TWICE. $1,750,000 here plus $1,631,436 inside the electrical trade = $3,381,436 of architectural lighting against our $299,100 of lighting and controls. Ours is almost certainly too thin for a room that trades on how it looks — but his is the same package paid for twice, and his own line says 'provided by others'.
TOTAL FF&E | 6012360 | 8292250 | 2279890
OFF-SITE
| OURS | HIS | Delta | His lines, verbatim | What it means
Off-site parking garage | 0 | 2257500 | 2257500 | D21 is '=86*25000' = $2,150,000 under a label reading 'Parking Garage - 260/spaces', plus 5% escalation = $107,500. | THE LABEL SAYS 260 SPACES AND THE FORMULA SAYS 86. We carry no off-site parking at all. Decide whether it is in the deal, then fix whichever of the two is wrong. Note this is the ONE line in his whole budget that gets escalation — the $63.7M building gets none.
TOTAL OFF-SITE | 0 | 2257500 | 2257500
TOTAL OTHER EXPENSES | 12411110 | 17334727.48 | 4923617.48

## What To Do
165 RANDOLPH STREET
THE OTHER EXPENSES, SORTED INTO ACTIONS
Soft costs, FF&E and off-site · everything below the construction number · 16 Sep 2026 vs our V2 · CONFIDENTIAL
WE CARRY SCOPE HE DOES NOT — and in most of these we are right
| Ours minus his | Why we are right to carry it
Investigation | 285000 | WE ARE $285,000 HIGHER AND WE SHOULD BE. He carries no Phase I, no Phase II, no existing-conditions survey and no Rooflifters Stage 3 structural analysis.
Legal & licensing | 250000 | HE CARRIES NO LEGAL AT ALL. On Factory Town the liquor licence was approved at ZERO and came in at $250,000.
Testing & controlled inspections | 90000 | Light. NYC special inspections on a job with new structural steel, a lifted roof, fireproofing, sprinklers and a new 8,000A service run well past $50,000.
Builder's risk & GL insurance | 385000 | ASK HIM TO CONFIRM IT IS ACTUALLY IN THE 9%. Schimenti's comparable line at 555 Johnson says 'Builder's Risk Insurance — Excluded' in black and white.
Administration & screening | 50000 | WE ARE HIGHER AND WE ARE RIGHT. One lot of metal detectors does not move 7,440 people.
Audio — house PA | 800000 | WE ARE $800,000 HIGHER AND THIS IS OUR NUMBER TO DEFEND. His own benchmark note on the same sheet says 'Audio $690k'.
FF&E installation labour | 600000 | Different home, not a different view — but ours is $600,000 across all FF&E against his $375,000 on the bar package alone. Once his lifts, soft goods and screening are installed too, the two get closer than they look.
SUBTOTAL | 2460000
If our numbers are right, HIS budget is missing this money — no Phase I or Phase II, no existing-conditions survey, no Rooflifters Stage 3 analysis, no legal at all, one lot of metal detectors for 7,440 people, and builder’s risk that may or may not be inside his 9%.
HE CARRIES MORE THAN US — and these split three ways
| His minus ours | What kind of difference it is
Abatement | 482930 | A METHOD DIFFERENCE. $21/SF on 70,000 SF of roof presumes the roof comes off. A lift keeps it. And nobody has done the ACP-5 survey.
Design & engineering | 655000 | UNKNOWABLE UNTIL HE SPLITS THE $3.1M A/E LUMP. But his acoustical engineering at $15,000 against our $200,000 is a real difference of view.
Permits & approvals | 258297.48 | A PERCENTAGE OF HIS OWN TRADE COST (1.3%). Cut the trade cost and this falls with it automatically.
Seating & furniture | 846990 | A LEGAL QUESTION. Seat count drives the theater classification which drives the liquor licence. Counsel decides this, not the estimator.
Bar & kitchen equipment | 267000 | BOTH OF US MAY BE LIGHT. His own note reads "BPT: 26 POS / Prep Kitchen / 1 Walk-in Cooler $837K" against 74 positions at $9,000 here.
Signage, wayfinding & art | 375000 | A BRAND DECISION. A $400,000 exterior sign may well be worth it on this building, but it is ours to decide, not an estimating error.
Production equipment | 120000 | HE IS RIGHT ON THE LIFTS. A room this size owns a fork lift and a scissor lift rather than renting them every load-in.
Soft goods | 280000 | HE IS PROBABLY RIGHT AND WE ARE LIGHT. His own benchmark note says $725k, and his $500,000 explicitly excludes the mezzanine-edge cutdown drape.
Video | 210000 | REAL SCOPE WE DO NOT CARRY. Concourse displays and distribution. The projector matches exactly and the video walls are Phase 2 on both sides.
Performance lighting | 180000 | HE IS ABOVE HIS OWN BENCHMARK ($450k) AND WE ARE BELOW IT. Ours probably moves up.
Architectural lighting | 1450900 | BOUGHT TWICE. $1,750,000 here plus $1,631,436 inside his electrical trade. His own line says "provided by others".
SUBTOTAL | 5126117.48
Plus the $2,257,500 off-site parking garage, which we do not carry at all and whose own label (260 spaces) contradicts its own formula (=86*25000).
ONLY ONE OF THESE IS A STRAIGHT ERROR
The architectural lighting bought twice. Everything else in the other expenses is either scope he is missing, scope we are missing, or a decision that belongs to us and to counsel — not to the estimator.