## Read Me First
165 RANDOLPH STREET
THE TAKEOFF CHANGES THE ANSWER
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
We were $24.4M apart. We are now $649,727 apart.
The RFEM model measures 1,994,335 lb of new and replacement steel — 997.2 SHORT TONS. Priced by the ton, our structure goes from an estimated $9,258,304 to a measured $16,710,249, and our budget goes from $64,648,067 to $77,897,555.
TWO OF MY 16 SEP FINDINGS ARE WRONG AND I AM WITHDRAWING THEM.
The model is NOT a roof lift. 62.4% of column steel starts at grade, all 517 truss members are new at +56.5 to +64.5 ft, the existing roof level carries zero members, and the words lift, jack, shore and splice appear nowhere in 8,658 rows. He and the structural engineer are building the same building; our lift assumption is the outlier.
His 135,953 SF is defensible. The model has 146,508 SF gross and 120,119 SF of enclosed floor. Our 14,000 SF mezzanine was an assumption; the model says 32,942 SF plus 13,077 SF of tiered seating plus a 26,389 SF occupied terrace.
Strip those two and the correction I reported falls from $20,940,896 to $11,836,763. Apply only what still stands and his $89,084,591 becomes about $77,247,828 — against our V3 of $77,897,555. That is 0.8% apart.
AND THE $12,000,000 PLUG IS NOW THE OTHER WAY ROUND. I told you it was right-sized. The measured structure alone is $16,710,249, of which $6,703,714 is bare steel by the ton, and his plug still has to cover all millwork, doors, storefront, glazing, tile, fireproofing and most of the drywall on top of that. When he prices it, his number goes UP.
| V2 (estimated) | V3 (measured) | Delta
Trade cost | 38166123 | 48557878.15 | 10391755.15
Escalation 10% | 3816612.3 | 4855787.815 | 1039175.515
General conditions 8.5% | 3244120.455 | 4127419.6428 | 883299.1878
Overhead, profit & insurance 9% | 3434951.07 | 4370209.0335 | 935257.9635
CONSTRUCTION COST | 48661806.825 | 61911294.6412 | 13249487.8163
Contingency | 5000000 | 5000000 | 0
FF&E | 5588260 | 5588260 | 0
Soft costs | 5398000 | 5398000 | 0
TOTAL DEVELOPMENT COST | 64648067 | 77897554.6412 | 13249487.6412
V3 $ per SF on 74,100 SF | 1051.2491
V3 $ per SF on the measured 146,508 SF gross | 531.6949
Thomas, as sent | 89084591.44
Thomas, after the corrections that SURVIVE the takeoff | 77247828
GAP to our V3 | -649726.6412

## The Takeoff
165 RANDOLPH STREET
WHAT THE STRUCTURAL MODEL ACTUALLY MEASURES
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
UNITS. The source reports tonnes (2,204.62 lb). US steel is bought in SHORT TONS (2,000 lb). Everything here is short tons, converted from the lb column. Using 904.62 where 997.17 belongs understates the steel by 10.2%.
VALUE ENGINEERING: MODEL REV 43 → VE1
| Rev 43 (lb) | VE1 (lb) | Saved (lb) | VE1 tons | %
Beams / girders | 1130205.08 | 1016730.12 | 113474.96 | 508.3651 | 10.04%
Columns / extensions | 1100161.51 | 721235.36 | 378926.15 | 360.6177 | 34.44%
Truss components | 166783.23 | 135424.31 | 31358.92 | 67.7122 | 18.8%
Braces | 131056.08 | 80323.25 | 50732.83 | 40.1616 | 38.71%
CFS — BOH & closure framing | 0 | 40621.96 | -40621.96 | 20.311
TOTAL NEW / REPLACEMENT STEEL | 2528205.89 | 1994335 | 533870.89 | 997.1675 | 21.12%
VE1 MEMBER DETAIL — 8,658 rows aggregated by system and section type
System | Section type | Members | LF | lb | Short tons
Beams/girders | Rolled W-shape | 992 | 17441 | 1003473 | 501.7365
Beams/girders | HSS tube | 104 | 338 | 13258 | 6.629
Columns/extensions | Built-up plate girder | 80 | 1320 | 403988 | 201.994
Columns/extensions | Rolled W-shape | 148 | 3107 | 307818 | 153.909
Columns/extensions | HSS tube | 15 | 197 | 9430 | 4.715
Truss components | Rolled W-shape | 517 | 5187 | 135424 | 67.712
Braces | HSS tube | 281 | 4781 | 52722 | 26.361
Braces | Rolled W-shape | 21 | 610 | 27601 | 13.8005
Cold-formed steel | CFS stud / track / strap | 2686 | 11557 | 40622 | 20.311
The highlighted row is the one that breaks a $6,000/TON rate: 80 shop-welded plate girder columns, I 48/24 to I 69.023/24, 60.00 LF each on grids B and E.
AREAS, COUNTS AND MASONRY
Scope | Unit | Rev 43 | VE1 | Change
Mezzanine / floor (+20 ft) | SF | 29062.39 | 32942 | 3879.61
Additional tiered seating coverage | SF | 0 | 13077 | 13077
Terrace / maintenance roof (+45 ft 7) | SF | 29059.08 | 26389 | -2670.08
Lower roof (+60 ft 6) | SF | 8055.42 | 5706 | -2349.42
High roof (+64 ft 6) | SF | 27392.99 | 27393 | 0.01
W01 / W02 roof caps | SF | 1441.28 | 1457 | 15.72
W03 / W09 roof caps (+60 ft 6) | SF | 363.06 | 350 | -13.06
BOH CFS roof (+33 ft 6) | SF | 0 | 4230 | 4230
Total new CMU | SF | 23329.93 | 39248 | 15918.07
Footing allowance | locations | 81 | 124 | 43

## Lift or Rebuild
165 RANDOLPH STREET
IS HE USING ROOF LIFTERS? NO. AND NEITHER IS THE STRUCTURAL ENGINEER.
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
Read off the member geometry, not off anybody’s description of it. Every number below is reproducible from the Member Detail sheet.
Test | What the model says
Where the columns start | 243 VE1 column members. 124 of them start at or below +2 ft — 450,114 lb, 225.1 short tons, 62.4% of all column steel — which is a NEW FULL-HEIGHT COLUMN off the slab. Only 25 members start at ~+20 ft, the existing roof line: 89,113 lb, 44.6 tons, 12.4%. The grid B and grid E columns are 60.00 LF each, built up from plate as I 48/24, I 64.961/24 and I 69.023/24 segments.
The high roof | All 517 truss members are phase NEW and sit between +56.5 ft and +64.5 ft: 135,424 lb of brand-new roof trusses at a level that does not exist in the building today.
The existing roof | The level 'Existing Roof / Lower (+20 ft and below)' carries ZERO members in VE1. Nothing of the existing roof structure is retained in the priced model.
Replacement vs new | Only 196,105 lb (98.1 short tons, 9.8%) is phase 'Replacement', and all of it is at 'Consolidated floor +20 ft and below' or 'Shared columns and vertical bracing'. None at the high roof.
Lifting language | The words lift, jack, shore, temporary, splice and underpin appear NOWHERE in the 8,658 member rows — not in phase, system, level, section or the overlap-review column.
Height | High roof is at +64 ft 6 in. Our locked project facts target 50 ft clear.
WHAT THIS MEANS
Thomas’s budget and the structural model agree with each other. Both demolish the existing roof and build new at height. His 74,000 SF of pre-cast roof demolition at $8/SF is not an error — it is the method.
Our locked project facts say a roof lift is mandatory, carried at $3.5M for the lifter plus roughly $3.5M of surrounding work, and that the 50 ft clear height is the moat. The model builds to +64 ft 6 in by rebuilding instead.
THIS IS THE DECISION THAT HAS TO BE MADE BEFORE ANYTHING ELSE RECONCILES. It moves concrete, steel, scaffolding, demolition, roofing, the DOB filing route and the programme. I have NOT changed the project facts file — that is your call, not mine, and it should be made with Wake and the structural engineer in the room.

## Findings Revised
165 RANDOLPH STREET
WHAT THE TAKEOFF CHANGES ABOUT THE 16 SEP AUDIT
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
Finding | What I said on 16 Sep | What the takeoff says | Verdict | $ withdrawn
Area basis — $11.3M of trade priced on 135,953 SF | I said 135,953 SF is a floor area this building does not have, and re-cut eight electrical, HVAC, paint and alarm lines plus two sprinkler lines onto 74,100 or 88,100 SF. I called it $4,710,823 of trade cost, $6,213,104 all-in. | The model has 146,508 SF of gross area: 74,100 ground + 32,942 mezzanine/floor + 13,077 tiered seating + 26,389 occupied terrace. Enclosed floor alone is 120,119 SF. Our 14,000 SF mezzanine was derived from test-fit occupancy loads; the structural model says it is 32,942 SF plus 13,077 SF of seating. His 135,953 SF sits between the enclosed floor and the gross, which is exactly where a stacked-area figure should sit. | WITHDRAWN. His denominator is defensible. Sprinkler coverage of 119,000 SF against a measured 120,119 SF of enclosed floor is close to right, and his 50,000 SF second-floor line lands near the measured 46,019 SF. I was wrong about this and the correction comes off. | 6213104
Roof method — he demolishes, we lift | I said his 74,000 SF of pre-cast roof demolition at $8/SF was pricing the wrong method, because a roof lift keeps the roof. $592,000 of trade, $780,789 all-in. | The structural model does not lift anything. 124 of 243 columns start at or below +2 ft — 450,114 lb, 62.4% of column steel — which is a new full-height column off the slab. Only 25 members start at the +20 ft existing roof line. All 517 truss members are new, between +56.5 and +64.5 ft. The level 'Existing Roof / Lower' carries ZERO members. The words lift, jack, shore, splice and underpin appear nowhere in 8,658 rows. | WITHDRAWN AND REVERSED. He and the structural engineer are building the same building. OUR roof-lift assumption is the outlier, and it is the single biggest thing to settle. | 780789
Interior scaffolding — $2,000,000 | I cut it to $400,000 on the grounds that a lift jacks the roof on the lifter's own towers and does not need the floor plate scaffolded. $1,600,000 of trade, $2,110,240 all-in. | If the roof comes off and a 64 ft frame goes up inside the existing walls, access, edge protection and interior staging are real and substantial. | WEAKENED, NOT WITHDRAWN. The $4,000,000 sidewalk-bridge lump still disagrees with his own $2,589,800 of backup rows, and that half of the finding stands. Hold the interior scaffolding at his number until he shows the staging plan. | 2110240
Contingency computed on the whole project | D67 reads 'Soft Costs & FFE Contingency 10%' and computes =(D23+D31+D47+D65)*0.1. | The takeoff has nothing to say about a spreadsheet formula. | STANDS. $6,590,876 over its own label, $578,648 of it contingency on contingency.
General conditions charged in two places | $3,141,000 below the line plus $3,034,000 of division 013000 inside trade cost = 12.36% against Schimenti's 7.80% and 8.90%. | Unaffected. | STANDS.
Coat check lockers, 2,000 at $500 | $1,000,000 for lockers serving 27% of the house. | Unaffected — though a building with 120,119 SF of enclosed floor has more room for them than one with 88,100. | STANDS.
Architectural lighting bought twice | $1,750,000 in FF&E plus $1,631,436 of 'I/O lighting package provided by others' inside the electrical trade. | Unaffected. The per-SF portion of that line is now defensible, but buying the package twice is not. | STANDS.
Structural steel at $0 and the $12,000,000 plug | I said the plug was right-sized — $12,000,000 against $10,614,464 of scope we price — and told you not to negotiate it. | The measured structure alone prices at $16,710,249 in our V3, of which $6,703,714 is bare steel by the ton. His plug has to cover that PLUS all millwork, doors, storefront, glazing, tile, fireproofing and most of the drywall. | REVERSED IN THE OTHER DIRECTION. The plug is far too SMALL. Do not negotiate it — but do not take comfort from it either. When he prices it, his total goes UP, not down.
Correction I reported on 16 Sep |  |  |  | -20940896
Withdrawn by the takeoff |  |  |  | 9104133
CORRECTION THAT STILL STANDS |  |  |  | -11836763

## V3 Detailed Budget
165 RANDOLPH STREET
V3 LINE SCHEDULE
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
Item | Qty | Unit | Rate | Amount | Basis / source
000 SITE & ENABLING
Sidewalk shed / bridge
Sidewalk shed, erect & dismantle | 1089 | LF | 210 |  | NYC shed ~$180-240/LF erected
Shed rental, 24 months | 26136 | LF-mo | 22 |  | SCHEDULE-DRIVEN. Rented monthly — every month of programme costs $23,958. Reduced from 30 to 24 months; confirm against the real construction schedule
DOT permit & renewals | 1 | LS | 45000 |  | Sidewalk shed permit, renewed periodically
Lighting & signage on shed | 1089 | LF | 18 |  | Required by DOT
Netting & debris containment | 32670 | SF | 1.1 |  | Facade protection during the lift
Interior protection & containment
Slab protection, hardboard & poly | 74100 | SF | 1.35 |  | Protecting the existing slab
Dust partitions & negative air | 1 | LS | 65000 |  | Containment during demo and abatement
Protection of retained equipment | 1 | LS | 22000
Temporary weather protection
Temporary roof membrane at open areas | 18525 | SF | 8.5 |  | Only ~25% of roof open at any stage on a lift
Perimeter tarping at the lift band | 32670 | SF | 3.2
Temporary heat & dehumidification | 1 | LS | 85000 |  | Winter work
Asbestos / hazmat abatement
ACP-5 / ACP-7 filing & asbestos investigator | 1 | LS | 45000 |  | NYC required on a 1948 building
Roofing felt & mastic abatement | 74100 | SF | 7.5 |  | SURVEY-DEPENDENT. PRESUMED ACM on a 1948 precast roof — nobody has sampled it. If the roof is clean this line goes to near zero. Get the ACP-5 survey done early; it is worth $555,750
Pipe & boiler insulation abatement | 1 | LS | 120000 |  | Dev budget notes a 5,250 MBH boiler and steam piping
Lead paint abatement at steel | 1 | LS | 95000
Air monitoring & clearance | 1 | LS | 55000
Hazmat disposal & manifesting | 1 | LS | 130000
Demolition — interior
Demo masonry walls at new entry/lobby | 2500 | SF | 12 |  | Dev budget 024100-1 rate & qty
Demo 8in CMU wall, 20ft tall | 1975 | SF | 14 |  | Dev budget qty, unpriced
Demo existing roll-up doors | 8 | EA | 1850 |  | Dev budget qty
Demo existing exterior doors | 7 | EA | 650 |  | Dev budget qty
Demo windows 1ft x 10ft | 34 | EA | 12 |  | Dev budget 024100 rate & qty
Demo ceiling-mount steam heaters & piping | 28 | EA | 1400 |  | Dev budget qty
Demo 5,250 MBH boiler & piping (15x6x7, 13,000 lb) | 2 | EA | 28000 |  | Dev budget qty. Rigging-out is the cost
Demo (5) steel columns | 5 | EA | 9500 |  | Dev budget qty
Caesarstone plant equipment removal & slurry pit remediation | 1 | LS | 185000 |  | Countertop manufacturing leaves silica and resin residue
Misc build-out demo, piping, CMU, partitions | 25935 | SF | 2 |  | Dev budget 024100-2 rate
Floor trenching for MEP | 1 | LS | 50000 |  | Dev budget 024100-5
Debris removal & dumpsters | 1 | LS | 95000
Sitework
New sidewalks around building | 1 | LS | 40000 |  | Dev budget 320000-1
Curb cuts & DOT restoration | 1 | LS | 35000
Site drainage tie-ins | 1 | LS | 15000
100 PRIMARY STRUCTURE — MEASURED FROM THE RFEM TAKEOFF
Structural steel — MEASURED off the RFEM model
Beams & girders — rolled W-shapes | 501.7 | TON | 6000 |  | MEASURED: 992 members, 17,441 LF, 1,003,473 lb. Rate is THE ESTIMATOR'S OWN, from his unpriced 055100 line 'F&I new Roof Trusses, girders, Columns at Music Hall area @ $6,000/TON'.
Beams & girders — HSS tube | 6.6 | TON | 6600 |  | MEASURED: 104 members, 338 LF. Tube carries more cutting, capping and end prep than rolled.
Columns — BUILT-UP PLATE GIRDER | 202 | TON | 8400 |  | MEASURED: 80 members, 1,320 LF, 403,988 lb. These are NOT rolled shapes — they are shop-welded from plate, I 48/24/0.438/1.375 through I 69.023/24, on grids B and E at 60.00 LF each. Plate girder columns run 30-45% over rolled because of the welding, NDT and handling. $6,000/TON IS THE WRONG RATE FOR THIS LINE.
Columns — rolled W-shapes | 153.9 | TON | 6000 |  | MEASURED: 148 members, 3,107 LF. Estimator's own rate.
Columns — HSS tube | 4.7 | TON | 6600 |  | MEASURED: 15 members, 197 LF.
Roof trusses — fabricated assemblies | 67.7 | TON | 7200 |  | MEASURED: 517 members, 5,187 LF, 135,424 lb, all between +56.5 ft and +64.5 ft. Truss fabrication carries more shop labour per ton than plain framing.
Braces — HSS tube | 26.4 | TON | 6600 |  | MEASURED: 281 members, 4,781 LF.
Braces — rolled W-shapes | 13.8 | TON | 6000 |  | MEASURED: 21 members, 610 LF. Estimator's own rate.
Cold-formed steel — BOH & closure framing | 11557 | LF | 22 |  | MEASURED: 2,686 pieces, 11,557 LF, 40,622 lb. CEMCO 1200S350-68 joists, 800S162-54 studs, track, blocking and flat strap. Priced per LF installed, which is how CFS is bought.
Erection, connections & inspection
Connection design & shop detailing | 1 | LS | 285000 |  | 976.9 tons of hot-rolled with built-up plate columns and a trussed high roof. Detailing and connection design is a separate engineering scope from the EOR's model.
Column base plates, anchor bolts & setting | 124 | EA | 4200 |  | MEASURED: 124 footing locations in VE1, up from 81 in Rev 43.
Grouting at column bases & truss bearings | 1 | LS | 38000 |  | The estimator's own 033000 line 'Grouting at Steel Trusses & Column Base Plates', which he left at zero quantity with a $15,000 rate. Scaled to 124 locations.
Shear studs & deck welding | 46019 | SF | 1.85 |  | MEASURED: 46,019 SF of composite floor and tiered seating.
Crane, rigging & hoisting for erection | 1 | LS | 940000 |  | 60 ft built-up columns and 150 ft trussed girders in a constrained Brooklyn lot. This is a crawler or tower crane over months, not a boom truck.
Erection engineering, temporary bracing & survey | 1 | LS | 265000 |  | Stability of a 64 ft frame during erection is its own design.
Special & controlled inspections — structural | 1 | LS | 195000 |  | NYC controlled inspection of welding, bolting and high-strength connections on 976.9 tons.
Foundations for the new load path
New column footings | 124 | EA | 11500 |  | MEASURED: 124 locations. Rate is above our old $7,500 because these carry 60 ft built-up columns and a high roof, not a mezzanine. GEOTECH-DEPENDENT — 13 borings at 50 ft are in the soft costs and not yet done.
Excavation, spoil removal & disposal | 124 | EA | 3400 |  | Per footing, replacing our old blanket 74,100 SF x $6.50. The takeoff gives locations, so price locations.
Underpinning at existing footings | 24 | EA | 9500 |  | CARRIED FORWARD from our V2 — the takeoff does not enumerate underpinning. Confirm against the geotech and the existing foundation drawings.
Rebar, dowelling & pier caps | 1 | LS | 145000 |  | Scaled from our V2 at 124 locations.
Slab cut, patch & pour-back at new columns | 124 | EA | 2600 |  | Measured locations.
Deck, masonry & fireproofing
Composite metal deck & concrete — floor & tiered seating | 46019 | SF | 34 |  | MEASURED: 46,019 SF (mezzanine/floor 32,942 + tiered seating 13,077).
Metal roof deck | 61295 | SF | 9.5 |  | MEASURED: 61,295 SF across terrace, lower roof, high roof and caps.
BOH CFS roof deck | 4230 | SF | 9.5 |  | MEASURED.
New CMU — walls, shafts & closure | 39248 | SF | 35 |  | MEASURED: 39,248 SF, up from 23,330 in Rev 43. Rate is THE ESTIMATOR'S OWN 042000 rate, $35/SF, which he left at zero quantity.
Spray-applied fireproofing on new steel | 107314 | SF | 5 |  | Rate is THE ESTIMATOR'S OWN 078100 rate, $5.00/SF, which he left at zero quantity across all three of his fireproofing lines.
Carried forward — not in the structural model
MEP disconnect & reinstatement | 1 | LS | 550000 |  | Carried forward from V2. The structural model has nothing to say about MEP.
Fire separation | 1 | LS | 200000 |  | Carried forward from V2.
Egress & guarding at raised levels | 1 | LS | 287216 |  | Carried forward from V2. Stairs and railings appear in the takeoff only as a few W-shapes; guarding, treads and nosings do not.
Roofing — new roofs need new roofing
Roof membrane, insulation & flashing — all new roofs | 61295 | SF | 36 |  | CONSEQUENCE OF THE METHOD CHANGE, not from the takeoff. 61,295 SF of new roof deck needs a new roof. Rate is THE ESTIMATOR'S OWN 075000 rate of $36/SF. V2 carried 'roof reinstatement' at $6/SF because a lift keeps the roof it already has.
Occupied terrace — pavers on pedestals | 26389 | SF | 31 |  | MEASURED: 26,389 SF. The model calls this level 'Occupied Terrace (+45 ft 7 in)', so it needs a walking surface. Rate is the estimator's own paver rate.
New roof drains & leaders | 18 | EA | 8500 |  | Carried forward from V2.
Roof dunnage for HVAC equipment | 8 | LOC | 20000 |  | Carried forward from V2. Matches the estimator's own unpriced 055100 line at $20,000/LOC.
Roof penetrations framing for exhaust | 1 | LS | 25000 |  | Carried forward from V2.
200 STAGE — ground-supported, Factory Town method
Stage foundations
Footings poured into slab | 12 | EA | 7500 |  | No hurricane scope — interior, zero wind load. FT Infinity footers were $826,986 open-air Miami-Dade
Slab cutting & patching at footings | 12 | EA | 2400
Anchor bolts & embeds | 12 | EA | 1850
Stage structure & deck
Stage structure design & fabrication | 1 | LS | 720000 |  | FT Infinity actual $2,163,275 (Mountain Production) INCLUDED an open-air roof and crowd weather cover this building does not need
Structural steel erection | 1 | LS | 180000
Stage deck framing & metal deck | 3500 | SF | 22
Stage T&G wood floor | 3500 | SF | 35 |  | Dev budget 096400-1, QTY 0
Stage stairs & access | 4 | EA | 13000 |  | Dev budget 055100-7 rate
Production towers & mounting structure
Black steel mounting structure — YOUR QUOTE | 1 | LS | 1000000 |  | Ground-supported so nothing hangs from the building. This is what lets the roof stay at 15 lb/SF
Access ladders & unistrut at overhead grid | 1 | LS | 15000 |  | Dev budget 055100-15 / 055100-11, QTY 0
Rigging grid over the crowd — ground-supported lighting towers + spanning steel
Tower footings poured into slab | 8 | EA | 8500 |  | Same detail as the stage footings. Interior, zero wind load — these carry gravity and the grid's own lateral bracing, not a hurricane case
Slab cutting & patching at tower bases | 8 | EA | 2400
Anchor bolts, embeds & base plates | 8 | EA | 1850
Lighting / support towers, 45ft lattice, fabricate & deliver | 8 | EA | 34000 |  | FT Infinity lighting towers were $92,020 for the lot (Mountain Production). These are dearer per tower because they carry a 150ft spanning grid, not just fixtures. 4 per side at 50ft on centre
Cross-span trussed girders over the crowd, 150ft clear span | 1050 | LF | 310 |  | THE ANSWER TO THE USER'S ASK. 7 girders at 25ft on centre spanning the full 150ft crowd width. ~6.5 tons each at $6,000/ton fabricated and erected, plus connections, camber, shop drawings and finish
Longitudinal header trusses on the tower lines | 350 | LF | 240 |  | Two header runs, one per side, 175ft each. They spread the cross-girder reactions to the towers at 50ft o.c. so no girder lands mid-span
Grid erection: crane, riggers, lifts | 1 | LS | 185000 |  | SCHEDULE. Erect this WHILE THE ROOF IS OFF during the lift window and you pick it straight down through the opening. Erect it after the roof closes and you are assembling 74 tons of steel by chain hoist inside a finished room
Chain hoists, 1-ton, at grid pick points | 32 | EA | 2850 |  | 32 points on a 150ft x 175ft grid is roughly one every 25ft x 25ft
Motor control, distro & festoon | 1 | LS | 48000
Load cells & live load monitoring | 1 | LS | 36000 |  | CODE. Rigging over an assembly occupancy — DOB and your insurer will both want the grid instrumented
Rigging steel, shackles, span sets, bridles & secondaries | 1 | LS | 42000
PE-stamped structural design & DOB filing for the grid | 1 | LS | 85000 |  | CODE. This is a permanent structure carrying live load over the public. It gets filed, not just built
Load test & certification | 1 | LS | 28000 |  | CODE
Access catwalk on the header lines | 350 | LF | 185 |  | CUTTABLE. Lets you focus and service the grid without a lift on the floor. Drop it and you focus from a genie between load-ins
Platforms & FOH
VIP platforms & decking fabrication | 1 | LS | 136000 |  | FT actual, Mountain Production
FOH platform / control position | 1 | LS | 55000 |  | CORRECTED. This line previously carried $92,020, which is actually FT's LIGHTING TOWERS lot (Mountain Production), not a FOH platform. That figure now sits against the towers below where it belongs. A ~600 SF decked and railed control position with cable management is ~$55,000
Stage decking | 1 | LS | 50468 |  | FT actual, Kamilla Productions
Erection labour & equipment
Stage build labour | 1 | LS | 122716 |  | FT actual, Island Productions
Crane & rigging for erection | 1 | LS | 45000 |  | FT actual, George's Crane
Heavy equipment & lifts | 1 | LS | 24390 |  | FT actual, HERC Rentals
400 ENVELOPE & INTERIORS
Masonry
Patch & repair existing masonry wall | 9972 | SF | 10 |  | Dev budget 042000-1 rate & qty
CMU & brick infill at removed windows/doors/grilles | 1 | LS | 68000 |  | Dev budget 042000-3, QTY 0
Repointing & cleaning existing facade | 1 | LS | 85000 |  | Dev budget 042000-4, QTY 0
New CMU — see division 100 | 0 | SF | 0 |  | MOVED. The takeoff measures 39,248 SF of new CMU across the whole building and it is priced in division 100. Patching, infill and repointing of EXISTING masonry stay here.
Doors, frames & hardware
Single hollow metal doors, non-acoustic | 64 | EA | 1800 |  | Dev budget 081000-1 rate, QTY 0
Double hollow metal doors, non-acoustic | 22 | PAIR | 2500 |  | Dev budget 081000-2 rate
Acoustic doors at music hall | 18 | EA | 6500 |  | Dev budget 081000-3 rate. Sound lock at every hall opening
Acoustic double doors at music hall | 10 | PAIR | 10000 |  | Dev budget 081000-4 rate
Special doors (Eliason) | 2 | EA | 3000 |  | Dev budget 083000-1, priced in file
Door hardware, closers, panic devices | 96 | EA | 950 |  | CODE — panic hardware on egress doors
Install doors/frames/hardware | 96 | EA | 650 |  | Dev budget 092000-7 rate
Storefront & glazing
New storefront with doors at entry | 900 | SF | 250 |  | Dev budget 084100-1 rate, QTY 0
Ballistic box office window | 1 | LOT | 10000 |  | Dev budget 088000-5
Mirrors at public restrooms & green rooms | 1 | LOT | 22000 |  | Dev budget 088000-2/3
Mirror behind bars | 1 | LOT | 35000 |  | Dev budget 088000-4
Drywall & partitions
Perimeter wall partition at existing exterior wall | 9972 | SF | 12 |  | Dev budget 092000-1 rate & qty
Perimeter partition at new exterior wall | 2022 | SF | 12 |  | Dev budget qty
2HR fire-rated wall rear of stage, 20ft high | 5565 | SF | 20 |  | Dev budget qty. CODE
2HR fire-rated wall rear of music hall, 20ft high | 2857 | SF | 20 |  | Dev budget qty. CODE
Plywood 8ft AFF at stage walls | 1672 | SF | 9 |  | Dev budget qty
2in insulation above 8ft AFF to 38ft AFF | 6932 | SF | 6 |  | Dev budget qty
Proscenium wall | 4194 | SF | 22 |  | Dev budget qty
Interior sound/fire rated walls at stairs & shafts | 18000 | SF | 20 |  | Dev budget 092000-3 rate, QTY 0
Interior non-rated partitions, BOH & offices | 14000 | SF | 12 |  | Dev budget 092000-4 rate, QTY 0
Blocking | 1 | LS | 30000 |  | Dev budget 092000-8
Acoustic treatment — licence to operate
Acoustic panels at music hall walls | 28000 | SF | 40 |  | Dev budget 100500-1 rate, QTY 0. The comparable venue died partly of noise
K13 at underside of mezzanine & hall ceilings | 42000 | SF | 12 |  | Dev budget 100500-2 rate, QTY 0
Isolation hangers & resilient mounts | 1 | LS | 145000 |  | Structure-borne isolation
Acoustic sealant & flanking control | 1 | LS | 95000
Finishes
Tile at restroom floors & walls | 6200 | SF | 30 |  | Dev budget 092300-1/2 rate, QTY 0
Sealed & polished concrete elsewhere | 52000 | SF | 8 |  | Dev budget 033000-12 rate. The Infinity aesthetic
LVT at green rooms & dressing rooms | 3200 | SF | 10 |  | Dev budget 096000-2 rate
Paint walls, doors, ceilings, exposed structure | 80000 | SF | 2.5 |  | Dev budget 099000-1 rate, QTY 0
Entry mats & stair treads | 1 | LS | 32500 |  | Dev budget 096000-6/7
Specialties
Toilet partitions | 60 | EA | 1500 |  | Dev budget 100000-3 rate, QTY 0
Toilet accessories | 30 | SET | 7500 |  | Dev budget 100000-2 rate
Fire extinguishers & cabinets | 45 | EA | 350 |  | Dev budget 100000-1 rate. CODE
Millwork
Bar & back bar, six bars | 380 | LF | 900 |  | Dev budget 064000 rate, QTY 0
Decorative feature above each back bar | 6 | EA | 10000 |  | Dev budget 064000-9
Box office millwork | 40 | LF | 500 |  | Dev budget 064000-18 rate
Merchandise millwork | 1 | LS | 12000 |  | Dev budget 064000-12
Public restroom countertops | 120 | LF | 400 |  | Dev budget 064000-11 rate
Green room bathrooms & countertops | 60 | LF | 350 |  | Dev budget 064000-10 rate
Coat check shelf & pole | 50 | LF | 150 |  | Dev budget 064000-14 rate
Signage & wayfinding
Interior wayfinding & ADA signage | 1 | LS | 100000 |  | CODE — egress and ADA portions
Interior door signs & directional | 1 | LOT | 25000 |  | Dev budget 101400
Rough carpentry & protection
Safety protection at roof cut-out | 1 | LS | 35000 |  | Dev budget 062000-1
Safety protection at footing trenches | 1 | LS | 30000 |  | Dev budget 062000-2
Safety at new raised levels | 46019 | SF | 2 |  | RESCALED from 14,000 SF to the measured 46,019 SF of elevated floor and tiered seating.
Rough carpentry at stage area | 3500 | SF | 5 |  | Dev budget 062000-5 rate
Diamond plate at loading dock walls | 1 | LS | 18000 |  | Dev budget 092000-10
500 MEP
HVAC
Air handling & distribution | 74100 | SF | 26 |  | CORRECTED to the 74,100 SF basis. Filed at 120,000 SF x $40
Chiller plant, 400-500 ton | 450 | TON | 3100 |  | People alone are ~250 tons at 7,440 occupants
Ductwork, diffusers, VAV | 74100 | SF | 9.5
Building management system | 1 | LS | 500000 |  | Dev budget 230000-2, priced in file
Toilet & BOH exhaust | 1 | LS | 95000 |  | WAS 'Kitchen & toilet exhaust' at $165,000. Kitchen exhaust moved to division 800 so the kitchen toggle actually controls every kitchen dollar. Toilet and BOH exhaust stay here because you need them whatever you do about food
Smoke control / exhaust at the hall | 1 | LS | 420000 |  | CODE — large-volume assembly space
Testing, adjusting & balancing | 1 | LS | 95000
Heating
Radiant tube / panel heating at height | 74100 | SF | 11 |  | No heating scope in the dev budget at all. Forced air fails at a 50ft ceiling
Fire protection
Rework existing sprinkler, first floor | 69000 | SF | 7 |  | Dev budget 210000-1 rate & qty
New sprinkler & mains at mezzanine | 14000 | SF | 10 |  | Dev budget 210000-2 rate
Standpipe & booster pump | 1 | LS | 185000 |  | Dev budget 260000 references a standpipe booster pump
Fire pump & controller | 1 | LS | 145000 |  | CODE at this height and area
Safe-off / disconnect | 1 | LS | 10000 |  | Dev budget 210000, priced in file
Fire alarm & detection
Fire alarm system | 88100 | SF | 2.5 |  | Dev budget 283100-1 rate, corrected to 88,100 SF protected floor
Vesda aspirating detection, music hall | 1 | LS | 150000 |  | Dev budget 283100-2, priced in file
FDNY filing, inspection & TCO affidavit | 1 | LS | 35000 |  | Dev budget soft cost 209
Plumbing
Water closets | 60 | EA | 5500 |  | Dev budget 220000-2, priced in file. CODE fixture count
Lavatories | 78 | EA | 5500 |  | Dev budget 220000-3
Urinals | 51 | EA | 5500 |  | Dev budget 220000-4
Showers | 6 | EA | 7500 |  | Dev budget 220000-5
Green room sinks | 6 | EA | 5500 |  | Dev budget 220000-6
Floor drains & sinks | 40 | EA | 3500 |  | Dev budget 220000-8
Electric water heaters | 10 | EA | 7500 |  | Dev budget 220000-9
Bar roughing, six bars | 6 | EA | 44167 |  | Dev budget 220000-11/12/13 rates, QTY 0
Gas piping to equipment | 1 | LS | 55000 |  | Dev budget 220000-18
Firestopping | 1 | LS | 15000 |  | Dev budget 220000-20
Water service upgrade & backflow | 1 | LS | 90000 |  | Domestic and fire demand at 7,440 occupants
Electrical service & distribution
(2) 2,500A switchboards | 2 | EA | 195000 |  | Dev budget 260000, priced in file
Con Ed vault, conduit & feeders from street | 1 | LS | 850000 |  | Dev budget carries only the $50k Con Ed fee
Transformer, CT cabinet, metering | 1 | LS | 325000 |  | Dev budget 260000-13, QTY 0
Combine existing services | 1 | LS | 200000 |  | Dev budget 260000-13, QTY 0
Panels & secondary distribution | 1 | LS | 480000 |  | Dev budget 260000-16, QTY 0
General power, devices, floor boxes | 74100 | SF | 3 |  | Dev budget 260000-7 rate, QTY 0
Power to mechanical equipment, VAVs, exhaust fans | 1 | LS | 295000 |  | Dev budget 260000-10/11/12, QTY 0
Dedicated circuits at bar & F&B equipment | 1 | LS | 165000 |  | Dev budget 260000-8 rate
Emergency power & inverter package | 1 | LS | 245000 |  | CODE — egress lighting and life safety
Generator for fire pump backup | 1 | LS | 185000 |  | Dev budget 260000-15, QTY 0
Temporary light & power for construction | 125000 | SF | 1.25 |  | Dev budget 260000-16, priced in file
Firestopping at cores & penetrations | 1 | LS | 12500 |  | Dev budget 260000-18, priced in file
Production power
Company switches & cam-lok tie-ins at stage | 1 | LS | 320000 |  | Underwriting carried $1.5M for production power; dev budget nothing
Production distro & feeder runs | 1 | LS | 285000
Dedicated power to stage equipment | 3500 | SF | 15 |  | Dev budget 260000-9 rate, QTY 0
Isolated technical ground | 1 | LS | 85000 |  | Audio system requirement
Lighting & controls
Exit signs & BOH fixtures | 1 | LS | 40000 |  | Dev budget 265000-1, priced in file. CODE
Emergency lighting package | 74100 | SF | 1 |  | Dev budget 260000-1 rate, QTY 0. CODE
House / architectural lighting, back of house & circulation | 1 | LS | 185000 |  | Not the $1.75M exterior package
Low voltage
Structured cabling backbone & horizontal | 1 | LS | 245000 |  | Dev budget 270000 light for this size
CCTV camera wiring | 110 | EA | 750 |  | Dev budget 270000-1, priced in file
AV wiring infrastructure | 1 | LS | 60000 |  | Dev budget 270000-3
Phone & data wiring | 1 | LS | 45000 |  | Dev budget 270000-4
Door intrusion & access control wiring | 24 | LOC | 5000 |  | Dev budget 270000-2 rate, QTY 0
Conveying
ADA passenger elevator, two stops | 1 | EA | 240000 |  | CODE — accessible route to every public level
BOH / production lift | 1 | EA | 60000
600 FF&E
Production — audio
House PA: mains, subs, fills, amplification, processing | 1 | LS | 1850000 |  | Always house — artists do not tour a PA for this size room. MT I61/I301: $2-2.2M for L-Acoustics
System design, tuning & commissioning | 1 | LS | 145000
Rigging, flying hardware & install | 1 | LS | 205000
Production — lighting
House rig: fixtures, truss, hoists | 1 | LS | 230000 |  | REDUCED. FT Infinity house rig actual was ~$205k for an open-air stage: 48x Chauvet Colorstrike M $118,616 (LPS) + rope + pixel bars. $230k for a larger enclosed room
Control, dimming & data distribution | 1 | LS | 85000
Install & focus | 1 | LS | 25000
Production — video & soft goods
Music hall projector & screen | 1 | LS | 75000 |  | Dev budget FF&E 309
Soft goods: stage & perimeter drape | 1 | LS | 220000 |  | REDUCED. Dev budget carried $200,000; the FT benchmark note on the same row said $725k. Working minimum at $220k
Production — equipment
Stage barricade | 1 | LS | 18000 |  | FT actual
Dock plates, ramps, hand carts, dollies | 1 | LS | 30000 |  | FT actual
Risers | 1 | LS | 12000 |  | FT actual
Storage shelving & tools | 1 | LS | 13500 |  | FT actual
Bar & F&B equipment
Bar equipment, six bars, ~53 POS positions | 53 | POS | 9000 |  | CORRECTED. FT and dev budget rate for bar equipment ALONE is $9,000/position. I had used Brooklyn Paramount's $32,192/POS which is ALL-IN incl. kitchen, walk-in and freight — while also carrying those separately below. Double count removed, $689,000
Ice machines | 4 | EA | 15000 |  | FT actual rate
Walk-in coolers | 2 | EA | 15000 |  | FT actual rate
Draft systems & glycol | 6 | EA | 18000 |  | Often vendor-supplied against a pouring agreement — ASK
Freight & installation | 1 | LS | 375000 |  | FT / dev budget actual
POS terminals | 53 | EA | 0 |  | ZEROED per MT I50: "I can get someone to give it to us for free for using the venue." Restore at $3,000/EA if that deal does not land
Seating — licensing dependency
Removable theatre seating, mezzanine | 720 | EA | 25 |  | TOGGLE. Rate is driven by the seating input cell at the top of this sheet — switch between $25 (MT H127 sourcing) and $125 (as filed in the dev budget). COUNT TO BE CONFIRMED BY COUNSEL — it carries the classification
Mezzanine raised-deck seating: stools, high-tops, rail perches | 1 | LS | 45000 |  | REPLACES 657 BOX CHAIRS AT $300 ($197,100). Loose seating on a stepped deck rather than fixed box furniture — flexes between standing and seated nights and holds more people in the same footprint
Seat & row numbering, aisle marking | 1 | LS | 13760 |  | Required with removable seating
Seating storage racks & carts | 1 | LS | 35000 |  | Stacked away on standing nights
Furniture
Dressing room furniture | 6 | EA | 10000 |  | Dev budget FF&E 301, priced in file
Crew & artist lounge | 1 | LS | 25000 |  | Dev budget FF&E 301
Office furniture, administration & production | 1 | LS | 65000 |  | Dev budget FF&E 304
Merchandise cases | 1 | LS | 26000 |  | Dev budget FF&E 307
IT, security & operations
VoIP, data switching & WiFi | 1 | LS | 200000 |  | Dev budget FF&E 303
CCTV cameras | 110 | EA | 2000 |  | Dev budget FF&E 303, priced in file
Walk-through magnetometers | 12 | EA | 10000 |  | FT paid $148,580 for a full OPENGATE system with LTE WiFi (CEIA USA) — 12 lanes at $10k lands in the same place
Radios & safes | 1 | LS | 23000 |  | Dev budget FF&E 306
Custodial, barricades, bike racks, shop equipment | 1 | LS | 29000 |  | FT unit rates: bike rack $211/each, crash barricade $200.76/ft
Signage
Exterior building signage | 1 | LS | 150000 |  | Identification and wayfinding, not a facade programme
Installation
FF&E installation labour | 1 | LS | 600000 |  | Dev budget 120000, priced in file
700 SOFT COSTS
Design & engineering
Architecture & engineering (Wake) | 1 | LS | 2200000 |  | Dev budget 203. MEP and structural folded in. FT's architect ran 3.9x its budget — watch this
Conceptual & brand development | 1 | LS | 45000 |  | Dev budget 203-1
Interior design | 1 | LS | 90000 |  | Dev budget 203-2
MEP consultant | 1 | LS | 30000 |  | Dev budget 203-7
Lighting design | 1 | LS | 51000 |  | Dev budget 203-8, Bandit
LV / AV design | 1 | LS | 35000 |  | Dev budget 203-10
Signage & wayfinding design | 1 | LS | 75000 |  | Dev budget 203-11
Renderings & reimbursables | 1 | LS | 80000 |  | Dev budget 203-12/13
Acoustical engineering & design | 1 | LS | 200000 |  | Designing $2M of treatment. Dev budget carried $15,000 for testing only
Structural engineering peer review | 1 | LS | 65000 |  | A roof lift warrants an independent check
Civil engineering | 1 | LS | 10000 |  | Dev budget 204
Traffic engineering | 1 | LS | 25000 |  | Dev budget 205. MT G45: 'prob more'
Investigation
Geotechnical — 13 borings 50ft deep | 1 | LS | 150000 |  | Dev budget 207. Required for the structural (ST) permit
Phase I environmental | 1 | LS | 45000 |  | Dev budget carried $0
Phase II environmental & soil sampling | 1 | LS | 105000 |  | 1948 industrial site, countertop manufacturer
Existing-conditions survey & scan | 1 | LS | 85000 |  | Required before a lift
Rooflifters Stage 3 structural analysis | 1 | LS | 50000 |  | Fee credited against the contract if awarded. WORTH $4.9M OF SCOPE CERTAINTY
Permits & approvals
DOB permit & plan review fees | 1 | LS | 90000 |  | Dev budget 209-1
Special Projects Program | 1 | LS | 50000 |  | Dev budget 209-2
MEP & misc permit fees | 1 | LS | 10000 |  | Dev budget 209-2
DOB structural (ST) permit filing & expediting | 1 | LS | 120000 |  | 12-18 month approval — the other half of the moat
FA consultant, filing & inspection scheduling | 1 | LS | 35000 |  | Dev budget 209-4
Fire safety & emergency action plan | 1 | LS | 21500 |  | Dev budget 209-5
Fire protection plan & FDNY filing | 1 | LS | 18500 |  | Dev budget 209-6
Place of Assembly certificate | 1 | LS | 25000 |  | CODE — required above a low occupant threshold
Utility connection fees (Con Ed) | 1 | LS | 50000 |  | Dev budget 210. The fee only
Legal & licensing
SLA liquor licence — application & counsel | 1 | LS | 120000 |  | FT's liquor licence came in at $250,000 against a ZERO budget
Cabaret licence / current equivalent | 1 | LS | 45000 |  | VERIFY — NYC repealed the cabaret law in 2017. Confirm what applies today
Theater use-classification filing & counsel | 1 | LS | 55000 |  | Carries both licences. Must be established at DOB filing
Land use / zoning determination | 1 | LS | 30000 |  | The as-of-right claim needs a written determination
Project management & control
Project management — owner's team (Thomas + consultants) | 1 | LS | 500000 |  | CUT TO $500,000 PER MT. WHO IT GOES TO: OUR OWN development team, not Live Nation. Carried against Thomas as project manager plus the outside consultants he runs. Live Nation is the programming / co-pro partner, NOT the developer — they do not staff this and they do not pay for it. At 1.1% of trade cost this is below the 2-4% norm, so it buys ONE full-time PM and a thin consultant bench, not an owner's-rep firm. Under-resourced owner PM is how change orders get approved unchallenged, so this is the line to watch, not the line to cut again
Estimating services | 1 | LS | 20000 |  | Dev budget 213-2
Controlled & special inspections | 1 | LS | 140000 |  | Dev budget 212 carried $50,000
Builder's risk & GL insurance | 1 | LS | 385000 |  | Not separately carried in the dev budget
Committed
Feasibility & due diligence (spent) | 1 | LS | 342000 |  | Dev budget 202. Already committed
800 KITCHEN & FOOD SERVICE — scope toggle at the top of the sheet
L0 · Base food service — you need this at ANY scope
Concession / grab-and-go service points, build-out | 4 | EA | 22000 |  | Four service points off the lobby and the mezzanine. Needed even if you never cook anything on site
Reach-in refrigeration at service points | 8 | EA | 4200
Power & water to service points | 1 | LS | 38000
Hand sinks & DOH compliance at service points | 6 | EA | 3800 |  | CODE. DOH requires a hand sink within reach of every food-handling station, whatever the food is
L1 · Warming / finishing kitchen — adds to L0
Quarry tile floor & coved base | 1400 | SF | 22 |  | CODE. DOH requires a hard, non-absorbent, coved floor in any food prep area
FRP wall panels at prep areas | 1200 | SF | 15 |  | Dev budget 092000-9 rate. MOVED HERE from division 400
Washable ceiling | 1400 | SF | 9 |  | CODE
Type II exhaust hood, non-grease | 20 | LF | 1400 |  | Type II is the cheap hood. It only works if you are NOT frying, grilling or char-broiling
Make-up air unit | 1 | LS | 42000 |  | A hood pulls air out of the room. You have to put it back or the room goes negative and the doors will not open
Kitchen exhaust duct, shaft & roof penetration | 1 | LS | 70000 |  | MOVED HERE from division 500
Kitchen plumbing rough-in | 1 | LS | 78000 |  | Dev budget 220000-15 was $135,000 for a FULL kitchen at qty 0. Warming scope is less
Dedicated power to equipment | 1400 | SF | 35 |  | Dev budget 260000-8 rate, QTY 0
Walk-in cooler, kitchen | 1 | EA | 42000 |  | Separate from the two BAR walk-ins already carried in division 600
Warming & finishing equipment: combis, holding cabinets, prep | 1 | LS | 165000
DOH & DOB kitchen filings | 1 | LS | 35000 |  | CODE. A food service establishment is its own permit track
L2 · Full production kitchen — adds to L1
Floor, wall & ceiling at the larger footprint | 1600 | SF | 40 |  | A production kitchen is roughly 3,000 SF against 1,400 for warming
Upgrade Type II to Type I grease hood incl. larger make-up air | 1 | LS | 118000 |  | CODE. The moment you fry, grill or char-broil you need a Type I grease hood. This is the single decision that drives the whole cost
Hood fire suppression, wet chemical | 1 | LS | 34000 |  | CODE. Follows the Type I hood, no exceptions. 40 LF at $850
Grease interceptor, 1,500 gal, cut into slab | 1 | LS | 85000 |  | CODE. DEP requires it. Cutting it into an existing slab is the expensive part
Gas service & piping to equipment | 1 | LS | 175000 |  | Dev budget 220000-18 carried $55,000 of piping at qty 0 and no gas SERVICE at all. If the building has no adequate gas service, National Grid is a separate application with its own lead time
Additional dedicated power | 1600 | SF | 35
Walk-in freezer | 1 | EA | 43000
Production equipment: hot line, cold line, ovens, fryers, dish machine | 1 | LS | 360000 |  | Dev budget 114000 listed this BY OWNER and never priced it
Smallwares & opening stock | 1 | LS | 45000
Roof platform & grease-duct cleaning access | 1 | LS | 18000 |  | CODE. Grease ducts must be cleanable

## V3 vs Thomas
165 RANDOLPH STREET
WHERE WE LAND AGAINST HIM NOW
V3 — rebuilt on the measured structural takeoff · RFEM 6.15 export, model Rev 38, version VE1 · CONFIDENTIAL
| Our V3 | Thomas as sent | Delta
Primary structure — measured | 20072927.65 | 0 | -20072927.65 | His division 055100 is $0. All nineteen lines, zero quantity.
His "Trade Costs To Be Priced" plug | 0 | 12000000 | 12000000 | Covers our $16.7M of structure PLUS millwork, doors, glazing, tile, fireproofing and drywall.
Everything else, trade cost | 28484950.5 | 34851959.75 | 6367009.25 | His trade less general-conditions content and preconstruction.
TRADE COST | 48557878.15 | 46851959.75 | -1705918.4
General conditions | 4127419.6428 | 6175000 | 2047580.3572 | Ours 8.5%. His staffing chart + div 013000.
Escalation | 4855787.815 | 0 | -4855787.815 | Blank in his file.
Overhead, profit & insurance | 4370209.0335 | 4777826.38 | 407617.3465
Contractor contingency | 0 | 5786478.61 | 5786478.61 | We hold one contingency, below.
Preconstruction | 0 | 60000 | 60000
CONSTRUCTION COST | 61911294.6412 | 63651264.74 | 1739970.0988
Contingency | 5000000 | 8098599.22 | 3098599.22 | His computes on the whole project. Still stands.
Soft costs | 5398000 | 6784977.48 | 1386977.48
FF&E | 5588260 | 8292250 | 2703990
Off-site parking garage | 0 | 2257500 | 2257500 | We carry none.
TOTAL | 77897554.6412 | 89084591.44 | 11187036.7988
AND AFTER THE CORRECTIONS THAT SURVIVE THE TAKEOFF
Thomas as sent | 89084591.44
Corrections that still stand | -11836763
Thomas, defensible | 77247828.44
Our V3, measured | 77897554.6412
GAP | -649726.2013
0.8% apart. The two budgets were never really in disagreement about the building — only about how much of it had been measured.